## LOI and Commissioning Master Sh
Basis Information | [21 empty] | Information Shared with MSO | [8 empty] | To be Filled By DO | [13 empty] | To be Filled by FO | [16 empty] | To be Filled by Engineers- for A sites SM(Engg) and for B sites by Area Engineer | [11 empty] | by DO
SN | Name of Location | Loi Holder Name | Retail Sales Area | SN of Location | LOI Holder contact details | Market Class | Type | RO/KSK | TYPE OF SITE | Letter of Intent Number | Marketing Plan | LOI Date | LOI Age | LOI Age Analysis | District | Description | Land Offer | Motor Spirit Potential | HSD Potential | Total Potential | Strategic | Commissionable | Comm. Plan in FY26-27 | IO Available/If not available target month (MMM-YY format) | Advanced Tender Approval Status | NA Available (Y/N) | PESO CA Available (Y/N) | NOC Available (Y/N) | NOC Month | Comm. Month | Commissionable | Case of Non-Commissionable | LOI cancellation | Valuation if applicable | Negotiations if applicable | NOC Available | Expected Month of NOC | Concept Note | Estimate | Note Draft | IO Available | IO NO | IO Reamrk | Expected Month of commissioning-Actual | LOI Collected (Yes/No) | LOI Commissionable (Yes/Yes but in next FY/No) | Reason for Non Commissionable and Commissionable in Next FY | If Non Commissionabl, whether recommended for Cancellation (Yes/No) | NOC Applied | Mojnai (Yet to Apply/Applied/Received/NA) | Building Plan Approval and NA (Yet to Apply/Applied/Received/NA) | Police (Yet to Apply/Applied/Received/NA) | NH/PWD (Yet to Apply/Applied/Received/NA) | MSEB (Yet to Apply/Applied/Received/NA) | Dy Dir Industrial safety (Yet to Apply/Applied/Received/NA) | Wild Life (Yet to Apply/Applied/Received/NA) | Forest (Yet to Apply/Applied/Received/NA) | LSR only (Yet to Assign/In Process/Received) | Site Readiness (Yes/No/WIP) | Expected Month of NOC (MMM-YY) | Expected Month of Commg (MMM-YY) | Layout Drawing (Yes/No/Moujani Awaited) | PESO Prior (Yet to Apply/Applied/Received) | BOQ Sent for Approved Cases (Yes/No/NA) | Advance Tender Status(Yet to Publish/Published/Awarded/NA/Approval Awaited) | Tender Publication by RCC Date | WO Number (NOC/IO Awaited) | WO Date | Name of Contractor | WO Completion Target Date Date | Date of Site Handing Over | Expected Date of Commissioning | PESO Final License Status (Applied/Received/Yet to Apply) | Final Commissioning Status | SAP Code | RO Name | LSR assigned to | Valuation assigned to | SRMP | LOI as on 01.04.2026 | MOU Target | LOA No | SAP Code | Name of RO | WIP | LOI Month | Category | MOU | Committed to SO | Admin Approval reference NO | Pending With
119 | Village Yelse on MDR (Pawna lake to Kamshet Road) | DIKSHA SACHIN SONAWANE | Pune Tathawade RSA | 2112 | 9767902929 | E | A | KSK | KSK-A w/o Reco | R/2023/IN003356/MAH/000373/3203/00114 | 2023-24 | 2024-01-24 | 862 | 2-3Y | PUNE | SC | Group 1: Owned land | 30 | 90 | 120 |  | Yes | Yes | Yes | Approved |  |  | Yes | 2026-03-01 | 2026-04-01 | Yes | NA | NA | Yes | Yes | Available | 2026-03-01 | Yes | Yes | Approved | Yes | 4337839 |  | 2026-04-01 | Yes | Yes | LOI holder asking for recon at LOI stage, LSR has come dtd 24.07.24 | NA | Yes | Yes | Yes | Received | Not Required | Received | Received | NA | NA | Received | Yes | 2026-04-01 | 2026-04-01 | Yes | Received |  | Yes | [8 empty] | Commissioned | 391546 | Sai Veenit Petroleum |  |  | SRMP 2023-24 | Yes | Yes |  | 391546 | Sai Veenit Petroleum | Yes | Jan'24 | SC | Yes | Yes
70 | From Kalas to Rui Village on MDR via Gosaviwadi | VIJAY BABAN KALE | Pune Saswad RSA | 2110 | 7499292270 | E | B | KSK | KSK-B w/o Reco | R/2023/IN000625/MAH/000058/3203/00018 | 2023-24 | 2023-11-19 | 928 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 51 | 81 |  | Yes | Yes | Yes | NA |  |  | Yes | 2026-05-01 | 2026-05-01 | Yes | NA | NA | Not Required | Not Required | Available | 2026-05-01 | Yes | Yes | Approved | Yes | 4337720 |  | 2026-05-01 | Yes | Yes |  | NA | Yes | Yes | Received | Received | Received | Received | Received | NA | NA | Received | Yes | 2026-05-26 | 2026-05-26 | Yes | Received | NA | NA | Not Required | 72293969 | 18.05.2026 | PC ENGINEERING CONTRACTORS | 29.06.2026 | 19.05.2026 |  | Applied | Commissioned | 393129 | Vijayraj Petroleum |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Nov'23 | Open | Yes | Yes
75 | From KM stone 33 to 35 on LHS of Khandala Lonand Road | SHEKHAR HANAMANT YADAV | Satara East RSA | 2109 | 7387890252 | E | B | KSK | KSK-B w/o Reco | R/2023/IN001265/MAH/000090/3203/00031 | 2023-24 | 2023-12-04 | 913 | 2-3Y | SATARA | OPEN | Group 1: Owned land | 20 | 80 | 100 |  | Yes | Yes |  | NA |  |  | Yes | 2026-05-01 | 2026-05-01 | Yes | NA | NA | Not Required | Not Required | Available | 2026-05-01 | Yes | Yes | Approved | Yes | 4338576 |  | 2026-05-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Received | Received | NA | NA | NA | Received | WIP | 2026-05-06 | 2026-05-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Commissioned | 392992 | Bhairavnath Petroleum |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | Open | Yes | Yes
79 | WITHIN 5 KM FROM DHEBEWADI PHATA KARAD TOWARDS SATARA ON LHS OF KARAD TO SATARA ROAD | CHINMAY ARVIND GHATE | Satara West RSA | 1925 | 9604101182 | D1 | B | RO | RO B Site | R/2023/IN001436/MAH/000103/3203/00039 | 2023-24 | 2023-12-11 | 906 | 2-3Y | SATARA | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | Yes | NA |  |  | Yes | 2026-05-01 | 2026-05-01 | Yes | NA | NA | Not Required | Not Required | Available | 2026-05-01 | Yes | Yes | Approved | Yes | 4337806 |  | 2026-05-01 | YES | YES | NA | NA | YES | Received | Received | Received | Applied | Received | NA | NA | NA | Received | WIP | 2026-05-26 | 2026-06-26 | Yes | Received | NA | NA | Not Required | [7 empty] | Commissioned | 393128 | Krishna Petroleum and Energy Hub |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | Open | Yes | Yes
123 | From Jadhavwadi to Laxmi Chowk on DP Road | MAYUR SUNIL BORATE | Pimpri Chinchwad RSA | 1801 | 7720000414 | A | A | RO | RO A Site | R/2023/IN003596/MAH/000399/3203/00122 | 2023-24 | 2024-01-31 | 855 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 150 | 50 | 200 |  | Yes | Yes | Yes | Approved | Yes | Yes | Yes | 2026-04-01 | 2026-05-01 | Yes | NA | NA | Yes | Yes | Available | 2026-04-01 | Yes | Yes | Approved | Yes | 4337869 |  | 2026-05-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Not Required | Received | Received | NA | NA | Received | Yes | 2026-04-01 | 2026-05-01 | Yes | Received |  | Yes | [8 empty] | Commissioned | 392301 | S N Borate Petroleum |  |  | SRMP 2023-24 | Yes | Yes |  |  |  | Yes | Jan'24 | Open | Yes | Yes
172 | Within 6 Km from Atmaram Baba Mandir,Mandali towards Solapur on Ahmednagar-Solapur NH | RAMAN PANDHARINATH KHULE | Ahmednagar West RSA | 1721 | 8329858727 | D1 | B | RO | RO B Site | R/2024/IN002364/MAH/000194/3203/00029 | 2023-24 | 2024-06-17 | 717 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 123 | 153 |  | Yes | Yes | Yes | NA |  |  |  | 2026-05-01 | 2026-05-01 | Yes | NA | NA | Not Required | Not Required | Available | 2026-05-01 | Yes | Yes | Approved | Yes | 4338116 |  | 2026-05-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Received | NA | NA | Received | Received | Received | Yes | 2026-03-01 | 2026-05-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Commissioned | 392938 | Gangagiri Petroleum |  |  | SRMP 2023-24 | Yes | Yes |  |  |  | Yes | Jun'24 | Open | Yes | Yes
203 | From Bhigwan Circle to Dalaj Phata on RHS of Pune- Solapur Highway | KUNDALIK UTTAM KAMBLE | Pune Saswad RSA | 1665 | 9960252231 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002520/MAH/000255/3203/00078 | 2023-24 | 2024-06-20 | 714 | 1-2Y | PUNE | SC | Group 2: Firm Offer | 30 | 130 | 160 |  | Yes | Yes | Yes | Approved |  |  | Yes | 2026-04-01 | 2026-05-01 | Yes | NA | NA | Yes | Yes | Available | 2026-04-01 | Yes | Yes | Approved | Yes | 4338194 |  | 2026-05-01 | Yes | Yes | NA | NA | Yes | Yes | Received | Received | Received | Received | Received | NA | NA | Received | Yes | 2026-03-26 | 2026-05-26 | Yes | Received |  | Yes | [8 empty] | Commissioned | 392994 | Mauli Petroleum |  |  | SRMP 2023-24 | Yes | Yes | R/2026/IN000139/3203/00004 |  |  |  | Jun'24 | SC | Yes | Yes
218 | At Village Karhavagaj on Jejuri-Morgaon-Baramati Road | BALASAHEB LIMBAJI AGAWANE | Pune Tathawade RSA | 1736 | 9922414802 | D2 | A | RO | RO A Site-Corpu | R/2024/IN003547/MAH/000391/3203/00107 | 2023-24 | 2024-09-12 | 630 | 1-2Y | PUNE | SC | Group 1: Owned land | 30 | 80 | 110 |  | Yes | Yes | Yes | Approved | Yes | No | Yes | 2026-05-01 | 2026-05-01 | Yes | NA | NA | Yes | Yes | Available | 2026-05-01 | Yes | Yes | Approved | Yes | 4338515 |  | 2026-05-01 | Yes | Yes | DM NOC received on 08.05.2026 | NA | Yes | Yes | Yes | Received | Received | Received | Received | NA | NA | Received | WIP | 2026-02-01 | 2026-11-01 | Yes | Received |  | Yes | [8 empty] | Commissioned | 393015 | Ahilya Petroleum |  |  | SRMP 2023-24 | Yes | Yes | R/2026/IN000141/3203/00005 |  |  |  | Sep'24 | SC | Yes | Yes
62 | AT VADAPURI ON LHS OF INDAPUR-AKLUJ ROAD , | VISHRAM MORE | Pune Saswad RSA |  | 9850601522 | D1 | A | RO | RO A Site-Corpu | M/2022/IN001731/MAH/000117/3203/00043 | 2018-19 | 2023-03-27 | 1165 | 3-4Y | PUNE | ST | Group 2: Firm Offer | 40 | 110 | 150 |  | Yes | Yes | 2026-06-01 | Approved |  |  |  | 2026-06-01 | 2026-06-01 | Yes | NA | NA | Yes | Yes |  | 2026-06-01 | Yes | Yes | Sent | No |  |  | 2026-06-01 | Yes | Yes | LSR dtd 11.05.2023. Supple LSR dtd 29.07.24 has come- IO to be taken | NA | Yes | Yes | Received | Received | Applied | Received | Received | NA | NA | Received | Yes | 2026-06-26 | 2026-06-26 | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | Yes |  |  |  |  | Mar'23 | st | Yes | Yes | Administrative Approval/3203/SL01/2025-2026/138315
72 | Within 3 KM from Akshata Mangal Karyalaya towards Taklibhan on Shrirampur Nevasa SH | PRASAD BALASAHEB CHAUDHARI | Ahmednagar East RSA | 1818 | 9822603682 | D2 | B | RO | RO B Site | R/2023/IN000927/MAH/000071/3203/00022 | 2023-24 | 2023-11-27 | 920 | 2-3Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 85 | 115 |  | Yes | Yes | Yes | NA |  |  |  | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-05-01 | Yes | Yes | Approved | Yes | 4337692 |  | 2026-06-01 | Yes | Yes | NA | NA | Yes | Received | Applied | Received | Received | Received | NA | Received | Received | Received | Yes | 2026-06-01 | 2026-06-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Nov'23 | OBC | Yes | Yes
96 | From Kasar-Dumala to Chikhali on Sangamner Akole SH | MADHURI RAVINDRA SHENKAR | Shirdi RSA | 1954 | 9156559088 | D2 | A | RO | RO A Site-Corpu | R/2023/IN001869/MAH/000198/3203/00074 | 2023-24 | 2023-12-19 | 898 | 2-3Y | AHMADNAGAR | ST | Group 1: Owned land | 30 | 85 | 115 |  | Yes | Yes | Yes | Approved |  |  |  | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Yes | Yes |  | 2026-05-01 | Yes | Yes | Approved | Yes | 4338093 |  | 2026-06-01 | Yes | Yes | NA | NA | Yes | Recieved | Applied | Recieved | Recieved | Recived | NA | Recived | Recived | Received | WIP | 2026-06-20 | 2026-08-31 | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | st | Yes | Yes
103 | On RHS of Pune-Solapur NH, From Vangali to intersection of Indapur Bypass & Baramati Highway | OMKAR GIRISH SHAH | Pune Saswad RSA | 1897 | 9730606767 | D1 | A | RO | RO A Site | R/2023/IN002958/MAH/000314/3203/00093 | 2023-24 | 2024-01-16 | 870 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | Yes | Approved |  |  |  | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Yes | Yes |  | 2026-05-01 | Yes | Yes | Approved | Yes | 4337433 |  | 2026-06-01 | Yes | Yes | All NOCs are send for revalidation and awaited | NA | Yes | Yes | Received | Received | Received | Received | Received | NA | NA | Received | Yes | 2026-06-01 | 2026-06-26 | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jan'24 | Open | Yes | Yes
140 | FROM SHITPUR PHATA TO NIMBODI PHATA ON SHRIGONDA - JAMKHED ROAD | PRASHANT BAPURAO GAIKWADE | Ahmednagar West RSA | 1738 | 9960968999 | D1 | B | RO | RO B Site | R/2023/IN004897/MAH/000498/3203/00150 | 2023-24 | 2024-02-27 | 828 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | Yes | NA |  |  |  | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Not Required | Not Required | Available | 2026-05-01 | Yes | Yes | Approved | Yes | 4338435 | NHAI Access Pending | 2026-06-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Applied | NA | NA | Received | Received | Received | Yes | 2026-05-01 | 2026-05-01 | Yes | Received | NA | NA | Not Required |  |  | PVT. LTD. |  |  |  |  | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'24 | Open | Yes | Yes
139 | From Navnagapur to Shendi on Shendi Bypass | AKSHAY PRAKASH CHAVAN | Ahmednagar East RSA | 1754 | 9923563624 | D2 | A | RO | RO A Site-Corpu | R/2023/IN004910/MAH/000499/3203/00151 | 2023-24 | 2024-02-27 | 828 | 2-3Y | AHMADNAGAR | ST | Group 1: Owned land | 30 | 100 | 130 |  | Yes | Yes |  | Approved |  |  | Yes | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Yes | Yes | Available | 2026-05-01 | Yes | Yes | Sent | Yes | 4338635 |  | 2026-06-01 | Yes | Yes | NA | NA | Yes | Received | Recieved | Received | Received | Received | NA | Received | Received | Received | Yes | 2026-05-01 | 2026-06-01 | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'24 | st | Yes | Yes | Administrative Approval/3203/SL01/2025-2026/141407
141 | Within 2 Km from DBM English Medium School on either side on Parner to Pune Highway (SH) | SANDIP BHASKAR NIKAM | Ahmednagar West RSA | 1976 | 7875162400 | D2 | A | RO | RO A Site-Corpu | R/2023/IN005327/MAH/000515/3203/00154 | 2023-24 | 2024-03-06 | 820 | 2-3Y | AHMADNAGAR | PHP ( ST ) | Group 1: Owned land | 20 | 80 | 100 |  | Yes | Yes |  | Approved |  |  | Yes | 2026-04-01 | 2026-06-01 | Yes | NA | NA | Yes | Yes | Available | 2026-04-01 | Yes | Yes | Sent | No |  |  | 2026-06-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Received | NA | NA | Received | Received | Received | Yes | 2026-04-01 | 2026-06-01 | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Mar'24 | st | Yes | Yes | Administrative Approval/3203/SL01/2025-2026/130023
157 | From Bahul to Sablewadi on LHS on NH (Chakan-Shikrapur Road) | PRAKASH SHANKAR LIMBHORE | Pune Wagholi RSA | 1842 | 8668477069 | D1 | B | RO | RO B Site | R/2024/IN002040/MAH/000089/3203/00004 | 2023-24 | 2024-06-13 | 721 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 40 | 181 | 221 |  | Yes | Yes | Yes | NA |  |  |  | 2026-01-01 | 2026-06-01 | Yes | NA | NA | Not Required | Not Required | Yes(P) | 2026-01-01 | Yes | Yes | Approved | Yes | 4337666 |  | 2026-06-01 | Yes | Yes | NA | No | Yes | yes | Yes | Yes | Yes | Yes | Yes | NA | NA | Received | Yes | 2026-06-01 | 2026-06-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  | Yes | Jun'24 | Open | Yes | Yes
161 | From Km Stone 8 to Km Stone 12 on Ahmednagar-Daund NH | AMRUTA VISHAL LOTAKE | Ahmednagar West RSA | 1716 | 9273739191 | D1 | B | RO | RO B Site | R/2024/IN002247/MAH/000179/3203/00014 | 2023-24 | 2024-06-15 | 719 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 35 | 120 | 155 |  | Yes | Yes | Yes | NA |  |  |  | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-05-01 | Yes | Yes | Approved | Yes | 4337973 |  | 2026-06-01 | Yes | Yes | NA | NA | Yes | Received | Yes | Received | Received | NA | NA | Received | Received | Received | Yes | 2026-06-01 | 2026-06-26 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | Open | Yes | Yes
200 | From Pingali Budruk To Gondawale Budruk on RHS on Satara Pandharpur Road | AKSHAYKUMAR RAOSAHEB BABAR | Satara East RSA | 1988 | 9765191946 | D1 | B | RO | RO B Site | R/2024/IN002500/MAH/000244/3203/00072 | 2023-24 | 2024-06-19 | 715 | 1-2Y | SATARA | OPEN | Group 1: Owned land | 40 | 110 | 150 |  | Yes | Yes | Yes | NA |  |  |  | 2026-07-01 | 2026-06-01 | Yes |  |  | Not Required | Not Required | Available | 2026-07-01 | 46478 | Yes | Approved | Yes | 4338611 | NHAI Access Pending | 2026-06-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Applied | Received | NA | NA | NA | Received | Yes | 2026-05-01 | 2026-06-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
233 | Within 3km From Jawakhede Khalsa Primary Health Sub Centre Towards Miri on Miri-Tisgaon Road (MDR) | CHARUDATTA UDDHAVRAO WAGH | Ahmednagar West RSA | 2106 | 9881916750 | E | B | KSK | KSK-B w/o Reco | R/2024/IN004699/MAH/000470/3203/00129 | 2023-24 | 2025-02-11 | 478 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 28 | 80 | 108 |  | Yes | Yes |  | NA |  |  |  | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-05-01 | Yes | Yes | Sent | No |  | LSR received | 2026-06-01 | Yes | Yes | NA | NA | Yes | Received | Applied | Received | Applied | NA | NA | Received | Received | In Process | Yes | 2026-06-01 | 2026-06-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'25 | Open | Yes | Yes | Administrative Approval/3203/SL01/2026-2027/18664
253 | From Talegaon Damdhere to Dhanore within 2km on SH (Talegaon Dhamdere - Pimpri Sandas Road) | MANOHAR VISHNU DHAMDHERE | Pune Wagholi RSA | 1783 | 9921224142 | D2 | B | RO | RO B Site | R/2025/IN000578/MAH/000077/3203/00018 | 2023-24 | 2025-11-03 | 213 | 6-12M | Pune | OPEN | Group 1: Owned land | 30 | 77 | 107 |  | Yes | Yes |  | NA |  |  | Yes | 2026-05-01 | 2026-06-01 | Yes | NA | NA | Not Required | Not Required | Available | 2026-05-01 | Yes | Yes | Approved | Yes | 4338612 |  | 2026-06-01 | Yes | yes | NA | no | Yes | Yes | yes | yes | Received | Yes | Yes | NA | NA | Received | WIP | 2026-05-25 | 2026-06-26 | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Nov'25 | Open | Yes | Yes
120 | On RHS From Lohare to Talegaon Dighe on Talegaon Dighe-Loni NH | BHAGWAN RAMESH MUTADAK | Shirdi RSA | 1881 | 9260271806 | D1 | B | RO | RO B Site | R/2023/IN003357/MAH/000374/3203/00115 | 2023-24 | 2024-01-24 | 862 | 2-3Y | AHMADNAGAR | OBC | Group 1: Owned land | 40 | 120 | 160 |  | Yes | Yes | Yes | NA |  |  |  | 2026-06-01 | 2026-07-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-06-01 |  | Yes | Approved | Yes | 4337686 |  | 2026-07-01 | Yes | Yes | NA | NA | Yes | Recieved | Applied | Recieved | Applied | Recived | NA | Recived | Recived | Received | WIP | 2026-07-31 | 2026-08-31 | Yes | To be applied | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jan'24 | OBC | Yes | Yes
195 | Dehu Phata to Moshi Chowk on RHS on Dehu - Alandi Road | VINOD MARUTI PARANDE | Pimpri Chinchwad RSA | 1949 | 9881999678 | A | B | RO | RO B Site | R/2024/IN002478/MAH/000232/3203/00061 | 2023-24 | 2024-06-19 | 715 | 1-2Y | PUNE | OPEN | Group 2: Firm Offer | 150 | 50 | 200 |  | Yes | Yes | Yes | NA | Yes | Yes |  | 2026-07-01 | 2026-07-01 | Yes |  |  | Not Required | Not Required | Yes(P) | 2027-06-01 |  | Yes | Approved | Yes | 4337491 | There is complaint related to Land, Mojani has been cancelled. Matter is subjudiced. Court orders are in our favor. PCMC commissioner has suspended the NOC temporarily.Meeting planned in We expect ervoke of suspension and remojani by Feb'26. | 2027-07-02 | Yes | Yes | There is court case Going on at Site, hence Commissioning will get delayted. NOC and Mojani has been canc elled by administration based on complaint received for the locaiton | NA | Yes | Received | Received | Received | Not Required | Received | Received | NA | NA | Received | Yes | 2026-09-01 | 2026-09-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open |  | Yes
208 | Within 4km from Within 4 km from M.M.Nirhali College, Pathardi towards baramat on Baramati-Amrapur SH | VAISHALI RAMESH BARDE | Ahmednagar West RSA | 1837 | 9763122772 | D2 | B | RO | RO B Site | R/2024/IN002781/MAH/000309/3203/00093 | 2023-24 | 2024-07-06 | 698 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 70 | 100 |  | Yes | Yes | Yes | NA |  |  |  | 2026-06-01 | 2026-07-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-06-01 | Yes | Yes | Approved | Yes | 4337805 |  | 2026-07-01 | Yes | Yes | NA | NA | Yes | Received | Yes | Received | Yet to apply | NA | NA | Received | Received | Received | No | 2026-09-26 | 2026-10-26 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jul'24 | OBC | Yes | Yes
22 | ON NH-4 BETWEEN KM STONE 760 TO 755 LHS OF PUNE TO SATARA ROAD | Yashodhan Shinde | Satara West RSA | 2018-129 | 9881321999 | D1 | B | RO | RO B Site | M/2018/IN002023/MAH/000207/3203/00064 | 2018-19 | 2019-03-12 | 2641 | >5Y | SATARA | OPEN | Group 2: Firm Offer | 40 | 110 | 150 |  | Yes | Yes | Yes | NA |  |  |  | 2026-07-01 | 2026-08-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-07-01 | Yes | Yes | Approved | Yes |  | LSR Awaited | 2026-08-01 | YES | YES | NA | NA | YES | Received | Received | Applied | Applied | Received | NA | NA | NA | In process | WIP | 2026-07-26 | 2026-08-26 | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | Yes |  |  |  |  | Mar'19 | Open | Yes | Yes
74 | Within 2 km from Chapadgaon Junction towards koregaon on Chapadgaon-Koregaon Road MDR Tal- Karjat | DNYANESHWAR RAMDAS SHINDE | Ahmednagar West RSA | 2095 | 9960927710 | E | B | KSK | KSK-B w/o Reco | R/2023/IN001195/MAH/000083/3203/00024 | 2023-24 | 2023-12-01 | 916 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 38 | 70 | 108 |  | Yes | Yes |  | NA |  |  |  | 2026-07-01 | 2026-08-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-07-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited, land change case | 2026-08-01 | Yes | Yes | NA | NA | Yes | Received | Applied | Applied | Not Required | NA | NA | Applied | Applied | In process | No | 2026-09-26 | 2026-10-26 | Yes | To be applied | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | Open | Yes | Yes
162 | Within 3 KM from Varunji Phata Karad Towards Chiplun On Karad Chiplun Road | NITIN DINKAR PATIL | Satara West RSA | 1608 | 8805000393 | D1 | B | RO | RO B Site | R/2024/IN002258/MAH/000183/3203/00018 | 2023-24 | 2024-06-15 | 719 | 1-2Y | SATARA | OPEN | Group 1: Owned land | 80 | 90 | 170 |  | Yes | Yes | 2026-08-01 | NA |  |  |  | 2026-07-01 | 2026-08-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-07-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2026-08-01 | YES | YES | NA | NA | YES | Received | Applied | Received | Applied | Received | NA | NA | NA | In Process | WIP | 2026-07-26 | 2026-08-26 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  | BS |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | Open | Yes | Yes
201 | Within 5 Km from Tasawde Toll plaza towards Karad On RHS of Pune to Satara NH | SWATI VIKRAM SHIVDAS | Satara West RSA | 1581 | 9822303957 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002508/MAH/000251/3203/00075 | 2023-24 | 2024-06-19 | 715 | 1-2Y | SATARA | SC | Group 1: Owned land | 40 | 110 | 150 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2026-07-01 | 2026-08-01 | Yes | NA | NA | Yes | Pending |  | 2026-07-01 | Yes | Pending | To be Initiated | No |  | LSR Awaited | 2026-08-01 | YES | YES | NA | NA | YES | Received | Applied | Received | Applied | Received | NA | NA | NA | In Process | No | 2026-07-26 | 2026-09-26 | Yes | Received |  | Pending | [8 empty] | Pending |  |  | BS | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | SC | Yes | Yes
265 | From Sawarchol to Nimgoan bk. on Sangamer-Kotul SH | HOUSHIRAM MARUTI MECHKAR | Shirdi RSA | 104 | 8805752023 | D2 | A | RO | RO A Site-Corpu | R/2025/IN000872/MAH/000099/3203/00030 | 2023-24 | 2026-03-18 | 78 | 0-6M | AHMADNAGAR | ST | Group 1: Owned land | 25 | 75 | 100 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2026-07-01 | 2026-08-01 | Yes |  |  | In Process | Pending |  | 2026-07-01 | Pending | Pending | To be Initiated |  |  | LSR Awaited | 2026-08-01 | Yes | Yes | LOI given in March 26 and need to see candidate progress for some time to conclude. | NA | Yes | Recieved | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | Yet to Apply | Yet to Apply | In Process | No | 2026-12-31 | 2027-03-30 | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  | AG on 14.05.2026 | Ellen and Gosavi on 180526 | SRMP 2023-24 | Yes | [5 empty] | Mar'26 | st
66 | WITH IN 5 KM FROM MORGAON ON LHS OF MORGAON -BARAMATI ROAD , | PURUSHOTTAM KADAM | Pune Tathawade RSA | 54 | 9665080752 | D2 | A | RO | RO A Site-Corpu | M/2023/IN000132/MAH/000015/3203/00009 | 2018-19 | 2023-05-01 | 1130 | 3-4Y | PUNE | SC | Group 1: Owned land | 30 | 90 | 120 |  | Yes | Yes | 2026-09-01 | Approved |  |  |  | 2026-07-01 | 2026-09-01 | Yes | NA | NA | Yes | Yes |  | 2026-07-01 | Yes |  | Sent | No |  |  | 2026-09-01 | Yes | Yes | PWD NOC pending | NA | Yes | Yes | Yes | Received | Applied | Received | Received | NA | NA | Received | WIP | 2026-07-01 | 2026-11-01 | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | Yes |  |  |  |  | May'23 | SC | Yes | Yes | Administrative Approval/3203/SL01/2025-2026/172925
90 | Within 3 Km from Ghodegaon Sonai Chowk towards Ahmednagar on Pune-Aurangabad NH | PRITI ATMARAM PAWAR | Ahmednagar East RSA | 96 | 8668904185 | D1 | A | RO | RO A Site-Corpu | R/2023/IN001620/MAH/000160/3203/00058 | 2023-24 | 2023-12-14 | 903 | 2-3Y | AHMADNAGAR | ST | Group 1: Owned land | 40 | 135 | 175 |  | Yes | Yes | 2026-09-01 | Yet to Initiate |  |  |  | 2026-07-01 | 2026-09-01 | Yes | NA | NA | Yes | Yes |  | 2026-07-01 | Yes | Pending | Sent | No |  |  | 2026-09-01 | Yes | Yes | NA | NA | Yes | Received | Applied | Received | Applied | Received | NA | Received | Received | Received | WIP | 2026-07-01 | 2026-09-01 | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | st | Yes | Yes | Administrative Approval/3203/SL01/2026-2027/18041
93 | From Village Walwane to Village Raytale on Supe Sarolakasar Road SH | AKASH SHANTILAL PATHARE | Ahmednagar West RSA | 1592 | 8530744612 | D2 | B | RO | RO B Site | R/2023/IN001673/MAH/000169/3203/00062 | 2023-24 | 2023-12-15 | 902 | 2-3Y | AHMADNAGAR | OBC | Group 1: Owned land | 25 | 80 | 105 |  | Yes | Yes |  | NA |  |  |  | 2026-08-01 | 2026-09-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-09-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2026-10-01 | Yes | Yes | NA | NA | Yes | Received | Applied | Applied | Yet to Apply | NA | NA | Applied | Applied | In process | No | 2026-09-26 | 2026-10-26 | Yes | To be applied | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | OBC | Yes | Yes
109 | From Village Pargaon Shingave to Village Manjarwadi on RHS on SH | RAMKRUSHNA RAMCHANDRA JANBHOR | Pune Wagholi RSA | 2076 | 9860520267 | D2 | B | RO | RO B Site | R/2023/IN003093/MAH/000338/3203/00098 | 2023-24 | 2024-01-18 | 868 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 40 | 80 | 120 |  | Yes | Yes | Yes | NA |  |  |  | 2026-08-01 | 2026-09-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-09-01 | Yes | Yes | Approved | Yes | 4338613 | PWD junction issue. Land comes within 300 Mt of junction. PWQD file sent for relaxation approval | 2026-10-01 | Yes | Yes but in next FY | PWD junction issue. Land comes within 300 Mt of junction. PWQD file sent for relaxation approval | No | Yes | Yes | Yes | Yes | Applies | Yes | yes | NA | NA | Received | No | 2026-05-01 | 2026-06-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jan'24 | Open | Yes | Yes
124 | Moshi Chowk on Pune Nashik Road to Talwade Chowk on LHS on Dehu Alandi Road (within PCMC Limits) | SACHIN PANDURANG BORATE | Pimpri Chinchwad RSA | 1672 | 9356705562 | A | A | RO | RO A Site | R/2023/IN003662/MAH/000405/3203/00125 | 2023-24 | 2024-02-01 | 854 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 150 | 50 | 200 |  | Yes | Yes | No | Approved |  |  |  | 2026-08-01 | 2026-09-01 | Yes | NA | NA | Yes | Yes | Yes(P) | 2026-12-01 | Yes | Yes | Sent | No |  |  | 2026-10-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Not Required | Received | Received | NA | NA | Received | WIP | 2026-10-01 | 2026-11-01 | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'24 | Open | Yes | Yes | Administrative Approval/3203/SL01/2026-2027/19224
173 | From Kapurhol to Kikvi on RHS on NH (Pune-Bangalore Highway) | SWAPNIL RAMDAS CHARWAD | Pune Tathawade RSA | 1712 | 9766110001 | D1 | B | RO | RO B Site | R/2024/IN002366/MAH/000196/3203/00030 | 2023-24 | 2024-06-17 | 717 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 40 | 120 | 160 |  | Yes | Yes | Yes | NA |  |  |  | 2026-07-01 | 2026-09-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-07-01 | Yes | Yes | Approved | Yes | 4338053 |  | 2026-09-01 | Yes | Yes | Provisional NH NOC pending and SP NOC pending | NA | Yes | Yes | Yes | Applied | Applied | Received | Received | NA | NA | Received | WIP | 2026-07-01 | 2026-11-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | Open | Yes | Yes
229 | Bhose to Shelpimpalgaon on LHS on Chakan Shikrapur Road | RAJABHAU MOTIRAM BANSODE | Pimpri Chinchwad RSA | 2030 | 7030954444 | D1 | A | RO | RO A Site-Corpu | R/2024/IN004518/MAH/000463/3203/00124 | 2023-24 | 2025-01-02 | 518 | 1-2Y | PUNE | SC | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | Yes | Approved | NA |  |  | 2026-01-01 | 2026-09-01 | Yes | NA | NA | Yes | Yes | Yes(P) | 2026-01-01 | Yes | Yes | Approved | Yes |  |  | 2026-09-01 | Yes | Yes | NA | NA | Yes | Received | Received | Received | Received | Received | Received | NA | NA | Received | Yes | 2026-09-01 | 2026-10-01 | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jan'25 | SC | Yes | Yes | Administrative Approval/3203/SL01/2025-2026/130494
104 | Within 3 Km From Dr Ambedkar Chowk (Kakadi) towards Korhale on RHS of Airport-Shirdi Road (MDR) | YASRAJ HARISHCHANDRA BHUSHARI | Shirdi RSA | 2111 | 9112735899 | E | A | KSK | KSK-A w/o Reco | R/2023/IN002952/MAH/000313/3203/00092 | 2023-24 | 2024-01-16 | 870 | 2-3Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | Yes | Approved |  |  |  | 2026-09-01 | 2026-10-01 | Yes |  |  | Yes | Yes |  | 2026-09-01 | Pending | Yes | Approved | Yes | 4338490 | frontage is 30 M against PWD requirement of 35 Mt. | 2026-10-01 | Yes | Yes | NA | NA | Yes | Recieved | Applied | Recieved | Applied | Recived | NA | Recived | Recived | Received | No | 2026-08-31 | 2026-12-31 | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | OBC
122 | AT JEUR ON AHMEDNAGAR-AURANGABAD ROAD | RANJANA RAJIV SALVE | Ahmednagar East RSA | 2018-766 | 9309939919 | D1 | A | RO | RO A Site-Corpu | M/2023/IN003549/MAH/000389/3203/00121 | 2018-19 | 2024-01-30 | 856 | 2-3Y | AHMADNAGAR | SC | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2026-09-01 | 2026-10-01 | Yes | NA | NA | Yes | Pending |  | 2026-09-01 | Yes | Pending | To be Initiated | No |  | Negotiation Pending | 2026-10-01 | Yes | Yes | NA | NA | Yes | Received | Yet to Apply | Received | Applied | Received | NA | Received | Received | Received | No | 2027-01-01 | 2027-02-01 | Yes | [11 empty] | Pending |  |  | Received | Received | SRMP 2018-19 | Yes | [5 empty] | Jan'24 | SC
132 | Within 2 KM from Medha Bus Stand towards Satara on Mahabaleshwar Satara Road | RUPALI KISAN SABLE | Satara West RSA | 97 | 8788144518 | D2 | A | RO | RO A Site-Corpu | R/2023/IN004334/MAH/000466/3203/00142 | 2023-24 | 2024-02-16 | 839 | 2-3Y | SATARA | ST | Group 1: Owned land | 22 | 90 | 112 |  | Yes | Yes | 2026-10-01 | Yet to Initiate |  |  |  | 2026-09-01 | 2026-10-01 | Yes | NA | NA | Yes | Pending |  | 2026-09-01 | Pending | Pending | To be Initiated | No |  | LSR Awaited, Financially week | 2026-10-01 | YES | YES | NA | NA | YES | Received | Applied | Applied | NA | Received | NA | NA | NA | In Process |  | 2026-09-26 | 2026-11-26 | Yes | Received |  | Pending | [8 empty] | Pending |  |  | BS | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'24 | st | Yes | Yes
156 | From km stone 56 to 58 on RHS on SH (Belhe -Jejuri road) | CHETAN NAMDEV DESHMUKH | Pune Wagholi RSA | 1805 | 8956677327 | D2 | B | RO | RO B Site | R/2024/IN002109/MAH/000114/3203/00005 | 2023-24 | 2024-06-13 | 721 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 20 | 84 | 104 |  | Yes | Yes | 2026-10-01 | NA |  |  |  | 2026-09-01 | 2026-10-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-09-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2026-10-01 | Yes | Yes | Commissionable | No | Yes | Yes | No | Yes | Yet to Apply | Applied | Yes | NA | NA | Received | WIP | 2026-07-26 | 2026-07-26 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | Open | Yes | Yes
155 | On LHS From Lohare to Talegaon Dighe on Talegaon Dighe-Loni NH | GAURAV GORAKSHA SANAP | Shirdi RSA | 1618 | 8693000910 | D1 | B | RO | RO B Site | R/2024/IN002007/MAH/000078/3203/00001 | 2023-24 | 2024-06-13 | 721 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 40 | 120 | 160 |  | Yes | Yes | 2026-10-01 | NA |  |  |  | 2026-09-01 | 2026-10-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-09-01 | Yes | Yes | To be Initiated | No |  |  | 2026-10-01 | Yes | Yes | NA | NA | Yes | Recieved | Applied | Recieved | Applied | Recived | NA | Recived | Recived | Yet to Assign | No | 2026-09-30 | 2026-10-31 | Yes | Applied but not received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | OBC | Yes | Yes
165 | Village Koradgaon Taluka Pathardi | NILESH PANDURANG GHULE | Ahmednagar West RSA | 2104 | 9011668400 | E | B | KSK | KSK-B w/o Reco | R/2024/IN002245/MAH/000177/3203/00012 | 2023-24 | 2024-06-15 | 719 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 20 | 40 | 60 |  | Yes | Yes | No | NA |  |  |  | 2026-09-01 | 2026-10-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-09-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2026-10-01 | Yes | Yes | NA | NA | Yes | Received | Yes | Applied | Not Required | NA | NA | Applied | Applied | In process | No | 2026-09-26 | 2026-10-26 | Yes | To be applied | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | OBC | Yes | Yes
174 | From Vadapuri to Vakilwasti on LHS of Indapur-Akluj NH | VIJAYSINH DATTATRAYA SHIRKE | Pune Saswad RSA | 1686 | 7709553333 | D1 | B | RO | RO B Site | R/2024/IN002360/MAH/000190/3203/00025 | 2023-24 | 2024-06-17 | 717 | 1-2Y | PUNE | OPEN | Group 2: Firm Offer | 40 | 130 | 170 |  | Yes | Yes | 2026-10-01 | NA |  |  |  | 2026-09-01 | 2026-10-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-09-01 | Yes | Yes | To be Initiated | No |  | TSR is not clear | 2026-10-01 | Yes | Yes |  | NA | Yes | Yes | Applied | Applied | Applied | Received | Received | NA | NA | In process | No | 2026-09-26 | 2026-10-26 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | Open | Yes | Yes
77 | From ALAGUDEWADI To SOMANTHALI ON PHALTAN BARAMATI ROAD | ROHIT MAHADEV POKALE | Satara East RSA | 1961 | 9975251537 | D1 | B | RO | RO B Site | R/2023/IN001291/MAH/000094/3203/00035 | 2023-24 | 2023-12-05 | 912 | 2-3Y | SATARA | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | Yes | NA |  |  |  | 2026-10-01 | 2026-11-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-10-01 | Yes | Yes | Approved | Yes | 4337974 |  | 2026-11-01 | Yes | Yes | NA | NA | Yes | Received | Applied | Received | Applied | Received | NA | NA | NA | Received | WIP | 2026-10-30 | 2026-11-30 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | Open | Yes | Yes
206 | On RHS From Venavadi to Ambeghar on National Highway (Bhor-Shirwal Road) | VISHWAJIT VIKRAM CHAVAN | Pune Tathawade RSA | 1873 | 9130821872 | D1 | B | RO | RO B Site | R/2024/IN002552/MAH/000261/3203/00081 | 2023-24 | 2024-06-21 | 713 | 1-2Y | PUNE | OBC | Group 1: Owned land | 50 | 110 | 160 |  | Yes | Yes |  | NA |  |  |  | 2026-10-01 | 2026-11-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-10-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2026-11-01 | Yes | Yes | TP plan to be applied online and Provisional NH NOC pending, LSR pending , candidate to complete lease with the Land owner | NA | Yes | Yes | Yet to apply | Applied | Applied | Received | Received | NA | NA | In Process | No | 2026-10-01 | 2026-11-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | OBC | Yes | Yes
217 | within 2 km on Either side of Zilla parishad Primary school, Sakat on Jamkhed-Patoda Road NH | RUSHIKESH MOHAN LAHANE | Ahmednagar West RSA | 1819 | 7272909666 | D1 | B | RO | RO B Site | R/2024/IN003519/MAH/000387/3203/00105 | 2023-24 | 2024-09-06 | 636 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | 2026-11-01 | NA |  |  |  | 2026-10-01 | 2026-11-01 | Yes |  |  | Not Required | Not Required |  | 2026-10-01 | Yes | Yes | To be Initiated |  |  | Very Slow Candidate | 2026-11-01 | Yes | Yes | NA | NA | Yes | Received | In process | Yet to apply | Yet to Apply | NA | NA | Yet to apply | Yet to apply | Yet to assign | No | 2026-10-01 | 2026-11-01 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Sep'24 | Open
240 | From Jejuri MIDC to Nira on LHS on Pune - Pandharpur Road (NH) | PRANJAL PANKAJ GHONE | Pune Saswad RSA | 102 | 8237342043 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000092/MAH/000013/3203/00005 | 2023-24 | 2025-05-06 | 394 | 1-2Y | PUNE | SC | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2026-09-01 | 2026-11-01 | Yes | NA | NA | Yes | Pending |  | 2026-09-01 | Pending | Pending | To be Initiated | No |  | LSR Awaited | 2026-11-01 | Yes | Yes |  | NA | Yes | Yes | Received | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2026-09-26 | 2026-10-26 | Yes | Received |  | Pending | [8 empty] | Pending |  |  | AN on 02.04.2026 | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | May'25 | SC | Yes | Yes
24 | VILLAGE KAPADGAON ON NH-965 LONAND PHALTAN ROAD | GANESH GALINDE | Satara East RSA |  |  | D1 | A | RO | RO A Site-Corpu | M/2018/IN002081/MAH/000216/3203/00066 | 2018-19 | 2019-03-23 | 2630 | >5Y | SATARA | SC | Group 1: Owned land | 25 | 135 | 160 |  | Yes | Yes | Yes | Approved | Yes | Yes | Yes | 2025-06-01 | 2026-12-01 | Yes | NA | NA | Yes | Yes | Available | 2025-06-01 | Yes | Yes | Approved | Yes | 4327589 | NOC is available for the site. However there are 4 landowners in undivided land in 7/12 extract out of which 2 sisters are not giving consent for lease deed execution. 2 tanks lowered. Lease pending, moreover traffic will be shifted from the location to lonand bypass | 2026-12-01 | Yes | Yes | Court case pending on land and because of that land lease is pending | NA | Yes | Received | Received | Received | Received | Received | NA | NA | NA | Received | Yes | 2025-06-30 | 2027-05-31 | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | Yes |  |  |  |  | Mar'19 | SC |  | Yes
107 | Gharkul Chowk to Jadhav Sarkar Chowk on Spine Road | GOVARDHAN SOMNATH KHANDAGALE | Pimpri Chinchwad RSA | 1667 | 7776079495 | A | A | RO | RO A Site | R/2023/IN002975/MAH/000315/3203/00094 | 2023-24 | 2024-01-16 | 870 | 2-3Y | PUNE | OPEN | Group 2: Firm Offer | 120 | 80 | 200 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2026-12-01 | 2026-12-01 | Yes | NA | NA | Yes | Pending |  | 2026-12-01 | Yes | Pending | To be Initiated | No |  | Negotiation Pending | 2027-03-01 | Yes | Yes | NA | NA | Yes | Yes | Applied | Applied | Not Required | Applied | Yes | NA | NA | Received | Yes | 2026-06-01 | 2026-11-01 | Yes | Received |  | Pending | [8 empty] | Pending |  |  | Received | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jan'24 | Open | Yes | Yes
115 | From Nhavare to Nirvi on NH (Nhavare-Shrigonda Road) | ANIL BALASAHEB WABLE | Pune Wagholi RSA | 1575 | 9890034141 | D1 | B | RO | RO B Site | R/2023/IN003314/MAH/000366/3203/00112 | 2023-24 | 2024-01-23 | 863 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 40 | 153 | 193 |  | Yes | Yes | 2026-12-01 | NA |  |  |  | 2026-11-01 | 2026-12-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-11-01 | Yes | Yes | To be Initiated | No |  | Very Slow Candidate | 2026-12-01 | Yes | Yes but in next FY | SLOW CANDIDATE |  | Yes | Yes | No | No | Yet to Apply | No | Na | na | NA | Yet to Assign | No | 2027-01-01 | 2025-12-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jan'24 | Open | Yes | Yes
158 | From Dahigaon Ne. to Khamgaon on Dahigaon-Khamgaon Road | DNYANESHWAR NAMDEV KALE | Ahmednagar East RSA | 2107 | 9011604232 | E | B | KSK | KSK-B w/o Reco | R/2024/IN002143/MAH/000133/3203/00007 | 2023-24 | 2024-06-13 | 721 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 20 | 40 | 60 |  | Yes | Yes |  | NA |  |  |  | 2026-11-01 | 2026-12-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-11-01 | Yes | Yes | Approved | Yes | 4338619 |  | 2026-12-01 | Yes | Yes | NA | NA | Yes | Received | Yet to Apply | Applied | Applied | Applied | NA | Applied | Applied | Received | No | 2026-11-01 | 2026-12-01 | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | OBC | Yes | Yes
225 | From Sus-Pashan Bridge to Bavdhan on RHS on NH (Pune-Bangalore Highway) | YOGESH SRIKANT MOKATE | Pune Tathawade RSA | 1605 | 9850837586 | A | A | RO | RO A Site | R/2024/IN003851/MAH/000424/3203/00115 | 2023-24 | 2024-10-15 | 597 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 250 | 100 | 350 |  | Yes | Yes | 2026-09-02 | Yet to Initiate | No | Yes |  | 2026-09-01 | 2026-12-01 | Yes |  |  | Yes | Pending |  | 2026-09-01 | Yes | Pending | To be Initiated | No |  | LSR, Negotiaiton Pending | 2026-12-01 | Yes | Yes | LSR pending , Negotiation to be done for the location, File pending at MOD ( Lohegaon with inward number- 302624), Final PMC NOC after receiving the MOD | NA | Yes | Yes | Applied | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2027-02-01 | 2027-03-01 | Yes | Received |  | Pending | [8 empty] | Pending |  |  | BS assigned by FO | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Oct'24 | Open | Yes | Yes
227 | On RHS from Chandni Chowk to Bhugaon Gram Panchayat on National Highway | ANAND SHANKAR MOKATE | Pune City RSA | 1838 | 9850958511 | A | A | RO | RO A Site | R/2024/IN004282/MAH/000437/3203/00121 | 2023-24 | 2024-12-06 | 545 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 125 | 150 | 275 |  | Yes | Yes | Yes | Approved | Yes | Yes |  | 2026-09-01 | 2026-12-01 | Yes | NA | NA | Yes | Yes | Pending | 2026-09-01 | Yes | Yes | Approved | Yes | 4338222 |  | 2026-12-01 | YES | YES | NA | NA | YES | Received | Applied | Received | Not Required | Received | NA | NA | NA | Received | Yes | 2027-02-01 | 2027-03-01 | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'24 | Open | Yes | Yes
258 | Within 2km from Shivaji Maharaj Square to Narayangaon on SH | ROHIDAS PUNAJI BULE | Pune Wagholi RSA | 1634 | 9881643987 | D2 | A | RO | RO A Site-Corpu | R/2025/IN000817/MAH/000091/3203/00023 | 2023-24 | 2026-02-17 | 107 | 0-6M | PUNE | ST | Group 2: Firm Offer | 25 | 110 | 135 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2026-10-01 | 2026-12-01 | Yes | NA | NA | Yes | Pending |  | 2026-10-01 | Yes | Pending | To be Initiated | No |  | LSR, Negotiaiton Pending | 2026-12-01 | Yes | Yes |  |  | No | Applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | NA | NA | In Process | No | 2026-12-25 | 2027-03-01 | Moujani Awaited | Yet to Apply |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'26 | st | Yes | Yes
261 | Vilage Modhave on National Highway (Nira Supe Road) | SHRI SHIVLING DNYANDEO JAGTAP | Pune Tathawade RSA | 1967 | 7499213190 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000821/MAH/000094/3203/00026 | 2023-24 | 2026-02-18 | 106 | 0-6M | PUNE | SC | Group 1: Owned land | 50 | 100 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2026-09-01 | 2026-12-01 | Yes | NA | NA | Pending | Pending |  | 2026-09-01 |  |  | To be Initiated | No |  |  | 2026-12-01 | No | No | The LOI is recommended for cancellation , as the lease deed was cancelled by the candidate and the candidate does not have hold of the land | No | No | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA |  | No | NA | NA | Moujani Awaited | Yet to Apply |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'26 | SC |  | Yes
9 | WATLUJ | MANOJ KISAN LONDHE | Pune Hadapsar RSA |  | 9860366892 | E | A | KSK | KSK-A w/o Reco | N/2015/IN001130/MAH/000146/3203/00031 | KSK 2014-15 | 2016-03-12 | 3736 | >5Y | PUNE | SC | Group 2: Firm Offer | 10 | 44 | 54 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2026-12-01 | 2027-01-01 | Yes |  |  | In Process | Pending |  | 2026-12-01 | Pending | Pending | To be Initiated |  |  | LSR Awaited, land change case | 2027-01-01 | Yes | Yes | NA | NA | No | [8 empty] | In Process |  | 2026-12-01 | 2027-01-01 | No | Yet to Apply | [10 empty] | Pending |  |  | AN on 08.04.2026 | Gosavi and VAC on 25.05.2026 | Pre 2018/Govt | Yes | [5 empty] | Mar'16 | SC
168 | On LHS, From Najik Babhulgaon to Rakshi On Shevgaon Georai SH | SHUBHAM BHAGNATH KATE | Ahmednagar East RSA | 1811 | 9404972337 | D2 | B | RO | RO B Site | R/2024/IN002256/MAH/000181/3203/00016 | 2023-24 | 2024-06-15 | 719 | 1-2Y | PUNE | OBC | Group 1: Owned land | 40 | 80 | 120 |  | Yes | Yes |  | NA |  |  |  | 2026-12-01 | 2027-01-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-12-01 | Yes | Yes | To be Initiated |  |  | Alternate land offered. Candidate is arranging NOC | 2027-01-01 | Yes | Yes | Candidate requested alternater land due to rejection by PWD. Alternate ladn offer is in Progress | NA | No | Applied | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | Yet to apply | Yet to apply | Yet to Assign | Yet to apply | 2027-03-01 | 2027-03-01 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
185 | From Kanheri-Katewadi to Junction on RHS on Baramati-Indapur NH | SIDDHANT GANESH RASKAR | Pune Saswad RSA | 1895 | 7588277374 | D1 | B | RO | RO B Site | R/2024/IN002441/MAH/000220/3203/00049 | 2023-24 | 2024-06-18 | 716 | 1-2Y | PUNE | OBC | Group 1: Owned land | 30 | 127 | 157 |  | Yes | Yes | 2027-01-01 | NA |  |  |  | 2026-12-01 | 2027-01-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-12-01 | Yes | Yes | To be Initiated | No |  | Slow Candidate, Family land dispute. | 2027-01-01 | Yes | Yes |  | NA | Yes | Yes | Received | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2026-12-26 | 2027-01-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | OBC | Yes | Yes
194 | From Chanda to Fattepur on Ghodegaon-Kukana SH | NILKANTH MARUTRAO KHARADE | Ahmednagar East RSA | 1933 | 9527297676 | D2 | B | RO | RO B Site | R/2024/IN002462/MAH/000228/3203/00057 | 2023-24 | 2024-06-18 | 716 | 1-2Y | AHMADNAGAR | OBC | Group 2: Firm Offer | 55 | 100 | 155 |  | Yes | Yes |  | NA |  |  |  | 2026-12-01 | 2027-01-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-12-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited, land change case | 2027-01-01 | Yes | Yes | NA | NA | Yes | Applied | Yet to apply | Applied | Applied | Applied | NA | Applied | Applied | In Process | No | 2026-12-01 | 2027-02-01 | Yes | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | OBC | Yes | Yes
196 | From Kasari to Kodhapuri on RHS on NH (Pune-Ahmednagar Road) | SACHIN VITHALRAO MANTAWAR | Pune Wagholi RSA | 1821 | 7875061656 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002491/MAH/000239/3203/00068 | 2023-24 | 2024-06-19 | 715 | 1-2Y | PUNE | ST | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes | 2027-01-01 | Yet to Initiate |  |  |  | 2026-11-01 | 2027-01-01 | Yes | NA | NA | Yes | Pending |  | 2026-11-01 | Pending | Pending | To be Initiated | No |  | LSR Awaited, land change case | 2027-01-01 | Yes | Yes | Alternate land case |  | NO | Applied | Yet to applied | Yet to applied | Yet to Apply | Yet to applied | Yet to applied | NA | NA | In Process | NO | 2027-01-27 | 2027-03-27 | Yes | Received |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | st | Yes | Yes
209 | Within 5 Km from Hotel Smile Stone towards Pune on Pune -Ahmednagar NH | AKSHATA RAJENDRA ROKADE | Ahmednagar East RSA | 1905 | 8275613407 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002780/MAH/000308/3203/00092 | 2023-24 | 2024-07-06 | 698 | 1-2Y | AHMADNAGAR | SC | Group 1: Owned land | 50 | 105 | 155 |  | Yes | Yes | 2027-01-01 | Approved |  |  |  | 2026-12-01 | 2027-01-01 | Yes | NA | NA | Yes | Yes |  | 2026-12-01 | Yes | Yes | To be Initiated |  |  | Land title is not clear. Will take some time to get TSR cleared | 2027-01-01 | Yes | Yes | NA | NA | Yes | Received | Applied | Received | Received | Received | NA | Received | Received | Received | WIP | 2026-09-01 | 2026-11-01 | Yes |  |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Received | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | SC
220 | From Theur Phata to Urlikanchan Police Station on LHS on NH (Pune-Solapur Road) | VIKRANT VIJAY SADAKALE | Pune Hadapsar RSA | 1914 | 9657892449 | D1 | A | RO | RO A Site-Corpu | R/2024/IN003782/MAH/000410/3203/00111 | 2023-24 | 2024-10-08 | 604 | 1-2Y | PUNE | SC | Group 2: Firm Offer | 30 | 125 | 155 |  | Yes | Yes | 2027-01-01 | Yet to Initiate |  |  |  | 2026-12-01 | 2027-01-01 | Yes |  |  | Yes | Pending |  | 2026-12-01 | Pending | Pending | To be Initiated |  |  | LSR Awaited, negoatiation pending | 2027-01-01 | Yes | Yes | NA | NA | Yes | Yes | Yet to apply | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2026-08-31 | 2026-12-31 | Yes | Received | [10 empty] | Pending |  |  | AN on 08.04.2026 | Received | SRMP 2023-24 | Yes | [5 empty] | Oct'24 | SC
223 | Within 3 KM from Lonand Bus Stand Towards Satara on Satara Lonand Road | VIJAY MALHARI SHELKE | Satara East RSA | 1600 | 9604685831 | D1 | B | RO | RO B Site | R/2024/IN003803/MAH/000416/3203/00114 | 2023-24 | 2024-10-10 | 602 | 1-2Y | SATARA | CC-1 DEFENCE | Group 2: Firm Offer | 30 | 120 | 150 |  | Yes | Yes |  | NA |  |  |  | 2026-12-01 | 2027-01-01 | Yes |  |  | Not Required | Not Required |  | 2026-12-01 | Yes | Yes | Approved | Yes | 4338620 |  | 2027-01-01 | Yes | Yes but in next FY | Slow condidate,NA applied but yet to be done | NA | Yes | Received | Applied | Applied | Applied | Applied | NA | NA | NA | In Process | No | 2027-06-30 | 2027-07-27 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | [5 empty] | Oct'24 | OBC
243 | Village Hivere zare, On Ahmednagar Daund Road (NH) | SATISH BHAGWANT HARAL | Ahmednagar West RSA | 2064 | 9326796545 | D1 | B | RO | RO B Site | R/2025/IN000254/MAH/000033/3203/00009 | 2023-24 | 2025-07-01 | 338 | 6-12M | AHMADNAGAR | CC-1 DEFENCE | Group 2: Firm Offer | 30 | 125 | 155 |  | Yes | Yes |  | NA |  |  |  | 2026-12-01 | 2027-01-01 | Yes | NA | NA | Not Required | Not Required |  | 2026-12-01 |  |  | To be Initiated | No |  |  | 2027-01-01 | Yes | Yes | NA | NA | Yes | Applied | Yet to apply | Yet to apply | Yet to Apply | NA | NA | Yet to apply | Yet to apply | Yet to assign | No | 2026-12-01 | 2027-01-01 | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jul'25 | Open | Yes | Yes
56 | ON NASIK-PUNE BYPASS ROAD | SONALI SUNIL RUPAWATE | Shirdi RSA |  | 9011533440 | D1 | A | RO | RO A Site-Corpu | N/2022/IN001409/MAH/000092/3203/00033 | SRMP 2014-15 | 2022-12-12 | 1270 | 3-4Y | AHMADNAGAR | SC | Group 2: Firm Offer | 30 | 130 | 160 |  | Yes | Yes | 2027-02-01 | Yet to Initiate |  |  |  | 2026-12-01 | 2027-02-01 | Yes | NA | NA | Yes | Yes |  | 2026-12-01 | Yes | Yes | To be Initiated | No |  | There is charge on landwhich needs to be cleard. LSR has huge charge on land | 2027-02-01 | Yes | Yes | LSR due with CHarge on land | NA | Yes | Recieved | Applied | Recieved | Applied | Recived | NA | Recived | Recived | In Process | WIP | 2026-07-31 | 2026-09-30 | Moujani Awaited | Yet to Apply |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Received | Pre 2018/Govt | Yes | Yes |  |  |  |  | Dec'22 | SC |  | Yes
71 | Within 4 kms from Warje Bridge towards Takalwadi in Shivane , Pune | CHAITRALI RAOSAHEB DANGAT | Pune City RSA | 1579 | 7030622003 | A | B | RO | RO B Site | R/2023/IN000870/MAH/000067/3203/00020 | 2023-24 | 2023-11-23 | 924 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 200 | 125 | 325 |  | Yes | Yes | 2027-02-01 | NA |  |  |  | 2026-11-26 | 2027-02-01 | Yes | NA | NA | Not Required | Not Required | Pending | 2026-09-01 | Yes | Yes | To be Initiated | No |  | Site requiresd MOD Approval, which is main reason for delay | 2027-02-01 | YES | YES | NA | NA | YES | Received | Applied | Applied | Not Required | Received | NA | NA | NA | In Process | NO | 2027-02-01 | 2027-02-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Nov'23 | Open | Yes | Yes
86 | From Ghusalkhamb Naka to Muleshwar temple on Lonavala Ambey Valley Road | SWAPNIL PRAKASH PAWAR | Pune Tathawade RSA | 2113 | 9545478686 | E | B | KSK | KSK-B w/o Reco | R/2023/IN001556/MAH/000128/3203/00052 | 2023-24 | 2023-12-13 | 904 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 90 | 120 |  | Yes | Yes | 2027-02-01 | NA |  |  |  | 2027-01-01 | 2027-02-01 | Yes | NA | NA | Not Required | Not Required |  | 2027-01-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2027-02-01 | Yes | Yes but in next FY | PMRDA permission pending and LOI holder is often not responsive, The location is in the monopoly market of OMC not recommended for cancellation | No | Yes | Yes | Applied | Applied | Applied | Received | Received | NA | NA | In Process | No | 2028-01-01 | 2028-02-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'23 | Open | Yes | Yes
114 | From Kanheri-Katewadi to Junction on LHS on Baramti-Indapur NH | ABABSAHEB BAPURAO NIMBALKAR | Pune Saswad RSA | 1817 | 9975023030 | D1 | B | RO | RO B Site | R/2023/IN003273/MAH/000358/3203/00106 | 2023-24 | 2024-01-23 | 863 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 122 | 152 |  | Yes | Yes | 2027-02-01 | NA |  |  |  | 2027-01-01 | 2027-02-01 | Yes | NA | NA | Not Required | Not Required |  | 2027-01-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2027-02-01 | Yes | Yes |  | NA | Yes | Yes | Received | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2026-12-26 | 2027-01-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jan'24 | Open | Yes | Yes
126 | From Undri Chowk to Mantarwadi Chowk towards Pune Saswad Road,Urlidevachi on NH | ANNASAHEB VINAYAK BAJARE | Pune Hadapsar RSA | 2023 | 9373762424 | D1 | A | RO | RO A Site | R/2023/IN004128/MAH/000442/3203/00129 | 2023-24 | 2024-02-12 | 843 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 80 | 85 | 165 |  | Yes | Yes | Yes | Approved |  |  |  | 2027-01-01 | 2027-02-01 | Yes | NA | NA | Yes | Yes |  | 2027-01-01 | Yes | Yes | Approved | Yes | 4338562 | IO received, Advance tender done, Site is ready, NOC awaited. Planned Comm in Mar'26 | 2027-02-01 | Yes | Yes | NA | NA | Yes | Yes | Applied | Received | Received | Received | NA | NA | NA | Received | yes | 2026-09-01 | 2026-09-30 | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'24 | Open | Yes | Yes
154 | Village Barhanpur, on RHS towards Patas on NH (Baramati Patas Road) | SWAPNIL SHIVAJI THORAT | Pune Tathawade RSA | 1917 | 8380077342 | D1 | B | RO | RO B Site | R/2024/IN002033/MAH/000087/3203/00003 | 2023-24 | 2024-06-13 | 721 | 1-2Y | PUNE | OPEN | Group 2: Firm Offer | 30 | 120 | 150 |  | Yes | Yes | No | NA |  |  |  | 2027-01-01 | 2027-02-01 | Yes | NA | NA | Not Required | Not Required |  | 2027-01-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2027-02-01 | Yes | Yes | Tentative NA pending , Provisional MH NOC pending | No | Yes | Yes | Applied | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2026-12-01 | 2027-01-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | Open | Yes | Yes
246 | Within 5 km from Sub-registrar Office, Paud on Mulshi- Chandni Chowk Highway towards Pirangut | SOMNATH BABURAO BEDARE | Pune City RSA | 1612 | 8788797700 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000329/MAH/000048/3203/00011 | 2023-24 | 2025-07-30 | 309 | 6-12M | PUNE | ST | Group 2: Firm Offer | 50 | 100 | 150 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2027-01-01 | 2027-02-01 | Yes | NA | NA | Yes | Pending | Pending | 2026-09-01 | Yes | Pending | To be Initiated | No |  |  | 2027-02-01 | YES | YES | NA | NA | YES | Received | Applied | Applied | Applied | Received | NA | NA | NA | In Process | NO | 2026-12-01 | 2027-01-01 | No | Yet to Apply |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jul'25 | st | Yes | Yes
53 | TALEGAON TOLL PLAZA TO KUSHGAON ON PUNE MUMBAI EXPRESSWAY ON LHS , | SATYAN BHIMSEN GAIKWAD | Pune Tathawade RSA |  | 7039131602 | D1 | A | RO | RO A Site | M/2022/IN001225/MAH/000074/3203/00023 | 2018-19 | 2022-11-10 | 1302 | 3-4Y | PUNE | OPEN | Group 2: Firm Offer | 100 | 120 | 220 |  | Yes | Yes | 2027-03-01 | Yet to Initiate |  |  |  | 2027-02-01 | 2027-03-01 | Yes | NA | NA | Yes | Pending |  | 2027-02-01 | Pending | Pending | To be Initiated | No |  | MSRDC NOC awaited, Site can be commissioned after MSIDC NOC. LSR assigned to AN | 2027-03-01 | Yes | Yes | Expressway location , Applied for MSRDC , Revised PESO construction approval pending | No | Yes | Yes | Applied | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2028-01-01 | 2028-02-01 | Yes | To be applied |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Received | SRMP 2018-19 | Yes | Yes |  |  |  |  | Nov'22 | Open |  | Yes
188 | Village Murti (Taluka Baramati) on National Highway 965D | VIKRAMSINHA BABANRAO JAGADALE | Pune Tathawade RSA | 1893 | 9637118817 | D1 | A | RO | RO A Site | R/2024/IN002458/MAH/000227/3203/00056 | 2023-24 | 2024-06-18 | 716 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 40 | 110 | 150 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2027-02-01 | 2027-03-01 | Yes | NA | NA | Yes | Pending |  | 2027-02-01 | Yes | Pending | To be Initiated | No |  | Negotiation Pending | 2027-03-01 | Yes | Yes | TP applied, Tentative NA pending , NH NOC pending, LSR submitted, Valuation Done, Negotiation pending | No | Yes | Yes | Applied | Applied | Applied | Received | Received | NA | NA | Received | WIP | 2026-12-01 | 2027-01-01 | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Jun'24 | Open | Yes | Yes
236 | From Garade to Khed Shivapur on Khed-Shivapur-Saswad Link Road | VAIBHAV NARENDRA LODHA | Pune Saswad RSA | 2102 | 9764499799 | E | B | KSK | KSK-B w/o Reco | R/2025/IN000076/MAH/000008/3203/00001 | 2023-24 | 2025-04-29 | 401 | 1-2Y | Pune | OPEN | Group 1: Owned land | 25 | 50 | 75 |  | Yes | Yes |  | NA |  |  |  | 2027-02-01 | 2027-03-01 | Yes | NA | NA | Not Required | Not Required |  | 2027-02-01 | Yes | Yes | To be Initiated | No |  | LSR Awaited | 2027-03-01 | Yes | Yes |  | NA | Yes | Yes | Applied | Applied | Applied | Applied | Applied | NA | NA | In Process | WIP | 2027-02-01 | 2027-03-01 | Yes | Received | [10 empty] | Pending |  |  | AN on 08.04.2026 |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Apr'25 | Open | Yes | Yes
251 | Nashik Phata to Moshi Toll on Pune Nashik Road LHS | SACHIN BITAKUL BHOSALE | Pimpri Chinchwad RSA | 1861 | 8208678882 | A | A | RO | RO A Site-Corpu | R/2025/IN000445/MAH/000061/3203/00016 | 2023-24 | 2025-09-11 | 266 | 6-12M | PUNE | ST | Group 2: Firm Offer | 100 | 100 | 200 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2027-01-01 | 2027-03-01 | Yes | NA | NA | In Process | Pending |  | 2027-01-01 | Pending | Pending | To be Initiated | No |  | LSR asigned to AN | 2027-03-01 | Yes | Yes | [11 empty] | In Process |  | 2026-12-01 | 2027-01-01 | No | To be applied |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Firodia and Phadtade on 080426 | SRMP 2023-24 | Yes | Yes |  |  |  |  | Sep'25 | st |  | Yes
254 | From Talegaon Dabhade Phata to Vadgaon on NH(Pune-Bangalore Highway) | SUPRIYA PRAVIN CHAVAN | Pune Tathawade RSA | 1642 | 8655755595 | D1 | A | RO | RO A Site | R/2025/IN000656/MAH/000084/3203/00019 | 2023-24 | 2025-12-06 | 180 | 6-12M | PUNE | OPEN | Group 1: Owned land | 50 | 200 | 250 |  | Yes | Yes |  | Yet to Initiate |  |  |  | 2027-02-01 | 2027-03-01 | Yes | NA | NA | Yes | Pending |  | 2027-02-01 | Pending | Pending | To be Initiated | No |  |  | 2027-03-01 | Yes | Yes | TP applied, Tentative NA pending , NH NOC pending | No | Yes | Yes | Applied | Applied | Applied | Received | Received | NA | NA | In Process | WIP | 2026-12-01 | 2027-01-01 | Yes | Received |  | Pending | [8 empty] | Pending |  |  | AN on 08.04.2026 | Received | SRMP 2023-24 | Yes | Yes |  |  |  |  | Dec'25 | Open | Yes | Yes
263 | From Pabal to Kanhur Mesai on SH (Shirur-Pabal Road) | KISHOREKUMAR SHRIRAM MANDALE | Pune Wagholi RSA | 1744 | 9975845625 | D2 | B | RO | RO B Site | R/2025/IN000820/MAH/000093/3203/00025 | 2023-24 | 2026-02-18 | 106 | 0-6M | PUNE | OBC | Group 1: Owned land | 30 | 70 | 100 |  | Yes | Yes |  | NA |  |  |  | 2027-01-01 | 2027-03-01 | Yes | NA | NA | Not Required | Not Required |  | 2027-02-01 | Pending |  | To be Initiated | No |  |  | Yes | Yes | Yes | New LOI |  | NO | Applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | NA | NA | Yet to Assign | No | 2027-02-27 | 2027-03-01 | Yes | To be applied | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | Yes |  |  |  |  | Feb'26 | OBC | Yes | Yes
198 | Between KM Stone 8 to 10 on RHS while going from Patas to Baramati on NH965G | SANTOSH MADHUKAR DORGE | Pune Hadapsar RSA | 1899 | 9881031111 | D1 | A | RO | RO A Site | R/2024/IN002484/MAH/000234/3203/00063 | 2023-24 | 2024-06-19 | 715 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes But not in 26-27 | 2027-06-01 | Yet to Initiate |  |  |  | 2027-06-01 | 2027-06-01 | Yes |  |  | Assigned to IAS and MA | Pending |  | 2027-06-01 | [5 empty] | very Slow Candidate | 2027-06-01 | Yes | Yes but in next FY | PESO Prior Change required | NA | No | Applied | Applied | Yet to Apply | Yet to Apply | Yet to Apply | NA | NA | NA | Yet to Assign | WIP | 2026-09-30 | 2027-01-28 | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
197 | From Pimpale to Nannaj Dumala on Talegaon Dighe Nandur Shingote NH | VIJAY MARUTI MOKAL | Shirdi RSA | 2087 | 9850883072 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002490/MAH/000238/3203/00067 | 2023-24 | 2024-06-19 | 715 | 1-2Y | AHMADNAGAR | SC | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes But not in 26-27 | 2027-06-01 | Yet to Initiate |  |  |  | 2027-06-01 | 2027-06-01 | Yes |  |  | Yes | Pending |  | 2027-06-01 | To be Provided | Estimate shall be provided after receiving approved concept note |  |  |  | Very Slow Candidate | 2027-06-01 | Yes | Yes but in next FY | Slow Candidate | NA | Yes | Recieved | Applied | Recieved | Applied | Recived | NA | Recived | Recived | Yet to Assign | No | 2027-01-31 | 2027-05-31 | Yes | [11 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | SC
257 | On RHS From Kamshet to Karla on NH (Pune-Bangalore Highway) | PRAVIN GAJANAN CHAUGULE | Pune Tathawade RSA | 1807 | 9422740000 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000816/MAH/000090/3203/00022 | 2023-24 | 2026-02-17 | 107 | 0-6M | PUNE | SC | Group 1: Owned land | 45 | 220 | 265 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-06-01 | Yes | [5 empty] | 2027-06-01 | [6 empty] | 2027-06-01 | Yes | Yes but in next FY | Greenbelt issue in the old Pune Mumbai Highway , Revised Mojini Applied | No | Yes | Yes | Applied | Applied | Applied | Applied | Received | NA | NA | Received | WIP | 2026-12-01 | 2027-01-01 | Yes | Recived | [10 empty] | Pending |  |  | AN on 26.05.2026 |  | SRMP 2023-24 | Yes | [5 empty] | Feb'26 | SC
259 | From Sahajpur Phata to Khamgaon Phata on RHS of PUNE SOLAPUR NH | SHRI SANTUJI NIVRUTTI KAMBLE | Pune Hadapsar RSA | 1750 | 9082061998 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000822/MAH/000095/3203/00027 | 2023-24 | 2026-02-18 | 106 | 0-6M | PUNE | CC-1 PMP/GOVT.EMPL | Group 2: Firm Offer | 40 | 158 | 198 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-06-01 | Yes | [5 empty] | 2027-06-01 | [5 empty] | Very Slow Candidate | 2027-06-01 | Yes | Yes but in next FY | NA | NO | NO | NA | NA | NA | NA | NA | NA | NA | NA | Yet to Assign | WIP | 2027-01-28 | 2027-03-31 | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'26 | SC
30 | ON SH 45 BETWEEN KM STONE NO. 3 & 8 | MAHESH ADHAV | Shirdi RSA |  | 9422250439 | D2 | A | RO | RO A Site-Corpu | M/2020/IN000066/MAH/000007/3203/00006 | 2018-19 | 2020-04-28 | 2228 | >5Y | AHMADNAGAR | SC | Group 2: Firm Offer | 30 | 120 | 150 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | Land Not Available due to RLY DPR issue |  |  |  |  | 2027-06-01 | To be Provided | Estimate shall be provided after receiving approved concept note |  |  |  | Land Issue due to Railway acquisition | 2027-07-01 | Yes | Yes but in next FY | DPR of railway awaited as the land may go in railway construction area. | No | Yes | Yet to apply. | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | No | 2027-11-30 | 2028-02-29 | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Apr'20 | SC
51 | VILLAGE SHENOLI ON KARAD TASGAON ROAD ON NH266 , | ASHOK BHAGWAN LOKHANDE | Satara West RSA |  | 9096420232 | D1 | A | RO | RO A Site-Corpu | M/2022/IN001167/MAH/000067/3203/00019 | 2018-19 | 2022-10-31 | 1312 | 3-4Y | SATARA | CC-1 DEFENCE | Group 1: Owned land | 30 | 125 | 155 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [5 empty] | Very Slow Candidate | 2027-07-01 | YES | Yes but in next FY | Slow candidate, No such sufficient progress in any other NOC except Health and MSEB | NA | YES | Received | Applied | Applied | Yet to Apply | Received | NA | NA | NA | In process. Lawyer has given list of document | No | 2027-06-30 | 2027-07-31 | Yes | Recived | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Oct'22 | SC
149 | From Pokhari to Rajpur on SH on RHS on Manchar Bhimshankar road | GANESH RAMCHANDRA TITKARE. | Pune Wagholi RSA | 1923 | 8010347872 | D2 | A | RO | RO A Site-Corpu | R/2023/IN006223/MAH/000582/3203/00171 | 2023-24 | 2024-03-15 | 811 | 2-3Y | PUNE | ST | Group 1: Owned land | 40 | 76 | 116 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes |  |  | Yes | Pending |  | 2027-06-01 | Pending | Pending | Pending |  |  | Very slow Candidate | 2027-07-01 | Yes | No | Issue in mauzni ,New Mauzni awited | No | No | Applied | Yet to applied | Yet to applied | Not Required | [8 empty] | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | st
202 | From Ravet to Malavli on Pune Mumbai Expressway | SARITA RAHUL BADOLE | Pune Tathawade RSA | 2028 | 9834486238 | D1 | A | RO | RO A Site | R/2024/IN002488/MAH/000236/3203/00065 | 2023-24 | 2024-06-19 | 715 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 90 | 110 | 200 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [6 empty] | 2027-07-01 | Yes | Yes but in next FY | Expressway location , Applied for MSRDC | No | Yes | Yes | Applied | Applied | Applied | Applied | Received | NA | NA | Yet to Assign | WIP | 2028-01-01 | 2028-02-01 | Yes | #N/A | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
210 | From Bhanashiware to Soundala on Nevasa-Shevgaon SH | SANJAY TUKARAM PAWARA | Ahmednagar East RSA | 1794 | 7722014513 | D2 | A | RO | RO A Site-Corpu | R/2024/IN002783/MAH/000311/3203/00094 | 2023-24 | 2024-07-06 | 698 | 1-2Y | AHMADNAGAR | ST | Group 2: Firm Offer | 35 | 90 | 125 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | NA | NA |  |  |  | 2027-06-01 | To be Provided | Estimate shall be provided after receiving approved concept note |  |  |  | Slow Candidate | 2027-07-01 | Yes | Yes but in next FY |  |  | Yes | Received | Yet to apply | Applied | Applied | Applied | na | Applied | Applied | Yet To assign |  |  |  | Yes | [11 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | st
228 | ON NH-4 RHS FROM PUNE TO SATARA BETWEEN KM STONE 760 TO 755 | SHUBHANGI PRAKASH GAIKWAD | Satara West RSA |  | 9922935234 | D1 | A | RO | RO A Site-Corpu | M/2024/IN004281/MAH/000436/3203/00120 | 2018-19 | 2024-12-06 | 545 | 1-2Y | SATARA | SC | Group 2: Firm Offer | 40 | 110 | 150 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [6 empty] | 2027-07-01 | YES | Yes but in next FY | Layout prepared recently, NA process yet to be initiated | NA | YES | Received | Yet to Apply | Applied | Yet to Apply | Applied | NA | NA | NA | Yet to Assign | No | 2027-06-30 | 2027-07-31 | Yes | Recived | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Dec'24 | SC
231 | From Mayani To Katarkhatav on Mayani Dahiwadi Road | YOGITA ARUN AHIRE | Satara East RSA | 110 | 7020657052 | D1 | A | RO | RO A Site-Corpu | R/2024/IN004519/MAH/000464/3203/00125 | 2023-24 | 2025-01-03 | 517 | 1-2Y | SATARA | ST | Group 1: Owned land | 30 | 120 | 150 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [5 empty] | No Progress in NOC | 2027-07-01 | Yes | Yes but in next FY | Slow condidate,NA applied but yet to be done,Condidate not responding on phone calls | NA | No | Received | Applied | Yet to apply | Yet to apply | Yet to apply | NA | NA | NA | Received | NA | 2027-06-30 | 2027-07-27 | Yes | [11 empty] | Pending |  |  |  | VAC and Gosavi on 25.05.2026 | SRMP 2023-24 | Yes | [5 empty] | Jan'25 | st
235 | From KM stone 749 to 747 On RHS of Pune To Satara NH | VISHAL SHIVAJI SONVANE | Satara West RSA | 1825 | 8329813327 | D1 | A | RO | RO A Site-Corpu | R/2024/IN004865/MAH/000491/3203/00132 | 2023-24 | 2025-03-26 | 435 | 1-2Y | SATARA | SC | Group 1: Owned land | 40 | 160 | 200 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [5 empty] | very slow candidate | 2027-07-01 | YES | Yes but in next FY | No much porgess as of now in NA which is a major requisite, LSR etc | NA | YES | Received | Applied | Applied | Yet to Apply | Received | NA | NA | NA | Yet to Assign | NO | 2027-06-30 | 2027-07-31 | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'25 | SC
244 | From KM stone 75 to KM stone 85 on Pune Solapur Highway | SAGAR ASHOK SALVE | Pune Hadapsar RSA | 1856 | 9763715716 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000253/MAH/000032/3203/00008 | 2023-24 | 2025-07-01 | 338 | 6-12M | PUNE | SC | Group 1: Owned land | 30 | 157 | 187 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [5 empty] | Very Slow Candidate | 2027-07-01 | Yes | Yes but in next FY | Financially Stressed Candidate | NA | Yes | Yes | Yet to Apply | Yet to apply | Yet to apply | Yet to apply | Applied | NA | NA |  |  |  |  | Yes | Recived | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'25 | SC
248 | From Antarwali Khurd she. to Kurudgaon on Bodhegaon Road | SHARAD DEVIDAS GHODAKE | Ahmednagar East RSA | 86 | 9657436679 | E | A | KSK | KSK-A w/o Reco | R/2025/IN000330/MAH/000049/3203/00012 | 2023-24 | 2025-07-30 | 309 | 6-12M | AHMADNAGAR | SC | Group 1: Owned land | 20 | 50 | 70 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | NA | NA |  |  |  | 2027-06-01 | Slow Candidate |  |  |  |  | Slow Candidate | 2027-07-01 | Yes | Yes but in next FY |  |  | Yes | Yes | Yet to Apply | Yet to Apply | Yet to Apply | Applied | NA | Applied | Applied | Yet To assign |  |  |  | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'25 | SC
252 | From KM stone 52 to KM stone 56 ON LHS OF PUNE SOLAPUR NH | VIJAY WAMAN MASURE | Pune Hadapsar RSA | 1590 | 9021613733 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000573/MAH/000076/3203/00017 | 2023-24 | 2025-10-31 | 216 | 6-12M | PUNE | SC | Group 2: Firm Offer | 37 | 120 | 157 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [5 empty] | Land is not available with Candidate | 2027-07-01 | Yes | No | Land is not available with Candidate | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Oct'25 | SC
260 | From Km stone 715 to 720 on LHS on Karad to Satara Road | SURESH PANDURANG RANDIVE | Satara West RSA | 1678 | 9552595582 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000818/MAH/000092/3203/00024 | 2023-24 | 2026-02-18 | 106 | 0-6M | SATARA | SC | Group 2: Firm Offer | 40 | 120 | 160 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 2027-06-01 | 2027-07-01 | Yes | [5 empty] | 2027-06-01 | [6 empty] | 2027-07-01 | YES | Yes but in next FY | Freshly issued LOI, All procedure to be started | NA | NO | Received | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | NA | NA | Yet to Assign | NO | 2027-06-30 | 2027-07-31 | [12 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'26 | SC
264 | Within 5 Km from Sai Anand Lawns towards Pune on Pune-Aurangabad NH | GURUDAS VIJAY PAWARA | Ahmednagar East RSA | 91 | 7972678127 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000871/MAH/000098/3203/00029 | 2023-24 | 2026-03-18 | 78 | 0-6M | AHMADNAGAR | ST | Group 2: Firm Offer | 25 | 125 | 150 |  | Yes | Yes But not in 26-27 |  | Yet to Initiate |  |  |  | 46539 | 2027-07-01 | Yes | NA | NA |  |  |  | 2027-06-01 | [6 empty] | 2027-07-01 | Yes | Yes but in next FY |  |  | No | Applied | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | Yet to Apply | Yet to Apply | In Process | [15 empty] | Pending |  |  | AG on 14.05.2026 |  | SRMP 2023-24 | Yes | [5 empty] | Mar'26 | st
31 | SARADWADI TO SHIRUR ON PUNE-AHMEDNAGAR ROAD, | GAURAV KALEWAR | Pune Wagholi RSA |  | 9764750909 | D1 | B | RO | RO B Site | M/2020/IN000088/MAH/000010/3203/00009 | 2018-19 | 2020-04-30 | 2226 | >5Y | PUNE | OBC | Group 1: Owned land | 25 | 130 | 155 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2027-07-02 | Yes | No | OlD loi , Financial issue ,Meeting with loi holder is cheduled on 18.05.2026 | No | Yes |  |  |  | 0 | [8 empty] | Yes | Recived | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Apr'20 | OBC
43 | KATI(TALUKA-INDAPUR) | TUSHAR BABAN SHENDE | Pune Saswad RSA |  | 8600400101 | E | B | KSK | KSK-B w/o Reco | M/2021/IN000872/MAH/000049/3203/00015 | 2018-19 | 2021-08-09 | 1760 | 4-5Y | PUNE | OPEN | Group 2: Firm Offer | 6 | 40 | 46 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Disinterested LOI holder | 2027-07-02 | Yes | Yes but in next FY |  | NA | Yes | Yes | Applied | Applied | Applied | Applied | Applied | NA | NA | In Process | No | 2027-06-01 | 2027-07-01 | Yes | Recived | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Aug'21 | Open
68 | BORIPARDHI (TALUKA-DAUND) | ABHIJIT NITIN TENGLE | Pune Hadapsar RSA |  | 9503035055 | E | B | KSK | KSK-B w/o Reco | M/2023/IN000176/MAH/000021/3203/00010 | 2018-19 | 2023-06-22 | 1078 | 2-3Y | PUNE | OBC | Group 1: Owned land | 6 | 40 | 46 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes | Disinterested LOI holder |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2027-07-02 |  | Yes but in next FY | [15 empty] | Yes | Recived | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jun'23 | OBC
73 | From Shiroli to Rajgurunagar on LHS on NH (Pune-Nashik Road) | RANJENDRA RAMESH SANDBHOR | Pune Wagholi RSA | Pune IV RSA | 9850581349 | D1 | B | RO | RO B Site | R/2023/IN000993/MAH/000075/3203/00023 | 2023-24 | 2023-11-28 | 919 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 131 | 161 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 |  | NOC rejected by DM/NH/PWD |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2027-07-02 | Yes | Yes but in next FY | There is a flyover sanctioned at nasik highway Due to that dealer has lost intrest. We are in talking with dealer as it is high potential location | No | Yes | Yes | Yes |  | 45992 | [8 empty] | Yes | #N/A | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Nov'23 | Open
80 | From Surwad to Bawada Police Station on RHS of Indapur-Akluj Road | SWAPNAJA AMARDEEP JAKHALKAR | Pune Saswad RSA | 1655 | 9004917007 | D1 | B | RO | RO B Site | R/2023/IN001438/MAH/000104/3203/00040 | 2023-24 | 2023-12-11 | 906 | 2-3Y | PUNE | OBC | Group 1: Owned land | 40 | 135 | 175 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes | Draft |  |  | Very Slow Candidate | 2027-07-02 | Yes | Yes but in next FY |  | NA | Yes | Yes | Applied | Applied | Yet to Apply | Received | 8985443 | NA | NA | Yet to assign | No | 2027-06-01 | 2027-07-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | OBC
81 | On LHS From Kamshet to Karla on NH (Pune-Bangalore Highway) | SANGRAM SUBHASH JADHAV | Pune Tathawade RSA | 1832 | 8805645273 | D1 | B | RO | RO B Site | R/2023/IN001467/MAH/000112/3203/00045 | 2023-24 | 2023-12-11 | 906 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 50 | 215 | 265 |  | Yes | Yes But not in 26-27 | Yes |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes | Approved | Yes | 4337975 | PMRD permission pending due to green zone of 45 meter from the ROW. | 2027-07-02 | Yes | No | Candidate not responding | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
98 | Within 5km of Chakan Chowk towards IOC Bottling Plant on LHS on Chakan - Shikrapur Road | DHANASHREE NITIN PATIL | Pimpri Chinchwad RSA | 1706 | 8390544048 | D1 | B | RO | RO B Site | R/2023/IN001865/MAH/000196/3203/00072 | 2023-24 | 2023-12-19 | 898 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 40 | 120 | 160 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2027-07-02 |  | Yes but in next FY | [6 empty] | 0 |  |  |  |  | Received |  |  |  | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
106 | From Kasari to Kondhapuri on NH (Pune-Ahmednagar Road) | ASHISH MURLIDHAR GAIKWAD | Pune Wagholi RSA | 1645 | 9921214545 | D1 | B | RO | RO B Site | R/2023/IN002989/MAH/000317/3203/00096 | 2023-24 | 2024-01-16 | 870 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 50 | 184 | 234 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | very Slow Candidate | 2027-07-02 | yes | Yes but in next FY | Land issue ,Meeting with dealer scheduled on 18.05.2026 | No | Yes | Yes |  |  | 0 | [8 empty] | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
121 | on RHS From Khadki to Bhigwan Circle on Pune-Solapur NH | PRASAD AJIT KSHIRSAGAR | Pune Hadapsar RSA | 1885 | 9850083232 | D1 | B | RO | RO B Site | R/2023/IN003534/MAH/000386/3203/00120 | 2023-24 | 2024-01-30 | 856 | 2-3Y | PUNE | OBC | Group 1: Owned land | 38 | 120 | 158 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes | Draft |  |  | very Slow Candidate | 2027-07-02 | Yes | Yes but in next FY | [15 empty] | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | OBC
131 | From Village Waranghushi to village Waki on RHS on Bhandardara- Ghoti SH road | SACHIN NATHURAM MUNDHE | Shirdi RSA | 1626 | 9890752925 | D2 | B | RO | RO B Site | R/2023/IN004161/MAH/000451/3203/00131 | 2023-24 | 2024-02-13 | 842 | 2-3Y | AHMADNAGAR | OBC | Group 2: Firm Offer | 20 | 84 | 104 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Alternate land has been offered. Candidate has to respond | 2027-07-02 | Yes | Yes but in next FY | Adendum to LOI need to be given against the recived land after rejection of first NOC due to Eco Sensitive zone. | NA | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to Assign | No | 2027-11-30 | 2028-02-29 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | OBC
137 | At Nirmal Pimpri towards Ahmednagar on Nagar-Manmad Road | AMRUT RAGHUNATH GAIKWAD | Shirdi RSA | 1948 | 9096955762 | D1 | B | RO | RO B Site | R/2023/IN004348/MAH/000469/3203/00145 | 2023-24 | 2024-02-16 | 839 | 2-3Y | AHMADNAGAR | OBC | Group 1: Owned land | 25 | 130 | 155 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Land Litigation is going on | 2027-07-02 | Yes | Yes but in next FY | There was court case by the near by land owner and case result come in LOI holder favour on 20.04.2026. | NA | Yes | Recieved | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to Assign | No | 2027-11-30 | 2028-02-29 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | OBC
136 | VILLAGE BHANGAON ON SHRIGONDA TO KOLGAON ROAD (TALUKA-SHRIGONDA) | AJIT KAKADE | Ahmednagar West RSA |  | 9673575151 | E | B | KSK | KSK-B w/o Reco | M/2023/IN004349/MAH/000470/3203/00146 | 2018-19 | 2024-02-16 | 839 | 2-3Y | AHMADNAGAR | OPEN | Group 2: Firm Offer | 20 | 60 | 80 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Junction issue, Alternate land Offer is required | 2027-07-02 | Yes | Yes | Alternate land offer received, LOI yet to issue. | NA | NA | NA | NA | NA | Not Required | NA | NA | NA | NA | NA | NA | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Feb'24 | Open
138 | From Intersection of Indapur Town Road and Indapur Bypass to Bhima River on RHS of Pune - Solapur NH | RAM MANIK ASABE | Pune Saswad RSA | 1682 | 9890156520 | D1 | B | RO | RO B Site | R/2023/IN004608/MAH/000476/3203/00149 | 2023-24 | 2024-02-22 | 833 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 27 | 150 | 177 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes | Draft |  |  | Forest land issue, conversion will take time. as of Now it is non commissionable. Huge amount of najrana to be paid | 2027-07-02 | Yes | Yes but in next FY |  | NA | Yes | Yes | Yet to Apply | Applied | Yet to Apply | Applied | Applied | NA | NA | In Process | No | 2027-06-01 | 2027-07-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | Open
150 | Within 5 Km from Wadegavhan Bus Stand towards Ahmednagar on Pune-Aurangabad NH | GANESH SHIVAJI JADHAV | Ahmednagar East RSA | 2072 | 9420949475 | D1 | B | RO | RO B Site | R/2023/IN006050/MAH/000569/3203/00164 | 2023-24 | 2024-03-15 | 811 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 50 | 150 | 200 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes | NA | NA | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Slow Candidate | 2027-07-02 | Yes | Yes but in next FY |  |  | Yes | Yes | Yet to Apply | Applied | Applied | Applied | NA | Applied | Applied | Yet to Assign |  |  |  | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
163 | From Khandala to Ahire on Khandala Lonand Road | SHANKAR KESHAV SHINDE | Satara East RSA | 1580 | 8208644541 | C | B | RO | RO B Site | R/2024/IN002260/MAH/000185/3203/00020 | 2023-24 | 2024-06-15 | 719 | 1-2Y | SATARA | OBC | Group 2: Firm Offer | 40 | 70 | 110 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2027-07-02 | Yes | Yes but in next FY | Slow condidate,NA applied but yet to be done | NA | No | Received | Applied | Yet to apply | Yet to apply | Yet to apply | NA | NA | NA | In Process | WIP | 2027-06-30 | 2027-07-27 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
164 | On RHS , Within 2 km from Pencil Chowk towards Bhigwan on Baramati Bhigwan Road | PRAKASH NARAHARI CHOUDHAR | Pune Tathawade RSA | 1584 | 9764501616 | D2 | B | RO | RO B Site | R/2024/IN002259/MAH/000184/3203/00019 | 2023-24 | 2024-06-15 | 719 | 1-2Y | PUNE | OBC | Group 1: Owned land | 40 | 110 | 150 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Alternate land offer given to candidate due to NOC rejection. Alternate land offer from candidate is pending | 2027-07-02 | Yes | Yes but in next FY | Candidate has submitted NOC application after the revised drawing submitted after the NOC Cancellation from PWD | No | Yes | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | 2028-01-01 | 2028-02-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
169 | From Varve Budruk to Harishchandri on NH (Pune-Bangalore Highway) | SOHAM SANDEEP KULKARNI | Pune Tathawade RSA | 1709 | 8975758779 | D1 | B | RO | RO B Site | R/2024/IN002246/MAH/000178/3203/00013 | 2023-24 | 2024-06-15 | 719 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 40 | 120 | 160 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Land not available | 2027-07-02 | Yes | No | Candidate not responding, The Land is not available and under aquisition from NH | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
177 | Within 2 Km from Zilla Parishad School (Mirajgaon) towards Kada on Mirajgaon-Kada SH | DIPALI RAVINDRA VATARE | Ahmednagar West RSA | 1737 | 7447535656 | D2 | B | RO | RO B Site | R/2024/IN002368/MAH/000198/3203/00031 | 2023-24 | 2024-06-17 | 717 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 70 | 100 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2027-07-02 | Yes | Yes but in next FY | NA | NA | Yes | Yes | Applied | Applied | PWD applied | NA | NA | Applied | Applied | In process | NA | 2027-07-01 | 2027-07-01 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
178 | From Walwad to Chincholi Phata on Jamkhed-Shrigonda NH | ASHWINI HARISHCHANDRA NANGARE | Ahmednagar West RSA | 1756 | 7756010203 | D1 | B | RO | RO B Site | R/2024/IN002400/MAH/000207/3203/00038 | 2023-24 | 2024-06-17 | 717 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 40 | 110 | 150 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | MORTH issue, Earlier while LEC there is no any toll plaza but now toll plaza has been constructed but relexation needed. | 2027-07-02 | Yes | Yes but in next FY | MORTH issue, Earlier while LEC there is no any toll plaza but now toll plaza has been constructed but relexation needed. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
176 | Within 3 Km from Bodhegaon Bus stand towards Georai on Shevgaon- Georai SH | KRISHNA GANPAT PAYGHAN | Ahmednagar East RSA | 1797 | 7972857045 | D2 | B | RO | RO B Site | R/2024/IN002381/MAH/000204/3203/00035 | 2023-24 | 2024-06-17 | 717 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 25 | 80 | 105 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes | NA | NA | Not Required | Not Required |  | 2027-06-01 | Yes | Yes | Draft |  |  | Very Slow Candidate. Loan updation pending on 7/12, Final NA, TP | 2027-07-02 | Yes | Yes but in next FY |  |  | Yes | Yes | Yet to Apply | Applied | Applied | Applied | NA | Applied | Applied | In Process |  |  |  | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  | Amol Gandhi |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
214 | From Junction to Nimgaon Ketki on Baramati- Indapur NH | ASMITA AADESH CHAVARE | Pune Saswad RSA | 1962 | 9850656135 | D1 | B | RO | RO B Site | R/2024/IN002849/MAH/000325/3203/00097 | 2023-24 | 2024-07-10 | 694 | 1-2Y | PUNE | OBC | Group 1: Owned land | 54 | 100 | 154 |  | Yes | Yes But not in 26-27 | 2027-07-02 |  |  |  |  | 2027-06-01 | 2027-07-02 | Yes |  |  | Not Required | Not Required |  | 2027-06-01 | Yes | Yes |  |  |  | Financially weak, slow candidate | 2027-07-02 | Yes | Yes but in next FY |  | NA | Yes | Yes | Applied | Applied | Yet to Apply | Received | Received | NA | NA | In Process | No | 2027-06-01 | 2027-07-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | OBC
242 | From Karde to Nhavare Phata on RHS on SH (Shirur-Satara Road ) | SHWETA SOMNATH LANGHE | Pune Wagholi RSA | 1984 | 7588870445 | D2 | B | RO | RO B Site | R/2025/IN000149/MAH/000019/3203/00007 | 2023-24 | 2025-05-26 | 374 | 1-2Y | PUNE | OBC | Group 1: Owned land | 20 | 80 | 100 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes | [5 empty] | 2027-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2027-07-02 | Yes | Yes but in next FY | There is family dividation issue , candidate sought 15 days time till 30.05.2026 to resolve the issue otherwise LOI will be cancelled | No | No | Applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | NA | NA | Yet to assign | no | 2027-05-27 | 2027-06-09 | [12 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | May'25 | OBC
| From Alephata to Pimpri Pendhar on LHS on NH (Ahmednagar- Kalyan Road) | ASHWINI NIVRUTTI KALE | Pune Wagholi RSA | 1880 | 9657069956 | D1 | B | RO | RO B Site | R/2025/IN000148/MAH/000018/3203/00006 | 2023-24 | 2025-05-26 | 374 | 1-2Y | Pune | OPEN | Group 2: Firm Offer | 28 | 130 | 158 |  | Yes | Yes But not in 26-27 | [5 empty] | 46539 | 2027-07-02 | Yes | [5 empty] | 2027-06-01 | [5 empty] | Very slow Candidate | 2027-07-02 |  | No | Land Issue | [26 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | May'25 | Open
256 | WITHIN 2 KMS FROM KARJAT | VIJAY RAOSAHEB KARPE | Ahmednagar West RSA |  | 9552379748 | D2 | B | RO | RO B Site | N/2025/IN000758/MAH/000087/3203/00021 | 2014-15 | 2026-01-20 | 135 | 0-6M | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 70 | 100 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes | [5 empty] | 2027-06-01 | [5 empty] | Recently issued LOI but the land owner not willing to offer lease as subsenstial time passed since advertisement. | 2027-07-02 | Yes | Yes but in next FY | Recently issued LOI but the land owner not willing to offer lease as subsenstial time passed since advertisement. | NA | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jan'26 | OBC
255 | On Manmad Bypass, Within 5 km from intersection of Ahmednagar Kalyan Highway and Manmad Bypass towards Vilad | VAIBHAV AJITRAO DEOKAR | Ahmednagar East RSA | 1742 | 9822816161 | D1 | B | RO | RO B Site | R/2025/IN000756/MAH/000086/3203/00020 | 2023-24 | 2026-01-20 | 135 | 0-6M | AHMADNAGAR | OPEN | Group 1: Owned land | 20 | 130 | 150 |  | Yes | Yes But not in 26-27 | [5 empty] | 2027-06-01 | 2027-07-02 | Yes | NA | NA |  |  |  | 2027-06-01 | Slow Candidate |  |  |  |  | Slow Candidate | 2027-07-02 | Yes | Yes but in next FY | In process of changing the land |  | No | Applied | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | Yet to Apply | Yet to Apply | Yet to Assign | [15 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'26 | Open
266 | From Rajuri to Alephata on RHS on NH (Ahmednagar- Kalyan Road) | SAMPADA ANIL DIVEKAR | Pune Wagholi RSA | 1888 | 8983530737 | D1 | B | RO | RO B Site | R/2025/IN000873/MAH/000100/3203/00031 | 2023-24 | 2026-03-18 | 78 | 0-6M | PUNE | OBC | Group 2: Firm Offer | 20 | 130 | 150 |  | Yes | Yes But not in 26-27 | [5 empty] | 46539 | 2027-07-02 | Yes | [5 empty] | 2027-06-01 | [6 empty] | 2027-07-02 | Yes | Yes | new Loi |  | No | Applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | NA | NA | Yet to applied | NO | 2027-01-27 | 2027-02-18 | No | No | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'26 | OBC
267 | FROM NARHE TO JAMBHULWADI,ON RHS OF NH (PUNE-BANGALORE HIGHWAY) | YASHODHAN SADASHIV SHINDE | Pune Tathawade RSA | 1583 | 9881321999 | A | B | RO | RO B Site | R/2025/IN000883/MAH/000101/3203/00032 | 2023-24 | 2026-03-25 | 71 | 0-6M | PUNE | OPEN | Group 2: Firm Offer | 10 | 120 | 130 |  | Yes | Yes But not in 26-27 | [5 empty] | 46539 | 2027-07-02 | Yes | [5 empty] | 2027-06-01 | [6 empty] | 2027-07-02 | Yes | Yes but in next FY | The drawing preparation is still pending . The frontage of the RO land is short as per the Mojini Drawing submitted | No | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | 2028-01-01 | 2028-02-01 | Moujani Awaited | Yet to Apply | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'26 | Open
1 | WITHIN 2KMS FRM GHODEGAON TOWARDS MANCHAR ON GHODEGAON MANCHAR ROAD | SHRI SAMEER BHASKAR KALE | Pune Wagholi RSA |  |  | D2 | B | RO | RO B Site | 2011/IN002092/MAH/000087/3203/00053 | SRMP 2009-11 | 2012-03-01 | 5208 | >5Y | PUNE |  | Group 1: Owned land | 30 | 100 | 130 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Subjuidice |  | Not Required | Not Required | Available | 2028-06-01 | Yes | Yes |  |  |  | Land is under litigation | 2028-09-01 | Yes | No | 2011 LOI having NOC in hand. Matter subjudice and awaiting court order in favour of our LOI holder | Will be submitted by 25.05.2026 |  |  |  |  | Not Required | [8 empty] | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Mar'12 | Open
2 | ON LHS FROM CHANDANI CHOWK TO BAVDHAN KHURD | SH RAJKUMAR EKNATH KARANJAKAR | Pune City RSA |  |  | A | B | RO | RO B Site | 2013/IN000697/MAH/000134/3203/00033 | SRMP 2011-13 | 2013-09-20 | 4640 | >5Y | PUNE |  | Group 2: Firm Offer | 60 | 90 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 |  | NO | Candidate not responding, legal issue | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Sep'13 | Open
3 | SHIROLI ON NH-50 ON LHS from Pune to Nashik | Puja Ravindra Karnawat | Pune Wagholi RSA |  |  | D1 | B | RO | RO B Site | 2014/IN000112/MAH/000026/3203/00020 | SRMP 2009-11 | 2014-05-30 | 4388 | >5Y | PUNE |  | Group 1: Owned land | 36 | 150 | 186 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 |  | No | Candidate is not tracable ,Need to visit at residence by 25.05.26 | No |  |  |  |  | Not Required | [10 empty] | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | May'14 | Open
4 | LONAND (KAPADGAON) | MAHARASTRA STATE WAREHOUSING C | Satara East RSA |  |  | D2 | B | RO | RO B Site | 2015/IN000020/MAH/000004/3203/00003 | SRMP | 2015-04-27 | 4056 | >5Y | SATARA | Govt Agency | Group 1: Owned land | 20 | 70 | 90 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Govt Site, Land is not available | 2028-09-01 | Yes | No | Govt Site, Land is not available | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | Recived | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Apr'15 | Open
5 | KARAD ON KARAD KARVE ROAD | MAHARASTRA STATE WAREHOUSING C | Satara West RSA |  |  | D2 | B | RO | RO B Site | 2015/IN000018/MAH/000002/3203/00001 | SRMP | 2015-04-27 | 4056 | >5Y | SATARA | Govt Agency | Group 1: Owned land | 25 | 80 | 105 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available | 2028-09-01 | YES | NO | These are Maharshtra State warehousing sites. APMC is not responding and not following up for NOCs | NO | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Apr'15 | Open
6 | PHALTAN PANDHARPUR ROAD (WITHIN 3 KMS FROM NANA PATIL CHOWK) | SANJEEV VIJAYSINH N NIMBALKAR | Satara East RSA |  | 9822037366 | D2 | B | RO | RO B Site | N/2015/IN000368/MAH/000027/3203/00003 | 2014-15 | 2015-07-04 | 3988 | >5Y | SATARA | OPEN | Group 1: Owned land | 25 | 80 | 105 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available | 2028-09-01 | Yes | No | Land is not available | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jul'15 | Open
7 | BHOKAR (BETWEEN TAKLIBHAN TO SHIRASGAON) | SHRI RAJENDRA BHANUDAS PAWAR | Shirdi RSA |  |  | D2 | B | RO | RO B Site | 2015/IN000079/MAH/000018/3203/00011 | SRMP 2011-13 | 2015-07-06 | 3986 | >5Y | AHMADNAGAR |  | Group 1: Owned land | 20 | 70 | 90 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | HPCL RO already commissioned on same land | 2028-09-01 | Yes | No | On the land, candidate constructed shopping complex and not interested. Last visit happened and candidate seeks time for land change and other related process in family and will come back. FO is trying to get final decission of the candidate and MOM for the same. | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jul'15 | Open
8 | ON RAHATA CHITALI ROAD UP TO 2 KMS FROM RAHATA CHOWK TOWARDS CHITALI | Dyaneshwar Pandharinath Lute | Shirdi RSA |  | 9049559466/9075010241 | E | B | KSK | KSK-B w/o Reco | N/2015/IN000961/MAH/000131/3203/00022 | 2014-15 | 2015-11-26 | 3843 | >5Y | AHMADNAGAR | OPEN | Group 1: Owned land | 6 | 40 | 46 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | LOI to be cancelled. Candidate has to submit written confirmation | 2028-09-01 | Yes | No | Meeting with candidate happened and found not interested as no action done since 11 year of the LOI. | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Nov'15 | Open
10 | KHEDSHIVAPUR-KUSGAON ROAD | Shri Suyash Sarjerao Gaikwad | Pune Tathawade RSA |  |  | E | A | KSK | KSK-A w/o Reco | N/2016/IN000121/MAH/000019/3203/00005 | 2014-15 | 2016-07-26 | 3600 | >5Y | PUNE | SC | Group 1: Owned land | 6 | 40 | 46 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | No Progress in NOC | 2028-09-01 | Yes | Yes but in next FY | The LOI holder has been counselled and provided with the revised drawings. The candidate has requested additional time for NOC | No | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | 2028-01-01 | 2028-02-01 | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jul'16 | SC
11 | SHIRSHUFAL | SMT DEEPA NILAMBAR KHARAT | Pune Tathawade RSA |  | 9423135961 | C | A | KSK | KSK-A w/o Reco | N/2016/IN000260/MAH/000044/3203/00018 | SRMP 2014-15 | 2016-09-16 | 3548 | >5Y | PUNE | SC | Group 2: Firm Offer | 6 | 42 | 48 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Land Not Available, Financial problem with LOI holder | 2028-09-01 | Yes | Yes but in next FY | The RO land is on the planned township area of the Baramati . The approval is applied for NA permission from the ministry which is still pending for approval | No | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | 2028-01-01 | 2028-02-01 | Yes | Recived | [10 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Sep'16 | SC
12 | ON LHS FROM PUNE TO SATARA ON NH-04 IN BET KM STONE 770&773 (PUNE BANG | Miss Pooja Jijaba Pawar | Satara West RSA |  | 9820521233 | D1 | B | RO | RO B Site | N/2016/IN000673/MAH/000098/3203/00036 | 2014-15 | 2016-12-07 | 3466 | >5Y | SATARA | OPEN | Group 1: Owned land | 20 | 130 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | HPC RO is commissioned on same land. LOI may be cancelled after taking in writing | 2028-09-01 | No | No | HPC Commissioned on same site.Dealer has given surrender letter on 10.04.2026 which reached to FO on 11.05.2026 through speed post | To be recommended by 14.05.2026 | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Dec'16 | Open
13 | BARAMATI, TAL - BARAMATI | APMC, BARAMATI | Pune Tathawade RSA |  |  | D2 | A | RO | RO A Site | 2018/IN000053/MAH/000004/3203/00002 | NA | 2018-07-16 | 2880 | >5Y | PUNE | Govt Agency | Group 1: Owned land | 70 | 100 | 170 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available | 2028-09-01 | Yes | No | LOI holder is the govt party does not have the free hold of the proposed RO land , LOI to be cancelled | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA | [12 empty] | Cancelled |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jul'18 | govt
14 | KHANDALA, A/P KHANDALA, TAL. KHANDALA | APMC, LONAND | Satara East RSA |  |  | C | A | KSK | KSK-A Recovery | 2018/IN000056/MAH/000006/3203/00004 | NA | 2018-07-30 | 2866 | >5Y | SATARA | Govt Agency | Group 1: Owned land | 35 | 50 | 85 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Govt Site, Land is not available | 2028-09-01 | Yes | No | Govt Site, Land is not available | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jul'18 | govt
15 | APMC, LONAND, A/P LONAND, TAL. KHANDALA | APMC,LONAND | Satara East RSA |  |  | C | A | KSK | KSK-A Recovery | 2018/IN000055/MAH/000005/3203/00003 | NA | 2018-07-30 | 2866 | >5Y | SATARA | Govt Agency | Group 1: Owned land | 35 | 50 | 85 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Govt Site, Land is not available | 2028-09-01 | Yes | No | Govt Site, Land is not available | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jul'18 | govt
16 | SONGIRWADI, Taluka Wai, District Satara | APMC, WAI | Satara West RSA |  |  | D2 | A | RO | RO A Site | 2018/IN000094/MAH/000016/3203/00009 | 2011-13 | 2018-10-11 | 2793 | >5Y | SATARA | Govt Agency | Group 1: Owned land | 25 | 85 | 110 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available | 2028-09-01 | YES | NO | These are APMC sites. APMC is not responding and not following up for NOCs | To be recommended for cancellation by 23.05.2026 after meeting taluka wise chairman for APMC Site | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Oct'18 | govt
17 | KUDAL, Taluka Jawali, District Satara | APMC, JAWALI | Satara West RSA |  |  | C | A | KSK | KSK-A Recovery | 2018/IN000093/MAH/000015/3203/00008 | 2011-13 | 2018-10-11 | 2793 | >5Y | SATARA | Govt Agency | Group 1: Owned land | 30 | 55 | 85 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available | 2028-09-01 | YES | NO | These are APMC sites. APMC is not responding and not following up for NOCs | To be recommended for cancellation by 23.05.2026 after meeting taluka wise chairman for APMC Site | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Oct'18 | govt
18 | GONDAVALE, Taluka Man, District Satara | APMC, MAN | Satara East RSA |  | 7588636344 | D1 | A | RO | RO A Site | 2018/IN000124/MAH/000018/3203/00010 | 2016-17 | 2019-01-02 | 2710 | >5Y | SATARA |  | Group 1: Owned land | 55 | 100 | 155 |  | No | Non-Commissionable | 2028-09-01 | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Yes | Yes |  | 2028-06-01 | Yes | Yes | Pending |  |  | Govt Site, Land is not available | 2028-09-01 | Yes | No | Govt Site, Not interested | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | LEC not available |  | Pending | [8 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jan'19 | govt
19 | SAIDAPUR ON MFR 36A TALUKA-SATARA | SUDAM PHAJGE | Satara West RSA |  | 9423113676 | E | A | KSK | KSK A SiteCorpu | M/2018/IN000926/MAH/000094/3203/00027 | 2018-19 | 2019-02-21 | 2660 | >5Y | SATARA | SC | Group 2: Firm Offer | 6 | 40 | 46 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Issue |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available with candidate | 2028-09-01 | YES | NO | Land negotiation with original landowner has been failed- NEGOTIATION REPORT UNSIGNED. Failed negotitation case. Applicant lives in Daund and not turning up for signing MOM at Satara | To be recommended for cancellation by 23.03.2026 | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Feb'19 | SC
21 | ON MDR 38 FROM VILLAGE VADUJ TO VILLAGE AMBERI (TALUKA-KHATAV) | VARSHA BHANUDAS MANE | Satara East RSA |  |  | E | B | KSK | KSK-B w/o Reco | M/2018/IN000958/MAH/000104/3203/00031 | 2018-19 | 2019-02-21 | 2660 | >5Y | SATARA | OPEN | Group 1: Owned land | 6 | 40 | 46 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required | Available | 2028-06-01 | Yes | Yes |  |  |  | Land is not available with canidate due to divorce with Landowner Husband | 2028-09-01 | Yes | No | Land is not available with canidate due to divorce with Landowner Husband | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Feb'19 | Open
20 | FROM THEUR TO NAIGAON ON THEUR-NAIGAON ROAD | NANDKUMAR VASANTRAO YADAV | Pune Hadapsar RSA |  | 8999868245 | D2 | B | RO | RO B Site | M/2018/IN000881/MAH/000078/3203/00020 | 2018-19 | 2019-02-21 | 2660 | >5Y | PUNE | CC-1 DEFENCE | Group 2: Firm Offer | 30 | 80 | 110 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding due to high land conversion charges | 2028-09-01 |  | No |  | No | [15 empty] | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Feb'19 | Open
23 | SUSGAON | Mahendra Sasar | Pune City RSA |  | 9822234040 | C | B | RO | RO B Site | M/2018/IN001734/MAH/000179/3203/00059 | 2018-19 | 2019-03-14 | 2639 | >5Y | PUNE | OPEN | Group 1: Owned land | 50 | 100 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 |  | NO | Candidate not interested - submitted original LOI with letter | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Mar'19 | Open
25 | VILLAGE RAJURI ON AHMEDNAGAR-KALYAN ROAD(NH-61) | MANISHA GHANGALE | Pune Wagholi RSA |  | 9960006945 | D1 | B | RO | RO B Site | M/2018/IN002409/MAH/000260/3203/00079 | 2018-19 | 2019-03-29 | 2624 | >5Y | PUNE | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | Yes |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Candidate not responding |  | Not Required | Not Required | Available | 2028-06-01 | Yes | Yes | Approved | Yes | 4327618 | Fixed fee given, RO under construction, 1 crore mortgage on land, we can commission in later after complaint clearance | 2028-09-01 | Yes | No | Fixed fee given, RO under construction, 1 crore mortgage on land, we can commission in later after complaint clearance | by 25.05.2026 |  |  | Yes |  | Available |  |  |  |  | Received |  |  | Available | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Mar'19 | Open
26 | FROM PATAS TOLL PLAZA TO KURKUMBH ON RHS OF PUNE SOLAPUR NH65 | SAMBHAJI SHIVAJI NEWALE | Pune Hadapsar RSA |  | 9028974805 | D1 | B | RO | RO B Site | M/2019/IN000808/MAH/000026/3203/00013 | 2018-19 | 2019-06-06 | 2555 | >5Y | PUNE | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | NOC rejected by DM/NH/PWD |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available | 2028-09-01 |  | No |  | No | [15 empty] | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jun'19 | Open
27 | VILLAGE MEHEKARI ON NH-61 ON LHS TOWARDS PATHARDI | AMOL NAMDEO SHIRSATH | Ahmednagar West RSA |  |  | D1 | B | RO | RO B Site | M/2019/IN002068/MAH/000095/3203/00028 | 2018-19 | 2019-08-26 | 2474 | >5Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 145 | 175 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Due to junction issue NH accress permmission cann't be obtained, LOI candidates has issued multiple letters. | Yes | Yes | Yes | Applied | Applied | Applied | NA | NA | NA | Applied | Yet to assign | No | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Aug'19 | OBC
28 | PRANJALI PATIL NAGAR, PUNE CITY, | BHUSHAN BABULAL MUTHA | Pune City RSA |  | 9850095753 | A | A | RO | RO A Site | M/2019/IN004073/MAH/000156/3203/00040 | 2018-19 | 2019-12-05 | 2373 | >5Y | PUNE | OPEN | Group 2: Firm Offer | 85 | 100 | 185 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | NOC rejected by DM/NH/PWD |  |  |  | NO | 2028-06-01 | [5 empty] | Land is not available with LOI holder | 2028-09-01 | YES | NO | land in eco sensitive zone, NOC rejection | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Dec'19 | Open
29 | SANSAR(TALUKA-INDAPUR) | SUPRIYA NIMBALKAR | Pune Saswad RSA |  | 9923258888 | E | B | KSK | KSK-B w/o Reco | M/2019/IN006056/MAH/000250/3203/00072 | 2018-19 | 2020-03-20 | 2267 | >5Y | PUNE | OPEN | Group 1: Owned land | 6 | 40 | 46 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 | Yes | No | LOI holder not interested- to be cancelled | No | Yes | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Mar'20 | Open
32 | AT VAKILWASTI ON RHS OF INDAPUR-AKLUJ ROAD, | SURESH BALBHIM MEHER | Pune Saswad RSA |  | 9561107474 | D1 | B | RO | RO B Site | M/2020/IN000558/MAH/000083/3203/00030 | 2018-19 | 2020-06-15 | 2180 | >5Y | PUNE | OBC | Group 1: Owned land | 40 | 110 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 | Yes | No | NH overbridge going to come infront of plot, NH not giving permission | No | Yes | Applied | Applied | Applied | Applied | Applied | Applied | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jun'20 | OBC
33 | PIMPALGAON SIDDHNATH ON JUNNAR - OTUR ROAD, | BHAGYASHREE SAGAR GAIKWAD | Pune Wagholi RSA |  |  | D2 | A | RO | RO A Site-Corpu | M/2020/IN000721/MAH/000089/3203/00034 | 2018-19 | 2020-07-03 | 2162 | >5Y | PUNE | SC | Group 2: Firm Offer | 35 | 120 | 155 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Subjuidice |  | Yes | Yes | Available | 2028-06-01 | Yes | Yes |  | Yes | Yes | Land is not available. Matter subjudice due to fake appendix III affidavit | 2028-09-01 | Yes | No | NOC available. Complaint case against LOI holder for false document submission- under investigation. Lease done | By 15.05.2026 |  |  |  |  | Not Required | [8 empty] | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jul'20 | SC
34 | FROM KHOKAR PHATA TO BHOKAR PHATA ON SHRIRAMPUR NEWASA SH-44 | RADHIKA ASANE | Ahmednagar East RSA |  | 9766297801 | D2 | B | RO | RO B Site | M/2020/IN000888/MAH/000099/3203/00038 | 2018-19 | 2020-07-20 | 2145 | >5Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 80 | 110 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding and not picking calls and not replying to letters | 2028-09-01 | Yes | NO | LOI holder not responsive after Jio BP RO started operation nearby- LOI to be cancelled | [7 empty] | NA | [8 empty] | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jul'20 | OBC
35 | WITHIN 5 KM FROM NARAYANA GAON BUS STAND TOWARDS NASHIK ON LHS OF PUNE TO NA | SURESH NETAKE | Pune Wagholi RSA |  | 8928175555 | D1 | A | RO | RO A Site-Corpu | M/2020/IN001524/MAH/000149/3203/00050 | 2018-19 | 2020-09-07 | 2096 | >5Y | PUNE | SC | Group 1: Owned land | 30 | 125 | 155 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | No Progress in NOC. Parner landowner withdrew | 2028-09-01 | Yes | No | LOI can be cancelled | BY 25.05.2026 |  |  |  |  | 0 | [20 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Sep'20 | SC
37 | ON KARJAT- SHRIGONDA ROAD VIA WALVAD(TALUKA-KARJAT) , | KRUSHNA KUNDALIK JAYBHAY | Ahmednagar West RSA |  | 9270375055 | E | B | KSK | KSK-B w/o Reco | M/2020/IN001776/MAH/000178/3203/00062 | 2018-19 | 2020-09-29 | 2074 | >5Y | AHMADNAGAR | OPEN | Group 1: Owned land | 10 | 30 | 40 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Disinterested LOI candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Sep'20 | Open
36 | AT WADKI ON HADAPSAR- PANDHARPUR NH , | JYOTI ARVIND KALOKHE | Pune Hadapsar RSA |  | 9822503220 | D1 | A | RO | RO A Site-Corpu | M/2020/IN001767/MAH/000172/3203/00056 | 2018-19 | 2020-09-29 | 2074 | >5Y | PUNE | SC | Group 2: Firm Offer | 30 | 125 | 155 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Alternate land offer letter was provided to Candidate but Candidate failed to provide alternate land | 2028-09-01 |  | No |  | No | [25 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Sep'20 | SC
39 | VILLAGE PATEGAON ON AHMEDNAGAR TO SOLAPUR NH-516A , | MUBARAK INAMDAR | Ahmednagar West RSA |  | 9284220660 | D1 | B | RO | RO B Site | M/2020/IN001937/MAH/000199/3203/00067 | 2018-19 | 2020-10-20 | 2053 | >5Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Due to junction issue. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Oct'20 | Open
38 | FROM YAVAT TO CHOUFULLA JUNCTION ON LHS OF PUNE SOLAPUR NH65 , | SAGAR SUBHASH NANAWARE | Pune Hadapsar RSA |  | 9604404204 | D1 | A | RO | RO A Site-Corpu | M/2020/IN001947/MAH/000203/3203/00071 | 2018-19 | 2020-10-20 | 2053 | >5Y | PUNE | ST | Group 1: Owned land | 30 | 125 | 155 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Candidate Not Responding | 2028-09-01 |  | No |  | No | [25 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Oct'20 | st
40 | VILLAGE GOLESHWAR ON RHS OF KARAD TO TASGAON NH266 , | RANJEET KHASHABA JADHAV | Satara West RSA |  | 9822458819 | D1 | B | RO | RO B Site | M/2020/IN002152/MAH/000215/3203/00075 | 2018-19 | 2020-11-03 | 2039 | >5Y | SATARA | OPEN | Group 1: Owned land | 40 | 110 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Frontage is not avaiable at land | 2028-09-01 | YES | NO | Sufficient frontage is not available with candidate | To be recommended for cancellation after ascertaining actual site condition | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Nov'20 | Open
41 | BHOSE TO SHELGAON ON NH-548D , | R. K. AWATE & A. P. AWATE, | Pimpri Chinchwad RSA |  | (9604274393)(9890196145) | D1 | A | RO | RO A Site | M/2020/IN002179/MAH/000221/3203/00081 | 2018-19 | 2020-11-05 | 2037 | >5Y | PUNE | OPEN | Group 1: Owned land | 30 | 150 | 180 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Land has been rejected by NHAI | 2028-09-01 |  | No | Alternate land LEC done in nov23- approval for same to be checked | No |  |  |  |  | 0 | [20 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Nov'20 | Open
42 | ON RIGHT HAND SIDE OF PUNE AHMEDNAGAR ROAD (NH753F (OLD SH-60)) BETWEEN | RUPALI VIRENDRA LANDGE | Pune Wagholi RSA |  | 9175483051 | D1 | B | RO | RO B Site | M/2020/IN002944/MAH/000301/3203/00100 | 2018-19 | 2021-01-25 | 1956 | >5Y | PUNE | OPEN | Group 1: Owned land | 50 | 100 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Fund issue | by 25.05.2026 |  |  |  |  | 0 | [10 empty] | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jan'21 | Open
44 | VILLAGE WALUNJ ON AHMEDNAGAR-SOLAPUR ROAD ON LHS | Prashant Sabajirao Gaikwad | Ahmednagar West RSA |  | 9822287715 | D1 | B | RO | RO B Site | M/2021/IN000866/MAH/000046/3203/00012 | 2018-19 | 2021-08-09 | 1760 | 4-5Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Disinterested LOI candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Aug'21 | Open
45 | LASURNE(TALUKA-INDIAPUR) | AMOL LOKHANDE | Pune Saswad RSA |  | 9604104321 | E | A | KSK | KSK A SiteCorpu | M/2021/IN001550/MAH/000107/3203/00030 | 2018-19 | 2021-11-01 | 1676 | 4-5Y | PUNE | SC | Group 2: Firm Offer | 6 | 40 | 46 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available | 2028-09-01 | Yes | Yes but in next FY | Land issue. | NA | Yes | Received | Applied | Applied | Applied | Applied | Applied | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | Yes | Recived | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Nov'21 | SC
46 | FROM MASWAD TO MARDI ON | RAVIRAJ RAJKUMAR SURYAWANSHI | Satara East RSA |  | 7755900181 | E | B | KSK | KSK-B w/o Reco | M/2022/IN000276/MAH/000012/3203/00005 | 2018-19 | 2022-06-02 | 1463 | 4-5Y | SATARA | OPEN | Group 1: Owned land | 6 | 40 | 46 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candiadte is not responding | 2028-09-01 | Yes | No | Candiadte is not responding | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jun'22 | Open
47 | VILLAGE NIMGAON DAKU ON TO SOLAPUR NH-516A , | ASHOKKUMAR PITAMBAR ANARASE | Ahmednagar West RSA |  | 9730142424 | D1 | B | RO | RO B Site | M/2022/IN000277/MAH/000013/3203/00006 | 2018-19 | 2022-06-02 | 1463 | 4-5Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Disinterested LOI candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Jun'22 | OBC
48 | VILLAGE SHEVGAON, | PUSHPAK PURUSHOTTAM DHOOT | Ahmednagar EASt RSA |  |  | D2 | A | RO | RO A Site | L/2022/IN000072/MAH/000010/3203/00003 | SRMP | 2022-07-06 | 1429 | 3-4Y | AHMADNAGAR |  |  | 35 | 70 | 105 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | LOI issued to Landowner for COCO Shevgaon |  |  |  |  | 2028-06-01 | [5 empty] | This is COCO LOI under landowner policy. Landowner is not interested | 2028-09-01 | Yes | NO | LOI awarded to land owner, and he wants very high rent and not ready for long lease | [7 empty] | NA | [9 empty] | To be done | [8 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Jul'22 | Open
49 | SHIRVAL TO SHEDGEWADI ON SHIRVAL LONAND ROAD | AISHWARYA SHIRISH TAMBE | Satara East RSA |  | 9765940088 | D1 | A | RO | RO A Site-Corpu | M/2022/IN000591/MAH/000031/3203/00008 | 2018-19 | 2022-08-02 | 1402 | 3-4Y | SATARA | SC | Group 2: Firm Offer | 40 | 120 | 160 |  | No | Non-Commissionable | 2028-09-01 | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Yes | Yes |  | 2028-06-01 | [5 empty] | Charge on Land, LOI holder is not showing interest | 2028-09-01 | Yes | No | Charge on Land, LOI holder is not showing interest | No | Yes | NA | NA | NA | NA | NA | NA | NA | NA | In Process | No | NA | NA | Yes | Recived | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Aug'22 | SC
50 | AT WAKHARI ON LHS OF PUNE TO SOLAPUR NH65 , | RAVIDAS GAVIT | Pune Hadapsar RSA |  | 9284942435 | D1 | A | RO | RO A Site-Corpu | M/2022/IN000595/MAH/000033/3203/00010 | 2018-19 | 2022-08-02 | 1402 | 3-4Y | PUNE | PHP ( ST ) | Group 2: Firm Offer | 30 | 125 | 155 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | NOC rejected by DM/NH/PWD |  |  |  |  | 2028-06-01 | [5 empty] | Candidate Not Responding | 2028-09-01 |  | No |  | No | [13 empty] | Yes | Recived | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Aug'22 | st
52 | SASWAD-KAPURHOL-BHOR ROAD,DEVADI , | PRADEEP KHAIRE | Pune Tathawade RSA |  | 9850771878 | D2 | B | RO | RO B Site | M/2022/IN001166/MAH/000066/3203/00018 | 2018-19 | 2022-10-31 | 1312 | 3-4Y | PUNE | OPEN | Group 2: Firm Offer | 30 | 90 | 120 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available | 2028-09-01 | Yes | No | The candidate has applied in group 2 and there is dispute in the land and is proposed for cancellation | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Cancelled |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Oct'22 | Open
54 | ON INDAPUR BYPASS ON LHS OF PUNE TO SOLAPUR NH65 , | ANIL ABHIMAN MAKHARE | Pune Saswad RSA |  | 7028654145 | D1 | A | RO | RO A Site-Corpu | M/2022/IN001224/MAH/000073/3203/00022 | 2018-19 | 2022-11-10 | 1302 | 3-4Y | PUNE | SC | Group 1: Owned land | 30 | 130 | 160 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Cancellation Approved | 2028-09-01 | Yes | No | There is financial constraint with dealer- LOI to be cancelled | Yes | No | No | No | No | No | No | No | NA | NA | No | No | [14 empty] | Cancelled |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Nov'22 | SC
55 | ON RIGHT HAND SIDE OF PUNE AHMEDNAGAR ROAD (NH753F) BETWEEN KONDHAPURI A | ALKA GAIKWAD | Pune Wagholi RSA |  | 9175168445 | D1 | A | RO | RO A Site-Corpu | M/2022/IN001298/MAH/000087/3203/00029 | 2018-19 | 2022-11-21 | 1291 | 3-4Y | PUNE | SC | Group 2: Firm Offer | 30 | 125 | 155 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available,Candidate not reacahable , need to meet |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available with candidate | 2028-09-01 | Yes | No | Applicant requested for addendum to LOI with new land in same stretch but title not clear of new land. LSR dtd 08.12.2023 | [26 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Nov'22 | SC
57 | MSRTC SHRIRAMPUR TAL. SHRIRAMPUR, DISTRICT AHMEDNAGAR | MSRTC SHRIRAMPUR | Shirdi RSA |  |  | D2 | A | RO | RO A Site | 2022/IN000234/MAH/000019/3203/00006 | GOVT AGENCY | 2023-02-09 | 1211 | 3-4Y | AHMADNAGAR | Govt Agency | Group 1: Owned land | 55 | 110 | 165 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Yes | Pending |  | 2028-06-01 | [5 empty] | There is no land available | 2028-09-01 | Yes | No | There is no land available | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | [11 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Feb'23 | govt
58 | MSRTC NASRAPUR AT CHELADI, VILLAGE NASRAPUR, DISTRICT PUNE | MSRTC NASRAPUR | Pune Tathawade RSA |  |  | D1 | A | RO | RO A Site | 2022/IN000233/MAH/000018/3203/00005 | GOVT AGENCY | 2023-02-09 | 1211 | 3-4Y | PUNE | Govt Agency | Group 1: Owned land | 60 | 115 | 175 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Title of Land is not Clear |  |  |  |  | 2028-06-01 | [5 empty] | Land Not Available | 2028-09-01 | No | NO | MSRDC has not taken the drawing as on date. Also NOC application is pending | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Feb'23 | govt
59 | MSRTC PARGAON KHANDALA TALUKA KHANDALA, DISTRICT SATARA | MSRTC PARGAON KHANDALA | Satara East RSA |  |  | C | A | RO | RO A Site | 2022/IN000237/MAH/000020/3203/00007 | GOVT AGENCY | 2023-02-15 | 1205 | 3-4Y | SATARA | Govt Agency | Group 1: Owned land | 35 | 60 | 95 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Title of Land is not Clear |  |  |  |  | 2028-06-01 | [5 empty] | Govt Site, Land is not available | 2028-09-01 | Yes | No | Govt Site, Land is not available | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | [12 empty] | Pending |  |  |  |  | Pre 2018/Govt | Yes | [5 empty] | Feb'23 | govt
60 | MIDSANGAVI ON NH-61 , | SANJAY DONGARE | Ahmednagar West RSA |  | 9822979166 | D1 | B | RO | RO B Site | M/2022/IN001662/MAH/000111/3203/00039 | 2018-19 | 2023-03-02 | 1190 | 3-4Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 130 | 160 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Due to BPC NRO commissioned in same stratch and hence LOI candidate not interested for RO development and seeking alternate land in different stretch. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Mar'23 | Open
61 | SARAFWADI (TALUKA-INDAPUR) , | TUSHAR SHENDE | Pune Saswad RSA |  | 8600400101 | E | B | KSK | KSK-B w/o Reco | M/2022/IN001717/MAH/000113/3203/00041 | 2018-19 | 2023-03-20 | 1172 | 3-4Y | PUNE | OBC | Group 2: Firm Offer | 6 | 40 | 46 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Financial issue with LOI holder | 2028-09-01 | Yes | Yes but in next FY | Slow and financially week candidate | No | Yes | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Mar'23 | OBC
63 | ON SH147 BETWEEN VILLAGE WATHAR NIMBALKAR TO VILLAGE TATHAVADA , | ARUNA BALASAHEB SHINDE | Satara East RSA |  | 7756899321 | D2 | B | RO | RO B Site | M/2022/IN001733/MAH/000118/3203/00044 | 2018-19 | 2023-03-27 | 1165 | 3-4Y | SATARA | OBC | Group 1: Owned land | 30 | 80 | 110 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate not interested | 2028-09-01 | Yes | No | Candidate not interested | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Mar'23 | OBC
64 | MURUM(TALUKA-BARAMATI) , | SHITAL GHODAKE | Pune Tathawade RSA |  | 8308704647 | E | A | KSK | KSK-A w/o Reco | M/2022/IN001742/MAH/000121/3203/00045 | 2018-19 | 2023-03-31 | 1161 | 3-4Y | PUNE | SC | Group 2: Firm Offer | 6 | 40 | 46 |  | No | Non-Commissionable | 2028-09-01 | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Yes | Pending |  | 2028-06-01 |  | Pending |  |  |  | PWD pending, larger land required as per PWD | 2028-09-01 | Yes | No | PWD pending, larger land required as per PWD, PWD NOC can not be given in the proposed land as the frontage does not meet the IRC rules | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Mar'23 | SC
65 | WITHIN 5 KMS FROM SASWAD ON SASWAD-NARAYANPUR ROAD , | ULKA GAIKWAD | Pune Saswad RSA |  | 9405815809 | D2 | A | RO | RO A Site-Corpu | M/2023/IN000025/MAH/000002/3203/00001 | 2018-19 | 2023-04-10 | 1151 | 3-4Y | PUNE | ST | Group 2: Firm Offer | 30 | 75 | 105 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land is not available |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available | 2028-09-01 | Yes | No | Slow Candidate and land issue | No | Yes | Applied | Applied | Applied | Applied | Applied | Applied | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | [12 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Apr'23 | st
67 | THEUR ON MDR (TAL-HAVELI) | ANKUSH KAMBLE | Pune Hadapsar RSA |  | 9822432697 | E | A | KSK | KSK-A w/o Reco | M/2023/IN000094/MAH/000009/3203/00005 | 2018-19 | 2023-05-23 | 1108 | 3-4Y | PUNE | SC | Group 2: Firm Offer | 6 | 40 | 46 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Land is going in PMRDA acquisition, Candidate has to arrange additional land to ensure depth of plot as per advertisement | 2028-09-01 |  | No |  | No | [13 empty] | Yes | Recived | [10 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | May'23 | SC
69 | BARAMATI WML | TEJASWINI AKASH GALINDE | Pune Tathawade RSA |  | 8208953981 | C | A | RO | RO A Site-Corpu | M/2023/IN000541/MAH/000040/3203/00017 | 2018-19 | 2023-10-10 | 968 | 2-3Y | PUNE | SC | Group 1: Owned land | 80 | 120 | 200 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | LOI cancellation Proposaed | 2028-09-01 | Yes | No | The LOI is already cancelled and the selection of another candidate is done , Scrutiny pending | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Cancelled |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Oct'23 | SC
76 | From KM Stone 102 to 104 on RHS on NH (Nhavare - Shrigonda Road) | AJINKYA DATTATRAY MOKASHI | Pune Wagholi RSA | Pune IV RSA | 9764372331 | D1 | B | RO | RO B Site | R/2023/IN001262/MAH/000089/3203/00030 | 2023-24 | 2023-12-04 | 913 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 124 | 154 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | LOI can be cancelled | No |  |  |  |  | 0 | [8 empty] | Yes | #N/A | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
78 | From Bharat Vidyalaya to Bodardi Phata on Mirajgaon-Shrigonda Road | ONKAR SHIVAJI RAHINJ | Ahmednagar West RSA | Ahmednagar West RSA | 9172969896 | E | B | KSK | KSK-B w/o Reco | R/2023/IN001333/MAH/000095/3203/00036 | 2023-24 | 2023-12-07 | 910 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 20 | 80 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Due to junction issue. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
83 | Within 2 km from Shri Ram Mandir ,Watephal towards Solapur on LHS on Ahmednagar- Solapur NH | AJINKYA DATTATRAYA NARALE | Ahmednagar West RSA | 1598 | 8668445459 | D1 | B | RO | RO B Site | R/2023/IN001462/MAH/000110/3203/00044 | 2023-24 | 2023-12-11 | 906 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Disinterested LOI candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
84 | From KM STONE 789 TO 787 ON LHS of Pune to Satara Road | SAGAR SIDHU DEVKATE | Satara West RSA | 1615 | 9921918171 | D1 | B | RO | RO B Site | R/2023/IN001442/MAH/000106/3203/00041 | 2023-24 | 2023-12-11 | 906 | 2-3Y | SATARA | OBC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Cancellation Approved | 2028-09-01 | YES | NO | BPC RO - Rudransh Petroleum commissioned. | Recommended for cancellation | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | OBC
82 | From Shivri to Shivajiraje Chowk (Jejuri) on LHS of Saswad -Jejuri NH | MAYURI ANIRUDDHA RATHI | Pune Saswad RSA | 1708 | 9423575556 | D1 | B | RO | RO B Site | R/2023/IN001443/MAH/000107/3203/00042 | 2023-24 | 2023-12-11 | 906 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 40 | 120 | 160 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | No | No | LOI not yet received by LOI holder | Yes | No | No | No | No | No | No | No | NA | NA | No | No |  |  | Yes | Received | NA | NA | Not Required | [7 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
85 | From Shiroli to Rajgurunagar on RHS on NH (Pune Nashik Road) | DATTATRAY BALKRUSHNA KOKANE | Pune Wagholi RSA | 1867 | 9890105532 | D1 | B | RO | RO B Site | R/2023/IN001517/MAH/000116/3203/00046 | 2023-24 | 2023-12-12 | 905 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 40 | 150 | 190 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 | Yes | No | No,Candidate is not reacahable , Residence visit is planned by 30.05.2026 | [5 empty] | 0 | [8 empty] | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
88 | Within 3 KM from Lonand Bus Stand Towards Pune on Satara Lonand Road | YASHODHAN SADASHIV SHINDE | Satara East RSA | 1979 | 9881321999 | D1 | B | RO | RO B Site | R/2023/IN001555/MAH/000127/3203/00051 | 2023-24 | 2023-12-13 | 904 | 2-3Y | SATARA | OPEN | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | CANDIDATE IS HAVING TOO MANY LOIs, land yet to be transferred to LOI holder name. Single candidate. LOI can be retained | 2028-09-01 | Yes | No | CANDIDATE IS HAVING TOO MANY LOIs, land yet to be transferred to LOI holder name. Single candidate. LOI can be retained | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
87 | From Shirur bus stand to Shirur NH Intersection on Shirur-Sangavi Road | SUBHASH MANOHAR KEDAR | Pune Wagholi RSA | 2021 | 8983987277 | C | A | RO | RO A Site-Corpu | R/2023/IN001560/MAH/000131/3203/00053 | 2023-24 | 2023-12-13 | 904 | 2-3Y | PUNE | ST | Group 2: Firm Offer | 90 | 70 | 160 |  | No | Non-Commissionable | Yes | Approved | Yes | Yes |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | land is not available |  | Yes | Yes | Available | 2028-06-01 | Yes | Yes | Dropped | Yes |  | Landowner is not interested in giving land now. LOI holder is seeking legal recourse for contunuing on the land. | 2028-09-01 | Yes | Yes but in next FY | LSR on email from shalukar, direct lease from land owner, 100/80 by 3rd year, negotiation unsuccessful | NOC available ,land owner is not agreeing for lease |  |  |  |  | Yet to Apply |  |  |  |  | Received |  |  | Yet to Apply | Yes | Received |  | Yes | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | st
89 | Village Warur Kh. on Shevgaon Akhegaon Road Tal Shevgaon | MANISHA BALASAHEB MURDARE | Ahmednagar EASt RSA | 2117 | 8668538688 | E | B | KSK | KSK-B w/o Reco | R/2023/IN001539/MAH/000122/3203/00047 | 2023-24 | 2023-12-13 | 904 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 70 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding and not picking calls and not replying to letters | 2028-09-01 | Yes | NO | LOI holder not responding- not collected LOI - to be cancelled | [7 empty] | NA | [6 empty] | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
92 | From Dahiwadi to Yelegaon on Dahiwadi Phaltan Road | KUNAL DURYODHAN WAGHMARE | Satara East RSA | Satara RSA | 8452980100 | D1 | A | RO | RO A Site-Corpu | R/2023/IN001670/MAH/000168/3203/00061 | 2023-24 | 2023-12-15 | 902 | 2-3Y | SATARA | SC | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | No |  |  | 2028-06-01 | [5 empty] | Candidate not responding | 2028-09-01 | Yes | No | Candidate not responding | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | #N/A | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | SC
91 | Khalumbre to Sudanvadi on LHS on Talegaon Chakan Road | ISHWAR TECHWANI | Pimpri Chinchwad RSA | 1761 | 8669150105 | D1 | B | RO | RO B Site | R/2023/IN001676/MAH/000170/3203/00063 | 2023-24 | 2023-12-15 | 902 | 2-3Y | PUNE | OPEN | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate has written mail for Cancelaltion | 2028-09-01 |  | No | Land dispute b/w land owner and LOI holder; High demand for doing NA | No: No; NA: 0; Yes Yes: Yes; Yes #N/A: Received | NA | NA | Not Required | [7 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
94 | At Jadhav Mala, Siddharth Nagar on 25m DP Road, within Ahmednagar Muncipal Limits | JAYANT MACHINDRANATH JADHAV | Ahmednagar EASt RSA | 1909 | 9822704949 | C | B | RO | RO B Site | R/2023/IN001763/MAH/000180/3203/00065 | 2023-24 | 2023-12-18 | 899 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 100 | 50 | 150 |  | No | Non-Commissionable | Yes | NA |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land is not Available. School is proposed on the land |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes | Approved | Yes | 4338118 | LOI Holder has provided the land for school. LOI needs to be cancelled | 2028-09-01 | Yes | NO | NOC pending from TP, LSR pending | NA: Yes; NA: Not Required; NA NA: NA; NA NA: Received; NA NA: 2026-10-01; Yes Yes: Yes | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
95 | Within 2 kms From Athithi Veg Restaurant, near Sinhagad Road towards Hinge khurd on Tukai Nagar Road under PMC Limits | YASHODHAN SADASHIV SHINDE | Pune City RSA | 1606 | 9881321999 | A | B | RO | RO B Site | R/2023/IN001765/MAH/000181/3203/00066 | 2023-24 | 2023-12-18 | 899 | 2-3Y | PUNE | OBC | Group 2: Firm Offer | 200 | 80 | 280 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 | YES | NO | Candidate slow | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | OBC
97 | Within 2 kms From intersection of Katraj-Ambegaon BK Road and Dattanagar Road towards Narhe on Katraj Ambegaon BK Narhe Road | YASHODHAN SADASHIV SHINDE | Pune City RSA | 2026 | 9881321999 | A | B | RO | RO B Site | R/2023/IN001868/MAH/000197/3203/00073 | 2023-24 | 2023-12-19 | 898 | 2-3Y | PUNE | OBC | Group 2: Firm Offer | 180 | 150 | 330 |  | No | Non-Commissionable | 2028-06-03 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Candidate is slow, having multiple LOIs. We have issued him a letter for expediting NOC Process. | 2028-09-01 | YES | NO | Change of Land due to BPCL RO already available adjacent to Land | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | OBC
99 | Within 3 KM from intersection of Pune Satara NH and Shirwal Lonand Road toward Lonand on Shirwal Lonand Road | YASHODHAN SADASHIV SHINDE | Satara East RSA | 1620 | 9881321999 | D1 | B | RO | RO B Site | R/2023/IN001861/MAH/000193/3203/00069 | 2023-24 | 2023-12-19 | 898 | 2-3Y | SATARA | OPEN | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Cancellation Approved | 2028-09-01 | Yes | No | Cancellation Approved | Yes | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | Open
100 | From Lonand to Taradgaon on Lonand Phaltan Road | RAMDAS SAMPAT MAHANVAR | Satara East RSA | 2037 | 9892420505 | D1 | B | RO | RO B Site | R/2023/IN002096/MAH/000234/3203/00083 | 2023-24 | 2023-12-27 | 890 | 2-3Y | SATARA | OBC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | NOC rejected by DM/NH/PWD |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate is not interested on the land offered with LOI and wants land change outside advertisement area | 2028-09-01 | Yes | No | Candidate is not interested on the land offered with LOI and wants land change outside advertisement area | Yes | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | #N/A | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Dec'23 | OBC
101 | From KM stone 11 to 13 on RHS on SH (Shirur-Satara Road ) | PUJA LAHU ZENDE | Pune Wagholi RSA | 1763 | 9657757830 | D2 | A | RO | RO A Site-Corpu | R/2023/IN002338/MAH/000274/3203/00089 | 2023-24 | 2024-01-04 | 882 | 2-3Y | PUNE | SC | Group 1: Owned land | 25 | 80 | 105 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land is not available |  | No |  |  | 2028-06-01 | [5 empty] | Candidate did not provide any alternate land, even after alternate land offer | 2028-09-01 | Yes | No | Alternate land paper didnt provided by candidate in 180 days | Yes: Recommendation by 15.05.2026; NA: Not Required; Yes: Yes; #N/A: Received | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | SC
102 | Within 4 km from Warje bridge towards Chandni Chowk on LHS of Pune Satara Highway | RAVINDRA SAKHARAM TAGUNDE | Pune City RSA | 1637 | 9975292929 | A | B | RO | RO B Site | R/2023/IN002358/MAH/000275/3203/00090 | 2023-24 | 2024-01-05 | 881 | 2-3Y | PUNE | OBC | Group 1: Owned land | 200 | 130 | 330 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land issue |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Site requiresd MOD Approval, which is main reason for delay. Land requires biodiversity approval | 2028-09-01 | YES | NO | Biodiversity park issue | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | OBC
108 | On LHS, From Bhagwatipur to Loni on Kolhar-Loni NH | PRIYANKA RAJESH KATKAR | Shirdi RSA | 2011 | 9881882149 | D1 | B | RO | RO B Site | R/2023/IN002943/MAH/000311/3203/00091 | 2023-24 | 2024-01-16 | 870 | 2-3Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | LOI needs to be cancelled | 2028-09-01 | Yes | No | Non interested candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | OBC
105 | Within 2 Km from Mahatma Phule Signal chowk,Mundhwa on Manjari Road(WITHIN PUNE MUNCIPAL LIMITS) | SWARAJ MILIND KODRE | Pune Hadapsar RSA | 2075 | 9922065544 | A | B | RO | RO B Site | R/2023/IN002978/MAH/000316/3203/00095 | 2023-24 | 2024-01-16 | 870 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 120 | 80 | 200 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate is not responding | 2028-09-01 |  | No |  | Yes: No; Yes: Yes; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
110 | From Village Pargaon Shingave to Village Manjarwadi on LHS on SH | YOGESH BALASAHEB WAGH | Pune Wagholi RSA | 1787 | 9665261714 | D2 | B | RO | RO B Site | R/2023/IN003096/MAH/000339/3203/00099 | 2023-24 | 2024-01-18 | 868 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 75 | 105 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes | Draft |  |  | Candidate not responding | 2028-09-01 | Yes | No | Candidate not responding,Mauzni is not submitted by candidate till now | Yes: by 25.05.2026; NA: Yet to Apply; NA: Yet to Assign; NA: Yet to Apply; Yes: Yes; #N/A: Received; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
111 | Shahid Ashok Kamte Smart Park to Pimple Nilakh Water Tank | SACHIN SURESHRAO TAKALE | Pimpri Chinchwad RSA | 1704 | 9923235254 | A | A | RO | RO A Site | R/2023/IN003111/MAH/000341/3203/00100 | 2023-24 | 2024-01-18 | 868 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 120 | 40 | 160 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available due to dispute among owners | 2028-09-01 |  | No | There is land reservation on land by PCMC | Yes: No; NA: Not Required; Yes: Yes; #N/A: Received | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
112 | From Bhakti Shakti Flyover Chowk to Mukai Chowk RHS | CHIRAG RAMAKANT PAWAR | Pimpri Chinchwad RSA | 1662 | 9167860603 | A | A | RO | RO A Site | R/2023/IN003091/MAH/000337/3203/00097 | 2023-24 | 2024-01-18 | 868 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 125 | 75 | 200 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Yes | Pending |  | 2028-06-01 | [5 empty] | Land Not Available | 2028-09-01 |  | No | PCMC plan yet to be passed, land issue | Yes: No; NA: Not Required; NA: Received; Yes: Yes; #N/A: Received | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
113 | From KM stone 11 to 13 on LHS on SH (Shirur-Satara Road ) | ATUL TANAJI BENDRE | Pune Wagholi RSA | 1768 | 9823646554 | D2 | B | RO | RO B Site | R/2023/IN003149/MAH/000344/3203/00102 | 2023-24 | 2024-01-19 | 867 | 2-3Y | PUNE | OPEN | Group 2: Firm Offer | 27 | 90 | 117 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available with candidate | 2028-09-01 | Yes | No | Landowner is not agreeing now and Land may be cahnged after statutory rejection. PWD issue | Yes: by 25.05.2026; NA: Not Required; Yes: Yes; #N/A: Received; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
117 | From Kondhapuri to Karegaon on RHS on NH (Pune-Ahmednagar road) | SANJAY SHIVAJI SHELKE | Pune Wagholi RSA | 1671 | 9850804702 | D1 | B | RO | RO B Site | R/2023/IN003261/MAH/000356/3203/00104 | 2023-24 | 2024-01-23 | 863 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 40 | 140 | 180 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | There is criminal case against candfidate hence he is unable to get Police NOC | 2028-09-01 | yes | No | There is criminal case against candfidate hence he is unable to get Police NOC,residence visit required by 30.05.2026 | Yes: by 30.05.2026; NA: Yes; NA: 45992; NA: Received; NA: 2025-12-01; Yes: Yes; #N/A: Received; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
116 | From Dalaj Phata to Loni Deokar on LHS of Pune- Solapur NH | ARTI HEMANT BEDRE | Pune Saswad RSA | 1697 | 9325605050 | D1 | B | RO | RO B Site | R/2023/IN003328/MAH/000370/3203/00113 | 2023-24 | 2024-01-23 | 863 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 136 | 166 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land issue, on Paper and Physical land Mismatch in 7/12 | 2028-09-01 | Yes | No | financially weak LOI holder. Land issue | No | Yes | Applied | Applied | Applied | Yet to Apply | Applied | Applied | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
118 | From Bhakti Shakti Flyover Chowk to Mukai Chowk LHS | DEEPAK ATMARAM DERE | Pimpri Chinchwad RSA | 1660 | 9823577177 | A | A | RO | RO A Site | R/2023/IN003305/MAH/000364/3203/00111 | 2023-24 | 2024-01-23 | 863 | 2-3Y | PUNE | OPEN | Group 2: Firm Offer | 150 | 50 | 200 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | NOC rejected by DM/NH/PWD |  | Yes | Pending |  | 2028-06-01 | [5 empty] | Land Not Available | 2028-09-01 |  | No | land yet to be transferred in LOI holder name, all NOC pending- regtd lease deed to be done | Yes: No; NA: Not Required; NA: Received; Yes: Yes; #N/A: #N/A | [8 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'24 | Open
125 | From Khadi Machine Chowk to Undri Chowk | VISHAL ARUN KAD | Pune City RSA | 1609 | 9850623755 | A | A | RO | RO A Site | R/2023/IN003674/MAH/000406/3203/00126 | 2023-24 | 2024-02-01 | 854 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 200 | 80 | 280 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land issue |  | Yes | Pending | NO | 2028-06-01 | [5 empty] | Land under litigation | 2028-09-01 | YES | NO | Control line issue, zoning pending | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | [11 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | Open
127 | From Datta Chowk Karad to Rajmachi on Karad Vita Road | RAJU SAHEBKHAN TADAVI | Satara West RSA | 1594 | 9422051546 | D1 | A | RO | RO A Site-Corpu | R/2023/IN004181/MAH/000459/3203/00138 | 2023-24 | 2024-02-13 | 842 | 2-3Y | SATARA | ST | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | 2028-09-01 | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Yes | Yes |  | 2028-06-01 | Yes | Yes | Pending |  |  | NH elevated road passing in front of RO, NOC not possible | 2028-09-01 | YES | NO | Site cannot get NH NOC due to bridge | Candidate to produce NOC rejection letter so as to explore alternate site option | Yes | Received | Applied | Applied | Yet to Apply | Received | NA | NA | NA | Received | NO | NA | NA | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | st
128 | Within 2 Km from Talathi Office,Wagholi on Baif Road towards Domkhel Wasti under PMC Limits | PRANAV DEEPAK DHAVALE | Pune City RSA | 1685 | 9021662667 | A | A | RO | RO A Site | R/2023/IN004175/MAH/000457/3203/00136 | 2023-24 | 2024-02-13 | 842 | 2-3Y | PUNE | OBC | Group 1: Owned land | 110 | 45 | 155 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  | NO | 2028-06-01 | [5 empty] | Candidate not responding | 2028-09-01 | NO | NO | LOI not yet received by LOI holder, HPC LOI taken | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | [11 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | OBC
129 | From Somatane Phata to Dehu Road police station on LHS of NH(Pune-Bangalore Highway) | AKSHAY MACHHINDRA MURHE | Pune Tathawade RSA | 1833 | 8275417502 | D1 | B | RO | RO B Site | R/2023/IN004185/MAH/000460/3203/00139 | 2023-24 | 2024-02-13 | 842 | 2-3Y | PUNE | OBC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC, Proposed land has Hotel | 2028-09-01 | Yes | No | The land is not available and Candidate is not interested | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | OBC
130 | From KM stone 133 to 131 on RHS of Surur-Wai Road | MANGESH SADHU JAGTAP | Satara West RSA | 1948 | 9022917388 | D2 | A | RO | RO A Site | R/2023/IN004173/MAH/000456/3203/00135 | 2023-24 | 2024-02-13 | 842 | 2-3Y | SATARA | OBC | Group 1: Owned land | 50 | 150 | 200 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | No |  |  | 2028-06-01 | [5 empty] | Candidate not responding | 2028-09-01 | Cannot be ascertained as candidate is not traceable | NO | Unresponsive candidate not traceable. called on registered mobile number on 20.04.2026 but receiver told he does not know anyone named mangesh | To be recommended for cancellation after physically reaching to the candidate | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Drawing available | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | OBC
134 | From Saswad to Yewalewadi on Yewelawadi-Bopdev- Saswad Road | Bhushan Dattatray Shendkar | Pune Saswad RSA | 1684 | 8369774966 | D2 | A | RO | RO A Site | R/2023/IN004350/MAH/000471/3203/00147 | 2023-24 | 2024-02-16 | 839 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 30 | 90 | 120 |  | No | Non-Commissionable | Yes | Yet to Initiate |  |  |  | 2026-09-01 | 2028-09-01 | Non-Commissionable |  |  | Yes | Yes |  | 2026-09-01 | Yes | Yes | Approved | Yes | 4338614 | Candidate is not responding | 2028-09-01 | Yes | Yes but in next FY | Slow Candidate | NA | Yes | Yes | Applied | Applied | Applied | Applied | Applied | NA | NA | Received | WIP | 2028-06-01 | 2028-07-01 | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | Open
133 | From KM STONE 757 TO 755 ON RHS of Pune to Satara Road | YASHORDHAN SADASHIV SHINDE | Satara West RSA | 1973 | 9881321999 | D1 | B | RO | RO B Site | R/2023/IN004340/MAH/000467/3203/00143 | 2023-24 | 2024-02-16 | 839 | 2-3Y | SATARA | OPEN | Group 1: Owned land | 40 | 150 | 190 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land issue |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes | Draft |  |  | Land is not available due to dispute from landowner | 2028-09-01 | YES | NO | CANDIDATE IS HAVING TOO MANY LOIs, land yet to be transferred to LOI holder name. Internat dispute of landowners | MOM drawn and time given till 31.07.2026. To be recommended for cancellation afer July 2026. | YES | Received | Applied | Applied | Yet to Apply | Received | NA | NA | NA | Yet to Assign | No | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | Open
135 | From Tehsildar Office Karad to Village Shere on Karad Tasgaon Road | MANGESH RAJENDRA SHINDE | Satara West RSA | 1953 | 8080371009 | D1 | B | RO | RO B Site | R/2023/IN004346/MAH/000468/3203/00144 | 2023-24 | 2024-02-16 | 839 | 2-3Y | SATARA | OPEN | Group 2: Firm Offer | 30 | 130 | 160 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available with candidate | 2028-09-01 | Cannot be ascertained as candidate is not traceable | NO | Unresponsive candidate. mangesh is relative of contact person as per application. Mangesh not lifted on 12.02.2026 and 12.03.2026.Always another person on registered number lift who claims he is not mangesh. He has provided another number over which mangesh does not lift as on 20.04.2026 | To be recommended for cancellation after physically reaching to the candidate | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'24 | Open
147 | From Lonikand to Koregaonbhima on LHS on NH (PUNE-AHMEDNAGAR ROAD) | ATUL DNYANESHWAR KATKE | Pune Wagholi RSA | 1625 | 9657234343 | D1 | A | RO | RO A Site-Corpu | R/2023/IN006244/MAH/000585/3203/00172 | 2023-24 | 2024-03-15 | 811 | 2-3Y | PUNE | SC | Group 2: Firm Offer | 50 | 101 | 151 |  | No | Non-Commissionable | 2028-09-01 | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Yes | Pending |  | 2028-06-01 |  | Pending |  |  |  | Land revised Mojini is done due to road widening hence LSR is required again and Negotiation to be done. | 2028-09-01 | yes | No | Land issue ,Meeting is scheduled on 24.05.2026 | NA: Yes; NA: 45962; NA: 45962; NA: 2025-11-01; Yes: Yes; #N/A: Received | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | SC
148 | On RHS, From Bhagwatipur to Loni on Kolhar-Loni NH | AMOL AMBADAS THETE | Shirdi RSA | 1588 | 9763481411 | D1 | B | RO | RO B Site | R/2023/IN006026/MAH/000567/3203/00163 | 2023-24 | 2024-03-15 | 811 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | Yes but in next FY | Slow Candidate | NA | Yes | Recieved | Applied | Applied | Applied | Recived | NA | Applied | Applied | Yet to Assign | No | 2027-02-28 | 2028-04-30 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
143 | From Hiwarwadi to Vadjal on Mayani Mhaswad Road | VIJAYA SUNIL WAGH | Satara East RSA | 1614 | 7057052340 | D2 | B | RO | RO B Site | R/2023/IN006013/MAH/000564/3203/00161 | 2023-24 | 2024-03-15 | 811 | 2-3Y | SATARA | CC-1 DEFENCE | Group 1: Owned land | 20 | 80 | 100 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate stopped responding | 2028-09-01 | Yes | No | Candidate stopped responding | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
144 | Within 2 Km from Khed Bus Stand towards Rashin on Bhigwan-Rashin SH | KAILAS ANKUSH MORE | Ahmednagar West RSA | 1778 | 9890915500 | D2 | B | RO | RO B Site | R/2023/IN006006/MAH/000562/3203/00160 | 2023-24 | 2024-03-15 | 811 | 2-3Y | AHMADNAGAR | OPEN | Group 1: Owned land | 20 | 90 | 110 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes | Draft |  |  | MORTH NOC issue, HPC RO on opposite side | 2028-09-01 | Yes | No | Due to issue as HPC RO on opposite site. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
145 | Within 5 KM from Mahaveer Chowk Phaltan Towards Satara on Phaltan Satara Road | AJAY ARUN BHOITE | Satara East RSA | 1960 | 9960008377 | D2 | B | RO | RO B Site | R/2023/IN006056/MAH/000570/3203/00165 | 2023-24 | 2024-03-15 | 811 | 2-3Y | SATARA | OPEN | Group 1: Owned land | 30 | 130 | 160 |  | No | Non-Commissionable | Yes |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | NOC rejected by DM/NH/PWD |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes | Approved | Yes | 4337314 | PWD Pending, complaint registered for location and same is closed,Need further clearance form PWD, SDO, TP. Site is 30x30 and PDW is asking plot size 35x35. LOI can be cancelled. NOC is denied by Collector | 2028-09-01 | Yes | No | PWD Pending, complaint registered for location and same is closed,Need further clearance form PWD, SDO, TP. Site is 30x30 and PDW is asking plot size 35x35. LOI can be cancelled. NOC is denied by Collector | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
146 | From Laxmi Chowk to the Main Gate of Kolte Patil Life Republic on Marunji - Kasarsai Road | RUTUJA MILIND KAMBLE | Pune City RSA | 1586 | 9322269661 | D2 | B | RO | RO B Site | R/2023/IN006187/MAH/000575/3203/00167 | 2023-24 | 2024-03-15 | 811 | 2-3Y | PUNE | OPEN | Group 2: Firm Offer | 100 | 80 | 180 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes | Draft |  |  | Candidate not responding | 2028-09-01 | YES | NO | Land Not finalized | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
151 | From Pusegaon Bus Stand To Khatav on Pusegaon Vaduj Road | MANOJ DILIP GHANVAT | Satara East RSA | 1577 | 8277181818 | D2 | B | RO | RO B Site | R/2023/IN005950/MAH/000553/3203/00155 | 2023-24 | 2024-03-15 | 811 | 2-3Y | SATARA | PHP ( OBC ) | Group 2: Firm Offer | 20 | 80 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate has not collected LOI despite several reminders | 2028-09-01 | No | No | Candidate has not collected LOI despite several reminders | Yes | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | OBC
142 | From Talegaon Dhamdere to Parodi on NH (Shikrapur-Nhavare Road) | BHARAT VISHNU GHOLAP | Pune Wagholi RSA | 1886 | 8600019603 | D1 | B | RO | RO B Site | R/2023/IN006195/MAH/000577/3203/00168 | 2023-24 | 2024-03-15 | 811 | 2-3Y | PUNE | OPEN | Group 1: Owned land | 55 | 100 | 155 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes | Draft |  |  | Land was changed however again NH is denying NOC on land | 2028-09-01 | Yes | Yes | Alternate land offer given by candidate ,LEC is pending |  | No | no | Yet to applied | Yet to applied | Yet to Apply | Yet to applied | Yet to applied |  |  | Yet to assign | no | 2027-03-27 | Yet to Apply | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
152 | From Baner Road Bridge on Pune Satara Highway to Mahalunge - Mann Hi Tech City Circle on Mahalunge - Nande Road within PMC Limits | SHRUTI SHASHANK BAIS | Pune City RSA | 2010 | 9975095747 | A | B | RO | RO B Site | R/2023/IN006309/MAH/000591/3203/00173 | 2023-24 | 2024-03-16 | 810 | 2-3Y | PUNE | OPEN | Group 2: Firm Offer | 200 | 80 | 280 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 | YES | NO | Land not finalised / leased | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | Open
153 | From KM stone 764 to 762 on LHS of Pune To Satara NH | YASHODHAN SADASHIV SHINDE | Satara West RSA | 1640 | 9881321999 | D1 | B | RO | RO B Site | R/2023/IN006320/MAH/000592/3203/00174 | 2023-24 | 2024-03-16 | 810 | 2-3Y | SATARA | OBC | Group 1: Owned land | 50 | 150 | 200 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | YES | NO | Unresponsive candidate having so many LOIs. Layout not yet prepared. Moujini not submitted | Candidate has been given time till 31.05.2026 to apply all NOCs post which it shall be recommended for further action | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Mar'24 | OBC
159 | Within 2 Km from Karpadi Phata towards Rasin on Bhigwan-Amrapur SH | JYOTI HAUSRAO WAGH | Ahmednagar West RSA | 1732 | 9561766650 | D2 | A | RO | RO A Site-Corpu | R/2024/IN002149/MAH/000136/3203/00008 | 2023-24 | 2024-06-13 | 721 | 1-2Y | AHMADNAGAR | ST | Group 1: Owned land | 20 | 95 | 115 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | candidate not responding | 2028-09-01 | Yes | No | Disinterested LOI candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | [11 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | st
160 | Within 5 Km from Tasawde Toll plaza towards Karad On LHS of Pune to Satara NH | NIRANJAN SATISH SALUNKHE | Satara West RSA | 1583 | 9284615858 | D1 | B | RO | RO B Site | R/2024/IN002137/MAH/000129/3203/00006 | 2023-24 | 2024-06-13 | 721 | 1-2Y | SATARA | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | NO | NO | OMC LOI in hand at nearby Plot. As per candidate, site has lost its viablity due to overbridge | Canddiate has been approached multiple times to be present at satara meets but did not turn up. LOI to be recommended for cancellation post physically reaching the candidate by 31.05.2026 | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
167 | From Village Kendur to Village Choufulla on MDR (Choufulla-Pabal road) | VAISHALI TUKARAM TATHE | Pune Wagholi RSA | 2098 | 9922175403 | E | B | KSK | KSK-B w/o Reco | R/2024/IN002250/MAH/000180/3203/00015 | 2023-24 | 2024-06-15 | 719 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 25 | 75 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | candidate not responding | 2028-09-01 | Yes | Yes but in Next FY | Mouzini not yet provided |  | No | applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | NA | NA | Yet to assign | NO | 2027-06-06 | 2027-07-07 | Yes | Recieved | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
170 | From KM stone 770 to 768 on LHS of Pune To Satara NH | PRAVIN BHAGWAN BULUNGE | Satara West RSA | 1644 | 9145578555 | D1 | B | RO | RO B Site | R/2024/IN002265/MAH/000188/3203/00023 | 2023-24 | 2024-06-15 | 719 | 1-2Y | SATARA | OBC | Group 1: Owned land | 90 | 110 | 200 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | NO | NO | Unresponsive candidate having so many LOIs.LOI not yet collected Layout not yet prepared. Moujini not submitted | Candidate has been given time till 31.05.2026 to apply all NOCs post which it shall be recommended for further action | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
166 | Moshi Toll to Chakan Chowk on LHS of Pune Nashik Highway | SHIVAJI S SONAWANE | Pimpri Chinchwad RSA | 1578 | 9881211227 | D1 | A | RO | RO A Site | R/2024/IN002257/MAH/000182/3203/00017 | 2023-24 | 2024-06-15 | 719 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 90 | 150 | 240 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Land is not available | 2028-09-01 |  | No | Land dispute | Yes: No; NA: 0; Yes: Yes; #N/A: Received | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
171 | Within 2 km from Nevasa Phata towards Ahmednagar on Pune-Aurangabad NH | PRAMOD KAKASAHEB SHINDE | Ahmednagar EASt RSA | 1659 | 7038689909 | D1 | B | RO | RO B Site | R/2024/IN002262/MAH/000186/3203/00021 | 2023-24 | 2024-06-15 | 719 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 62 | 110 | 172 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate denied due to large investment. Written confirmation to be collected by FO | 2028-09-01 | Yes | NO | LOI holder not responding- not collected LOI - to be cancelled | NA: NA; Yes: Moujani Awaited; #N/A: Yet to Apply; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
180 | On LHS of Pune-Solapur NH, From Vangali to inter-section of Indapur Bypaas & Akluj Highway | GUNAVANT BALIRAM BANSODE | Pune Saswad RSA | 1656 | 8239301003 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002391/MAH/000206/3203/00037 | 2023-24 | 2024-06-17 | 717 | 1-2Y | PUNE | SC | Group 1: Owned land | 35 | 150 | 185 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Candidate not responding | 2028-09-01 | No | Yes but in next FY | Financially weak, slow candidate | No | No | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | SC
175 | From Shitpur Phata to Nimbodi Phata on Shrigonda-Jamkhed NH | MOSIM DAUT SHAIKH | Ahmednagar West RSA | 1746 | 9579167940 | D1 | B | RO | RO B Site | R/2024/IN002363/MAH/000193/3203/00028 | 2023-24 | 2024-06-17 | 717 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 50 | 100 | 150 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2028-09-01 | Yes | No | Multiple LOI in same stretch, one LOI commissioned soon. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
179 | From Bandalwadi to Kanheri on State highway (Indapur Road) | BARAMATI AGRO LIMITED | Pune Tathawade RSA | 1760 | 9922414791 | D2 | B | RO | RO B Site | R/2024/IN002406/MAH/000210/3203/00041 | 2023-24 | 2024-06-17 | 717 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 35 | 90 | 125 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Title of Land is not Clear |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Heavy charge on Land, Site May not be commissioned | 2028-09-01 | Yes | Yes | There is charge of 200 cr on the land , the management of Barmati Agros is willing to commission the RO based if permission of self installed CBG is provided . The proposal received from the candidate is sent to HO for review. Only PWD NOC is pending | No | Yes | Received | Received | Yes | Applied | Received | Received | NA | NA | Received | Yes | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
181 | Within 5 Kms from Wagholi towards lohegaon on Wagholi -Lohegaon Road | PRATHAMESH VINAYAK JAWARE | Pune City RSA | 1630 | 7607760712 | A | A | RO | RO A Site-Corpu | R/2024/IN002380/MAH/000203/3203/00034 | 2023-24 | 2024-06-17 | 717 | 1-2Y | PUNE | SC | Group 1: Owned land | 160 | 100 | 260 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  | NO | 2028-06-01 | [5 empty] | Land under litigation | 2028-09-01 | YES | NO | Not responding | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | SC
182 | From Zilla Parishad School Waghmode Wadi towards Deulgaon Siddhi on Deulgaon Siddhi-Baburdi Bend road | DNYANESHWAR KISAN FOLE | Ahmednagar West RSA | 2094 | 9561955578 | E | A | KSK | KSK-A w/o Reco | R/2024/IN002383/MAH/000205/3203/00036 | 2023-24 | 2024-06-17 | 717 | 1-2Y | AHMADNAGAR | ST | Group 1: Owned land | 20 | 32 | 52 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | No Progress in NOC | 2028-09-01 | Yes | No | Non-responding candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | Land dispute for drawing preparation | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | st
183 | Within 2 km From Jawala Bus Stand towards Jamkhed on Jamkhed-Karmala Road | RAVINDRA MAHADEV KOLHE | Ahmednagar West RSA | 1703 | 7218716824 | D2 | B | RO | RO B Site | R/2024/IN002369/MAH/000199/3203/00032 | 2023-24 | 2024-06-17 | 717 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Due to PWD accress permission issue. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | No |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
184 | On LHS From Venavadi to Ambeghar on National Highway (Bhor-Shirwal Road) | SAGAR SIDHU DEVKATE | Pune Tathawade RSA | 1740 | 9921918171 | D1 | B | RO | RO B Site | R/2024/IN002361/MAH/000191/3203/00026 | 2023-24 | 2024-06-17 | 717 | 1-2Y | PUNE | OBC | Group 1: Owned land | 60 | 100 | 160 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Candidate has been counselled again on 30.04.2026. He has requested for 1 month. | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
187 | From Miri to Maka on Vambori-Shevgaon SH | SUBHASH EKNATH NAWALE | Ahmednagar EASt RSA | 1924 | 8378837080 | D2 | B | RO | RO B Site | R/2024/IN002434/MAH/000216/3203/00045 | 2023-24 | 2024-06-18 | 716 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 35 | 90 | 125 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | No Progress by Candidate |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate has been very slow in NOC process | 2028-09-01 | Yes | NO | Final NA pending, TP | NA: Yes; NA: 45962; NA: NA; NA: 45962; NA: 2025-11-01; Yes: Yes; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
186 | Within 5 KMs from Arogyavardhani Kendra , Male on Mulshi Road towards Pirangut on National Highway | YOGESH LAXMAN THOMBARE | Pune City RSA | 1921 | 9822542525 | D1 | B | RO | RO B Site | R/2024/IN002464/MAH/000229/3203/00058 | 2023-24 | 2024-06-18 | 716 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 50 | 110 | 160 |  | No | Non-Commissionable | 2028-09-01 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Candidate not responding | 2028-09-01 | YES | NO | Slow candidate | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
189 | From Mhaswad To Dhuldev on Satara Pandharpur Road | HANMANT GANPATI PAWAR | Satara East RSA | 1603 | 7507330220 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002437/MAH/000218/3203/00047 | 2023-24 | 2024-06-18 | 716 | 1-2Y | SATARA | SC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | No Progress in NOC | 2028-09-01 | Yes | No | No Progress in NOC | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | No | NA | NA | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | SC
| From V-Trans (India) Limited to Narvir Tanaji Malusare Chowk, Village Vanjarvadi, Baramati | SUNNY BABASAHEB GALINDE | Pune Tathawade RSA | 1816 | 9021069420 | D1 | A | RO | RO A Site-Corpu | R/2024/IN002431/MAH/000213/3203/00042 | 2023-24 | 2024-06-18 | 716 | 1-2Y | PUNE | SC | Group 1: Owned land | 40 | 180 | 220 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Candidate not responding | 2028-09-01 | No | No | LOI not collected by the candidate yet | Yes | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | Yet to apply | NA | NA | Yet to Assign | WIP | NA | NA | Yes | #N/A | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | SC
192 | Within 5 KM from Hotel Jakson Inn Nimbhore towards Phaltan on Lonand Phaltan Road | LAKHAN SAVALARAM BARKADE | Satara East RSA | 1898 | 7020096202 | D1 | B | RO | RO B Site | R/2024/IN002452/MAH/000225/3203/00054 | 2023-24 | 2024-06-18 | 716 | 1-2Y | SATARA | OPEN | Group 1: Owned land | 40 | 110 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | No Progress in NOC | [18 empty] | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open | bar: Yes to NA; NA to NA
193 | From Village Atit To Kashil On RHS of Satara- Karad NH | TUSHAR VISHWANATH BHISE | Satara West RSA | 1903 | 9881513221 | D1 | B | RO | RO B Site | R/2024/IN002451/MAH/000224/3203/00053 | 2023-24 | 2024-06-18 | 716 | 1-2Y | SATARA | OBC | Group 2: Firm Offer | 57 | 100 | 157 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Cancellation Approved | 2028-09-01 | NO | NO | Land not available. financially weak candidate | Recommended for cancellation in Apr 2026 | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
191 | From Mindewadi Chowk to Navlakh Umbre Chowk | PRATAP BABUSHA JADHAV | Pimpri Chinchwad RSA | 2057 | 9545822822 | C | B | RO | RO B Site | R/2024/IN002476/MAH/000231/3203/00060 | 2023-24 | 2024-06-18 | 716 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 40 | 110 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land issue as conversion charges are very high and candidate not showing interested | 2028-09-01 |  | No | Slow candidate, non responsive | Yes: No; NA: Not Required; Yes: Yes; #N/A: #N/A; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
199 | Within 2 km From Navle Bridge Bus Stop towards Wadgaon bridge on LHS | YASHODHAN SADASHIV SHINDE | Pune City RSA | 1629 | 9881321999 | A | B | RO | RO B Site | R/2024/IN002494/MAH/000240/3203/00069 | 2023-24 | 2024-06-19 | 715 | 1-2Y | PUNE | OBC | Group 1: Owned land | 250 | 100 | 350 |  | No | Non-Commissionable | 2028-06-03 |  |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required | NO | 2028-06-01 | Yes | Yes |  |  |  | Cancellation Approved | 2028-09-01 | YES | NO | SLOW CANDIDATE | YES | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | OBC
205 | On LHS, From Junction to Bawada via Walchandnagar-Nimsakhar-Redani on SH | ABHISHEK SURESH NIDBANE | Pune Saswad RSA | 1683 | 8329641001 | D2 | A | RO | RO A Site-Corpu | R/2024/IN002514/MAH/000252/3203/00076 | 2023-24 | 2024-06-20 | 714 | 1-2Y | PUNE | ST | Group 1: Owned land | 20 | 83 | 103 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Alternate land offer is given, however the candidate is unable to arrange the land | 2028-09-01 | Yes | No | Dispute b/w land owner and LOI holder | No | No | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | Yes | Received | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | st
204 | Triveni Hospital Chowk to Ravet Police Station ( Walhekarwadi Road) | SANDESH PRALHAD SONAWANE | Pimpri Chinchwad RSA | 1639 | 7020939868 | A | A | RO | RO A Site-Corpu | R/2024/IN002519/MAH/000254/3203/00077 | 2023-24 | 2024-06-20 | 714 | 1-2Y | PUNE | SC | Group 2: Firm Offer | 130 | 70 | 200 |  | No | Non-Commissionable | 2028-06-03 | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | LSR awaited, Negotiation pending. Land is showing less in 7/12. 7/12 needs updation. | 2028-09-01 |  | No | Land issue | Yes: No; NA: Not Required; Yes: Yes; #N/A: Received | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | SC
207 | From Village Ravadewadi to Village Pargaon Shingave on LHS on LHS on SH | BHARATA PARAJI DHOBALE | Pune Wagholi RSA | 1991 | 9834737806 | D2 | B | RO | RO B Site | R/2024/IN002550/MAH/000260/3203/00080 | 2023-24 | 2024-06-21 | 713 | 1-2Y | PUNE | CC-1 DEFENCE | Group 2: Firm Offer | 30 | 70 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available with candidate | 2028-09-01 | No | No | Dispute b/w land owner and LOI | Yes: by 25.05.2026; NA: Not Required; Yes: Moujani Awaited; #N/A: Yet to Apply; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jun'24 | Open
213 | From Puntamba Phata to Zagde Phata on Sangamner-Kopargaon NH | MANISHA RAMNATH KANDALKAR | Shirdi RSA | 2018 | 9822773671 | D1 | B | RO | RO B Site | R/2024/IN002778/MAH/000307/3203/00091 | 2023-24 | 2024-07-06 | 698 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 40 | 110 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | There is NH intersection within 300 Mt. | 2028-09-01 | Yes | Yes but in next FY | Slow Candidate and there is NH intersection issue. | NA | Yes | Recieved | Applied | Recieved | Yet to Apply | Applied | NA | Applied | Applied | Yet to Assign | No | 2027-11-30 | 2028-02-29 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | OBC
211 | Within 4 Km from Krantisury Mahatma Phule Chowk (Rashin) towards Bhigwan on Bhigwan-Rashin SH | MIRAJGAON MULTIPURPOSE CO OP S | Ahmednagar West RSA | 2050 | 9767222999 | D2 | B | RO | RO B Site | R/2024/IN002777/MAH/000306/3203/00090 | 2023-24 | 2024-07-06 | 698 | 1-2Y | AHMADNAGAR | CC-2 PACS | Group 2: Firm Offer | 30 | 70 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Very Slow Candidate | 2028-09-01 | Yes | No | Land yet to decide by society as applied under Group 2 beside not responding. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | Open
212 | Within 2 km from Entry Junction of Village Ghugalwadgaon towards Mandavganon Shrigonda-Mandavgaon road | VIKAS BARKU GONDHALI | Ahmednagar West RSA | 2115 | 8055750844 | E | B | KSK | KSK-B w/o Reco | R/2024/IN002770/MAH/000299/3203/00086 | 2023-24 | 2024-07-06 | 698 | 1-2Y | AHMADNAGAR | OBC | Group 1: Owned land | 20 | 55 | 75 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land is not available | 2028-09-01 | Yes | No | Alternate land requested and offered but not available in same stretch due to forest NOC issue. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | Received | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | OBC
215 | From Dalaj Phata to Junction on Dalaj -Walchandnagar SH | DATTATRAY APPAJI KAMBLE | Pune Saswad RSA | 1719 | 9420916471 | D2 | A | RO | RO A Site-Corpu | R/2024/IN002844/MAH/000323/3203/00095 | 2023-24 | 2024-07-10 | 694 | 1-2Y | PUNE | SC | Group 1: Owned land | 20 | 96 | 116 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Candidate Not Responding | 2028-09-01 | Yes | No | Dispute b/w land owner and LOI holder | No | Yes | Applied | Applied | Applied | Applied | Applied | Applied | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | No | Site visit done. Maujni Not available | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | SC
216 | Within 10 Km from Nira on RHS of Shirur-Satara Road towards Morgaon | ATUL KALYANRAO KAKADE | Pune Wagholi RSA | 1747 | 7083272929 | D1 | B | RO | RO B Site | R/2024/IN002846/MAH/000324/3203/00096 | 2023-24 | 2024-07-10 | 694 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate Not Responding | 2028-09-01 |  | No | Financial issue of dealer | Yes: No; Yes: Moujani Awaited; #N/A: Yet to Apply; NA: NA; NA: NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'24 | Open
219 | ON SHEVGAON TO GEORAI ROADWITHIN 5 KM FROM NITYA SEVA HOSPITAL TOWARDS GEORA | DIPAK ASHOK KALE | Ahmednagar EASt RSA |  | 9423126607 | D2 | A | RO | RO A Site-Corpu | M/2024/IN003545/MAH/000390/3203/00106 | 2018-19 | 2024-09-12 | 630 | 1-2Y | AHMADNAGAR | ST | Group 2: Firm Offer | 20 | 80 | 100 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | No Progress by Candidate |  |  |  |  | 2028-06-01 | [5 empty] | No Progress by Candidate. Mojani is pending | 2028-09-01 | Yes | NO | Land change required | NA: NA; Yes: Yes | [8 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Sep'24 | st
222 | AT JEJURI ON LHS OFJEJURI-NIRA NH | Radhika Harish Sonawane | Pune Saswad RSA |  |  | D1 | B | RO | RO B Site | M/2024/IN003774/MAH/000408/3203/00109 | 2018-19 | 2024-10-08 | 604 | 1-2Y | PUNE | OPEN | Group 1: Owned land | 30 | 125 | 155 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Land issue, Candidate not responding | 2028-09-01 | Yes | No | SLOW CANDIDATE | No | Yes | Applied | Applied | Applied | Applied | Applied | Applied | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | Yes |  | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2018-19 | Yes | [5 empty] | Oct'24 | Open
221 | From Aundh To Rahimatpur (On SH) on Satara Rahimatpur Road | ASHOK GOVIND NIRGUDA | Satara East RSA | 101 | 9834714125/7039891038 | D2 | A | RO | RO A Site-Corpu | R/2024/IN003781/MAH/000409/3203/00110 | 2023-24 | 2024-10-08 | 604 | 1-2Y | SATARA | ST | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | NA | NA | Ellen and Gosavi |  |  | 2028-06-01 | [5 empty] | NOC rejected, Alternate land offer in Progress | 2028-09-01 | Yes | Yes but in next FY | NOC rejected, Alternate land offer in Progress-LEC yet to be done |  | No | Yet to applied | Yet to applied | Yet to applied | Yet to applied | Yet to applied | NA | NA | NA | Yet to Assign | No | NA | NA | Yes | Received |  | Pending | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Oct'24 | st
224 | From Wathar to Deur on Satara Lonand Road | VISHAL DATTATRAYA TIRMAKE | Satara East RSA | 2025 | 9595033304 | D1 | A | RO | RO A Site-Corpu | R/2024/IN003799/MAH/000414/3203/00113 | 2023-24 | 2024-10-10 | 602 | 1-2Y | SATARA | SC | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | [5 empty] | 2028-06-01 | [5 empty] | Land is not abutting the road | 2028-09-01 | Yes | No | Land is not abutting the road | No | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Yes | [11 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Oct'24 | SC
226 | From Village Shiwade To Village Varade On LHS of Satara to Karad Road | SHASHIKANT RAMCHANDR DEVKAR | Satara West RSA | 2055 | 9921902612 | D1 | B | RO | RO B Site | R/2024/IN004204/MAH/000430/3203/00119 | 2023-24 | 2024-11-28 | 553 | 1-2Y | SATARA | OBC | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Financial issue with LOI holder | 2028-09-01 | NO | NO | Land not available. financially weak candidate | MOM drawn for non availability of land. Will be recommended for cancellation by 15.05.2026 | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Moujani Awaited | Yet to Apply | NA | NA | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Nov'24 | OBC
230 | Within 5km from IOCL Loni Terminal towards Solapur on Pune - Solapur NH | DEEPAK BHAGAVANT GOTE | Pune Hadapsar RSA | 1604 | 9822667378 | D1 | B | RO | RO B Site | R/2024/IN004517/MAH/000462/3203/00123 | 2023-24 | 2025-01-02 | 518 | 1-2Y | PUNE | OBC | Group 2: Firm Offer | 40 | 180 | 220 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  | Not Required | Not Required |  | 2028-06-01 | Yes | Yes |  |  |  | Candidate has no sufficient frontage | 2028-09-01 |  | No | [19 empty] | Not Required | [7 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'25 | OBC | bar: Yes; NA to NA
232 | From Shivajiraje Chowk (Jejuri) to Jejuri MIDC on RHS of Saswad-Pandarpur Road towards Nira | SAHIL DHNYNESHWAR PAWAR | Pune Saswad RSA | 1994 | 8600373330 | D1 | A | RO | RO A Site-Corpu | R/2024/IN004522/MAH/000466/3203/00127 | 2023-24 | 2025-01-03 | 517 | 1-2Y | PUNE | ST | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Land Issue, Candidate is not responding | 2028-09-01 | Yes | No | Dispute b/w land owner and LOI holder | No | Yes | Received | Applied | Applied | Applied | Applied | Applied | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | [12 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jan'25 | st
234 | Thermax Chowk to Pune Nashik Road Junction on Nigdi Bhosari Road | VISHAL DILWAR PAWARA | Pimpri Chinchwad RSA | 1896 | 9545200200 | A | A | RO | RO A Site-Corpu | R/2024/IN004769/MAH/000474/3203/00130 | 2023-24 | 2025-02-24 | 465 | 1-2Y | PUNE | ST | Group 2: Firm Offer | 150 | 50 | 200 |  | No | Non-Commissionable | 2028-06-03 | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable |  |  | Assigned to IAS and MA | Pending |  | 2028-06-01 |  | Pending |  |  |  | Commercial conversion fee is very high. Not viable for LOI holder. LOI holder is not responding now | 2028-09-01 |  | No | Hefty amount required for NA from industrial to Commercial | Yes: No; NA: Not Required; Yes: Moujani Awaited; #N/A: Yet to Apply | [8 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'25 | st
237 | From Loni Deokar to Vangali on LHS of Pune-Solapur NH towards Solapur | ONKAR SHIVAJI SHINDE | Pune Saswad RSA | 1741 | 7745061111 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000079/MAH/000009/3203/00002 | 2023-24 | 2025-04-30 | 400 | 1-2Y | Pune | SC | Group 1: Owned land | 30 | 120 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Candidate is not reposonding | 2028-09-01 | No | Yes but in next FY |  | No | No | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | Yet to Apply | NA | NA | Yet to Assign | No | 2028-06-01 | 2028-07-01 | Yes | Recieved | [10 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Apr'25 | SC
238 | From Shri Siddheshwar Vidhyalaya (Bhambora) to Mahdev Mandir on Rashin-Siddhitek SH | OMKAR AMRUT KHARADE | Ahmednagar West RSA | 1824 | 9730976692 | D2 | B | RO | RO B Site | R/2025/IN000089/MAH/000010/3203/00003 | 2023-24 | 2025-05-06 | 394 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 20 | 80 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | Yes | Yes |  |  |  | Cancellation Approved | 2028-09-01 | Yes | No | Due to junction issue. | Yes LOI cancelled. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | May'25 | Open
239 | Within 2 Km from Karjat Bus Stand towards Karmala on Karjat-Karmala SH | SHITAL NITIN KADAM | Ahmednagar West RSA | 1769 | 9890191470 | D2 | B | RO | RO B Site | R/2025/IN000090/MAH/000011/3203/00004 | 2023-24 | 2025-05-06 | 394 | 1-2Y | AHMADNAGAR | OPEN | Group 1: Owned land | 30 | 85 | 115 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | Yes | Yes |  |  |  | No Progress in NOC | 2028-09-01 | Yes | No | Disinterested LOI candidate. | Yes | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [12 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | May'25 | Open
245 | On LHS Within 5 km from Supa Toll Plaza towards Pune on Pune-Aurangabad NH | SANDIP LAXMAN ITHAPE | Ahmednagar EASt RSA | 2088 | 9325454101 | D1 | B | RO | RO B Site | R/2025/IN000255/MAH/000034/3203/00010 | 2023-24 | 2025-07-01 | 338 | 6-12M | AHMADNAGAR | OBC | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Cancellation Approved | 2028-09-01 | No | NO | LOI cancelled from MSO | [26 empty] | Cancelled |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'25 | OBC | bar: NA
247 | Village Belwandi,Taluk Shrigonda on Shrigonda Shirur Road | DHANANJAY SUDHAKAR LATE | Ahmednagar West RSA | 1951 | 9096171111 | D2 | B | RO | RO B Site | R/2025/IN000332/MAH/000050/3203/00013 | 2023-24 | 2025-07-30 | 309 | 6-12M | AHMADNAGAR | CC-2 PACS | Group 2: Firm Offer | 20 | 80 | 100 |  | No | Non-Commissionable | [5 empty] | 2028-06-01 | 2028-09-01 | Non-Commissionable | Land Not Available |  |  |  |  | 2028-06-01 | [5 empty] | Very Slow Candidate | 2028-09-01 | Yes | No | Land yet to decide by society as applied under Group 2 | [26 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Jul'25 | Open | bar: Yes to NA
249 | From Vadi To Kalambi on Rahimatpur Pusesavali Road | SUMIT SANJAY WAYADANDE | Satara East RSA | 2003 | 7744899095 | D2 | A | RO | RO A Site-Corpu | R/2025/IN000387/MAH/000055/3203/00014 | 2023-24 | 2025-08-20 | 288 | 6-12M | SATARA | SC | Group 2: Firm Offer | 30 | 70 | 100 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Very Slow Candidate. No Progress in NOC | 2028-09-01 | Yes | No | Very Slow Candidate. No Progress in NOC | [26 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Aug'25 | SC | bar: Yes to NA
250 | From Diskal To Shendgewadi on Pusegaon Phaltan Road | RANJANA BABU SABALE | Satara East RSA | 109 | 8698598404 | D2 | A | RO | RO A Site-Corpu | R/2025/IN000427/MAH/000059/3203/00015 | 2023-24 | 2025-09-02 | 275 | 6-12M | SATARA | ST | Group 2: Firm Offer | 30 | 120 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Very Slow Candidate. No Progress in NOC | 2028-09-01 | Yes | No | Very Slow Candidate. No Progress in NOC | [26 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Sep'25 | st | bar: Yes to NA
262 | Within 3 KM from Mhaswad Bus Stand Towards Dahiwadi on Mhaswad Dahiwadi Road | SHRI AMOL RUSTUMA TAPARE | Satara East RSA | 2047 | 9821646488 | D1 | A | RO | RO A Site-Corpu | R/2025/IN000823/MAH/000096/3203/00028 | 2023-24 | 2026-02-18 | 106 | 0-6M | SATARA | SC | Group 2: Firm Offer | 40 | 110 | 150 |  | No | Non-Commissionable |  | Yet to Initiate |  |  |  | 2028-06-01 | 2028-09-01 | Non-Commissionable | Disinterested LOI holder |  |  |  |  | 2028-06-01 | [5 empty] | Very Slow Candidate. No Progress in NOC | 2028-09-01 | Yes | No | Very Slow Candidate. No Progress in NOC | [26 empty] | Pending |  |  |  |  | SRMP 2023-24 | Yes | [5 empty] | Feb'26 | SC | bar: Yes to NA
Formulas:
LOI Age = +TODAY()-[LOI Date]
NOC Month = +[Expected Month of NOC]
Comm. Month = +[Expected Month of commissioning-Actual]
Expected Month of commissioning-Actual = +[Expected Month of NOC]+31

## Summary
|  | Total | [9 empty] | A | A | A | A | A | A | A | A | A | D1 | D1 | D1 | D1 | D1 | D1 | D1 | D1 | D1 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | C | C | C | C | C | C | C | C | C | E | E | E | E | E | E | E | E | E | Already Commissioned | [11 empty] | Total
|  | Commissionable in this FY |  |  | Drawing | NOC Available |  |  | IO Available |  |  | Commissionable in this FY |  |  | NOC Available |  |  | IO Available |  |  | Commissionable in this FY |  |  | NOC Available |  |  | IO Available |  |  | Commissionable in this FY |  |  | NOC Available |  |  | IO Available |  |  | Commissionable in this FY |  |  | NOC Available |  |  | IO Available |  |  | Commissionable in this FY |  |  | NOC Available |  |  | IO Available |  |  | A | A | B | B | C | C | D1 | D1 | D2 | D2 | E | E | All COM
RSA | Total | A | B | Total | A+B | A | B | Total | A | B | Total | A | B | otal | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | A | B | A | B | A | B | A | B | A | B
Ahmednagar East RSA | 22 | 4 | 4 | 8 | 7 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ahmednagar West RSA | 33 | 1 | 10 | 11 | 10 | 1 | 0 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 2 | 3 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Pune City RSA | 16 | 2 | 1 | 3 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pimpri Chinchwad RSA | 16 | 5 | 1 | 6 | 5 | 1 | 0 | 1 | 2 | 1 | 3 | 4 | 1 | 5 | 1 | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Pune Saswad RSA | 28 | 4 | 5 | 9 | 9 | 1 | 1 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 7 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2
Pune Wagholi RSA | 34 | 2 | 6 | 8 | 7 | 0 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Hadapsar RSA | 17 | 3 | 0 | 3 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Tathawade RSA | 29 | 7 | 4 | 11 | 11 | 2 | 0 | 2 | 2 | 1 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
Satara West RSA | 25 | 2 | 3 | 5 | 4 | 0 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 0 | 1 | 1 | 0 | 2 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Satara East RSA | 31 | 1 | 4 | 5 | 5 | 1 | 1 | 2 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 1 | 0 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Shirdi RSA | 16 | 4 | 2 | 6 | 4 | 0 | 0 | 0 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 267 | 35 | 40 | 75 | 66 | 7 | 4 | 11 | 11 | 15 | 26 | 6 | 2 | 8 | 1 | 0 | 1 | 2 | 1 | 3 | 18 | 21 | 39 | 2 | 1 | 3 | 5 | 10 | 15 | 8 | 9 | 17 | 3 | 1 | 4 | 2 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 11 | 1 | 2 | 3 | 2 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 8
Tally
Total
|  | Commissionable in this FY |  |  |  |  | NOC Available |  |  | IO Available
RSA | Total | A | B |  |  |  | A | B |  | A | B
Ahmednagar East RSA | 22 | 4 | 4 |  |  |  | 1 | 0 |  | 0 | 1
Ahmednagar West RSA | 33 | 1 | 10 |  |  |  | 1 | 0 |  | 0 | 4
Pune City RSA | 16 | 2 | 1 |  |  |  | 0 | 0 |  | 1 | 0
Pimpri Chinchwad RSA | 16 | 5 | 1 |  |  |  | 1 | 0 |  | 2 | 1
Pune Saswad RSA | 28 | 4 | 5 |  |  |  | 1 | 1 |  | 2 | 1
Pune Wagholi RSA | 34 | 2 | 6 |  |  |  | 0 | 1 |  | 0 | 2
Pune Hadapsar RSA | 17 | 3 | 0 |  |  |  | 0 | 0 |  | 1 | 0
Pune Tathawade RSA | 29 | 7 | 4 |  |  |  | 2 | 0 |  | 2 | 1
Satara West RSA | 25 | 2 | 3 |  |  |  | 0 | 1 |  | 0 | 2
Satara East RSA | 31 | 1 | 4 |  |  |  | 1 | 1 |  | 1 | 2
Shirdi RSA | 16 | 4 | 2 |  |  |  | 0 | 0 |  | 2 | 1
| 267 | 35 | 40 |  |  |  | 7 | 4 |  | 11 | 15
Pending LOI - Class of Market Wise-As of 01.10.25
Divisional Office | A | B | C | D1 | D2 | E | Total
Pune DO | 25 | 0 | 11 | 134 | 66 | 31 | 267
Commissionable | 9 | 0 | 1 | 68 | 26 | 15 | 119
Planned 2025-26 | 8 | 0 | 0 | 39 | 17 | 11 | 75
Aready Commissioned | 1 | 0 | 0 | 3 | 1 | 3 | 8
- Age analysis as of 01.07.25
| RO | [7 empty] | KSK | [7 empty] | Total
DO | 0-6M | 6-12M | 1-2Y | 2-3Y | 3-4Y | 4-5Y | >5Y | RO | 0-6M | 6-12M | 1-2Y | 2-3Y | 3-4Y | 4-5Y | > 5Y | KSK
Pune DO | 13 | 11 | 82 | 76 | 17 | 2 | 29 | 230 | 0 | 1 | 7 | 10 | 3 | 3 | 12 | 36 | 266
Commissionable | 11 | 7 | 45 | 32 | 5 | 0 | 4 | 104 | 0 | 1 | 4 | 8 | 0 | 1 | 1 | 15 | 119
NOC Age Analysis – As of 01.07.25
| A |  |  |  |  | B |  |  |  |  | Grand Total
Divisional Office | 0-3M | 3-6M | 6-12M | Above 1Y | Total | 0-3M | 3-6M | 6-12M | Above 1Y | Total
Pune DO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Already Commissioned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
commissionable Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-Commissionable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning | A | C | D1 | D2 | E | Total |  | LOI Generation | A | C | D1 | D2 | E | Total
LOIs as on 01.04.2026 | 25 | 11 | 134 | 66 | 31 | 267 |  | LOIs as on 01.04.2026 | 25 | 11 | 134 | 66 | 31 | 267
Pre 2018/Govt | 1 | 5 | 5 | 10 | 3 | 24 |  | Pre 2018/Govt | 1 | 5 | 5 | 10 | 3 | 24
SRMP 2018-19 | 1 | 2 | 27 | 9 | 12 | 51 |  | SRMP 2018-19 | 1 | 2 | 27 | 9 | 12 | 51
SRMP 2023-24 | 23 | 4 | 102 | 47 | 16 | 192 |  | SRMP 2023-24 | 23 | 4 | 102 | 47 | 16 | 192
Commissioning in Apr'26 | 0 | 0 | 0 | 0 | 1 | 1 |  | LOI Issued in Apr'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 1 | 1 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in May'26 | 1 | 0 | 3 | 1 | 2 | 7 |  | LOI Issued in May'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 1 | 0 | 3 | 1 | 2 | 7 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Jun'26 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Jun'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Jul'26 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Jul'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Aug'26 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Aug'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Sep'26 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Sep'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Oct'26 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Oct'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Nov'26 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Nov'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Dec'26 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Dec'26 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Jan'27 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Jan'27 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Feb'27 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Feb'27 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissioning in Mar'27 | 0 | 0 | 0 | 0 | 0 | 0 |  | LOI Issued in Mar'27 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Total Commissioned | 1 | 0 | 3 | 1 | 3 | 8 |  | Total LOI issued in FY 26-27 | 0 | 0 | 0 | 0 | 0 | 0
Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0 |  | Pre 2018/Govt | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0 |  | SRMP 2018-19 | 0 | 0 | 0 | 0 | 0 | 0
SRMP 2023-24 | 1 | 0 | 3 | 1 | 3 | 8 |  | SRMP 2023-24 | 0 | 0 | 0 | 0 | 0 | 0
Commissionable LOIs Total | 8 | 1 | 65 | 25 | 12 | 111 |  | LOI as on 01.04.2026 | 22 | 10 | 124 | 62 | 28 | 246
Pre 2018/Govt | 0 | 0 | 1 | 1 | 1 | 3 |  | Pre 2018/Govt | 1 | 5 | 5 | 9 | 3 | 23
SRMP 2018-19 | 0 | 0 | 8 | 2 | 3 | 13 |  | SRMP 2018-19 | 1 | 1 | 26 | 8 | 12 | 48
SRMP 2023-24 | 8 | 1 | 56 | 22 | 8 | 95 |  | SRMP 2023-24 | 20 | 4 | 93 | 45 | 13 | 175
Commissionable LOIs in FY 2026-27 | 7 | 0 | 36 | 16 | 8 | 67 |  | LOI cancelled in FY 2026-27 | 2 | 1 | 7 | 3 | 0 | 13
Pre 2018/Govt | 0 | 0 | 1 | 0 | 1 | 2 |  | Pre 2018/Govt | 0 | 0 | 0 | 1 | 0 | 1
SRMP 2018-19 | 0 | 0 | 5 | 1 | 0 | 6 |  | SRMP 2018-19 | 0 | 1 | 1 | 1 | 0 | 3
SRMP 2023-24 | 7 | 0 | 30 | 15 | 7 | 59 |  | SRMP 2023-24 | 2 | 0 | 6 | 1 | 0 | 9
Commissioning | A | C | D1 | D2 | E | Total |  | Commissioning | A | C | D1 | D2 | E | Total
MoU Target 2025-26 | 7 | 0 | 34 | 15 | 9 | 65 |  | MoU Target 2025-26 | 8 | 0 | 39 | 17 | 11 | 75
A Site | 6 | 0 | 16 | 7 | 1 | 30 |  | A Site | 6 | 0 | 18 | 8 | 3 | 35
B Site | 1 | 0 | 18 | 8 | 8 | 35 |  | B Site | 2 | 0 | 21 | 9 | 8 | 40
MoU Plan 2025-26 | 8 | 0 | 39 | 17 | 11 | 75 |  | MoU Plan 2025-26 | 8 | 0 | 39 | 17 | 11 | 75
A Site | 6 | 0 | 18 | 8 | 3 | 35 |  | A Site | 6 | 0 | 18 | 8 | 3 | 35
B Site | 2 | 0 | 21 | 9 | 8 | 40 |  | B Site | 2 | 0 | 21 | 9 | 8 | 40
Commissioned Apr'26-Mar'27 | 1 | 0 | 3 | 1 | 3 | 8 |  | Commissioned Apr'26-Mar'27 | 1 | 0 | 3 | 1 | 3 | 8
A Site | 1 | 0 | 1 | 1 | 1 | 4 |  | A Site | 1 | 0 | 1 | 1 | 1 | 4
B Site | 0 | 0 | 2 | 0 | 2 | 4 |  | B Site | 0 | 0 | 2 | 0 | 2 | 4
Balance Commissioning | 6 | 0 | 31 | 14 | 6 | 57 |  | Balance Commissioning | 7 | 0 | 36 | 16 | 8 | 67
A Site | 5 | 0 | 15 | 6 | 0 | 26 |  | A Site | 5 | 0 | 17 | 7 | 2 | 31
B Site | 1 | 0 | 16 | 8 | 6 | 31 |  | B Site | 2 | 0 | 19 | 9 | 6 | 36
Budgetary Estimate Approved | 3 | 0 | 21 | 10 | 6 | 40 |  | Budgetary Estimate Approved | 4 | 0 | 25 | 11 | 7 | 47
A Site | 2 | 0 | 6 | 3 | 0 | 11 |  | A Site | 2 | 0 | 7 | 3 | 1 | 13
B Site | 1 | 0 | 15 | 7 | 6 | 29 |  | B Site | 2 | 0 | 18 | 8 | 6 | 34
Legal Search Completed | 0 | 0 | 0 | 0 | 0 | 0 |  | Legal Search Completed | 6 | 0 | 18 | 8 | 2 | 34
A Site | 0 | 0 | 0 | 0 | 0 | 0 |  | A Site | 3 | 0 | 9 | 4 | 1 | 17
B Site | 0 | 0 | 0 | 0 | 0 | 0 |  | B Site | 3 | 0 | 9 | 4 | 1 | 17
IO Available | 1 | 0 | 11 | 5 | 1 | 18 |  | IO Available | 2 | 0 | 13 | 5 | 2 | 22
A Site | 1 | 0 | 4 | 1 | 0 | 6 |  | A Site | 1 | 0 | 4 | 1 | 1 | 7
B Site | 0 | 0 | 7 | 4 | 1 | 12 |  | B Site | 1 | 0 | 9 | 4 | 1 | 15
IO Note under Approval | 1 | 0 | 2 | 3 | 1 | 7 |  | IO Note under Approval | 1 | 0 | 2 | 3 | 1 | 7
A Site | 1 | 0 | 2 | 3 | 0 | 6 |  | A Site | 1 | 0 | 2 | 3 | 0 | 6
B Site | 0 | 0 | 0 | 0 | 1 | 1 |  | B Site | 0 | 0 | 0 | 0 | 1 | 1
Advance Tendering Approval | 2 | 0 | 4 | 1 | 0 | 7 |  | Advance Tendering Approval | 2 | 0 | 4 | 1 | 0 | 7
A Site | 2 | 0 | 4 | 1 | 0 | 7 |  | A Site | 2 | 0 | 4 | 1 | 0 | 7
B Site | 0 | 0 | 0 | 0 | 0 | 0 |  | B Site | 0 | 0 | 0 | 0 | 0 | 0
DM+NH NOC Available | 0 | 0 | 1 | 3 | 0 | 4 |  | DM+NH NOC Available | 0 | 0 | 1 | 3 | 0 | 4
A Site | 0 | 0 | 1 | 2 | 0 | 3 |  | A Site | 0 | 0 | 1 | 2 | 0 | 3
B Site | 0 | 0 | 0 | 1 | 0 | 1 |  | B Site | 0 | 0 | 0 | 1 | 0 | 1
Construction WIP at Site | 0 | 0 | 0 | 0 | 0 | 0 |  | Construction WIP at Site | 0 | 0 | 0 | 0 | 0 | 0
A Site | 0 | 0 | 0 | 0 | 0 | 0 |  | A Site | 0 | 0 | 0 | 0 | 0 | 0
B Site | 0 | 0 | 0 | 0 | 0 | 0 |  | B Site | 0 | 0 | 0 | 0 | 0 | 0
LOIs as on 01.02.2026 | 22 | 10 | 124 | 62 | 28 | 246 |  | LOIs as on 01.06.2026 | 22 | 10 | 124 | 62 | 28 | 246
Pre 2018/Govt | 1 | 5 | 5 | 9 | 3 | 23 |  | Pre 2018/Govt | 1 | 5 | 5 | 9 | 3 | 23
SRMP 2018-19 | 1 | 1 | 26 | 8 | 12 | 48 |  | SRMP 2018-19 | 1 | 1 | 26 | 8 | 12 | 48
SRMP 2023-24 | 20 | 4 | 93 | 45 | 13 | 175 |  | SRMP 2023-24 | 20 | 4 | 93 | 45 | 13 | 175
|  | Total | [9 empty] | A | A | A | A | A | A | A | A | A | D1 | D1 | D1 | D1 | D1 | D1 | D1 | D1 | D1 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | D2 | C | C | C | C | C | C | C | C | C | E | E | E | E | E | E | E | E | E | Already Commissioned | [11 empty] | Total
Commissionable in this FY A: Commissionable in this FY; Drawing A+B: Drawing; NOC Available A: NOC Available; IO Available A: IO Available; Commissionable in this FY A: Commissionable in this FY; NOC Available A: NOC Available; IO Available A: IO Available; Commissionable in this FY A: Commissionable in this FY; NOC Available A: NOC Available; IO Available A: IO Available; Commissionable in this FY A: Commissionable in this FY; NOC Available A: NOC Available; IO Available A: IO Available; Commissionable in this FY A: Commissionable in this FY; NOC Available A: NOC Available; IO Available A: IO Available; Commissionable in this FY A: Commissionable in this FY; NOC Available A: NOC Available; IO Available A: IO Available; A A: A; A B: A; B A: B; B B: B; C A: C; C B: C; D1 A: D1; D1 B: D1; D2 A: D2; D2 B: D2; E A: E; E B: E | All COM
RSA | Total | A | B | Total | A+B | A | B | Total | A | B | Total | A | B | otal | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | Total | A | B | A | B | A | B | A | B | A | B | A | B
Ahmednagar East RSA | 22 | 2 | 3 | 5 | 4 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ahmednagar West RSA | 33 | 1 | 9 | 10 | 9 | 1 | 0 | 1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 2 | 3 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Pune City RSA | 16 | 2 | 1 | 3 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pimpri Chinchwad RSA | 16 | 5 | 0 | 5 | 4 | 1 | 0 | 1 | 2 | 0 | 2 | 4 | 0 | 4 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Pune Saswad RSA | 28 | 4 | 5 | 9 | 9 | 1 | 1 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 7 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2
Pune Wagholi RSA | 34 | 2 | 6 | 8 | 7 | 0 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 5 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Hadapsar RSA | 17 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Tathawade RSA | 29 | 8 | 4 | 12 | 11 | 2 | 0 | 2 | 2 | 1 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 7 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
Satara West RSA | 25 | 2 | 3 | 5 | 4 | 0 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 4 | 0 | 1 | 1 | 0 | 2 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Satara East RSA | 31 | 1 | 2 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Shirdi RSA | 16 | 2 | 2 | 4 | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 267 | 30 | 35 | 65 | 57 | 7 | 4 | 11 | 10 | 13 | 23 | 6 | 1 | 7 | 1 | 0 | 1 | 2 | 0 | 2 | 16 | 18 | 34 | 2 | 1 | 3 | 5 | 9 | 14 | 7 | 8 | 15 | 3 | 1 | 4 | 2 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 9 | 1 | 2 | 3 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 8

## Planned in Nov Dec
SALES AREA | Pending LOI as on 01.04.2026 (As per Class of Market) | [7 empty] | Pending LOI as on 01.04.2026 (As per Type of Site) | [6 empty] | Commissionable LOI in FY 26-27 as on 01.04.2026 (As per Class of Market) | [7 empty] | Commissionable LOI as on 01.04.2026 (Type of Site) | [7 empty] | Current Commissionable & Non-Commisisonable LOI |  |  |  | Current Commissionable & Non-Commisisonable LOI (As per Class of Market) | [7 empty] | Total Commissionable LOI as on 01.04.2026 (As per Class of Market)
| A | B | C | D1 | D2 | E | Total |  | Govt | OPEN | OBC | SC | ST | PH | Total | A | B | C | D1 | D2 | E | Total |  | Govt | OPEN | OBC | SC | ST | Total |  |  | Commissionable | Non-Commissionable | Total |  | A | B | C | D1 | D2 | E | Total |  | A | B | C | D1 | D2 | E | Total
Ahmednagar East RSA | 0 | 0 | 1 | 8 | 10 | 3 | 22 |  | 0 | 7 | 7 | 3 | 5 | 0 | 22 | 0 | 0 | 0 | 3 | 4 | 1 | 8 |  | 0 | 0 | 4 | 2 | 2 | 8 |  |  | 14 | 8 | 22 |  | 0 | 0 | 1 | 2 | 4 | 1 | 8 |  | 0 | 0 | 0 | 6 | 6 | 2 | 14
Ahmednagar West RSA | 0 | 0 | 0 | 13 | 12 | 8 | 33 |  | 0 | 21 | 9 | 0 | 3 | 0 | 33 | 0 | 0 | 0 | 5 | 3 | 3 | 11 |  | 0 | 7 | 3 | 0 | 1 | 11 |  |  | 15 | 18 | 33 |  | 0 | 0 | 0 | 7 | 7 | 4 | 18 |  | 0 | 0 | 0 | 6 | 5 | 4 | 15
Pune City RSA | 12 | 0 | 1 | 2 | 1 | 0 | 16 |  | 0 | 9 | 5 | 1 | 1 | 0 | 16 | 2 | 0 | 0 | 1 | 0 | 0 | 3 |  | 0 | 2 | 0 | 0 | 1 | 3 |  |  | 3 | 13 | 16 |  | 10 | 0 | 1 | 1 | 1 | 0 | 13 |  | 2 | 0 | 0 | 1 | 0 | 0 | 3
Pimpri Chinchwad RSA | 10 | 0 | 1 | 5 | 0 | 0 | 16 |  | 0 | 12 | 0 | 2 | 2 | 0 | 16 | 5 | 0 | 0 | 1 | 0 | 0 | 6 |  | 0 | 4 | 0 | 1 | 1 | 6 |  |  | 7 | 9 | 16 |  | 5 | 0 | 1 | 3 | 0 | 0 | 9 |  | 5 | 0 | 0 | 2 | 0 | 0 | 7
Pune Saswad RSA | 0 | 0 | 0 | 18 | 4 | 6 | 28 |  | 0 | 12 | 5 | 7 | 4 | 0 | 28 | 0 | 0 | 0 | 7 | 0 | 2 | 9 |  | 0 | 5 | 1 | 2 | 1 | 9 |  |  | 13 | 15 | 28 |  | 0 | 0 | 0 | 8 | 4 | 3 | 15 |  | 0 | 0 | 0 | 10 | 0 | 3 | 13
Pune Wagholi RSA | 0 | 0 | 1 | 19 | 13 | 1 | 34 |  | 0 | 21 | 4 | 5 | 4 | 0 | 34 | 0 | 0 | 0 | 3 | 5 | 0 | 8 |  | 0 | 5 | 1 | 0 | 2 | 8 |  |  | 15 | 19 | 34 |  | 0 | 0 | 1 | 11 | 6 | 1 | 19 |  | 0 | 0 | 0 | 8 | 7 | 0 | 15
Pune Hadapsar RSA | 1 | 0 | 0 | 12 | 1 | 3 | 17 |  | 0 | 5 | 3 | 7 | 2 | 0 | 17 | 0 | 0 | 0 | 2 | 0 | 1 | 3 |  | 0 | 1 | 0 | 2 | 0 | 3 |  |  | 9 | 8 | 17 |  | 1 | 0 | 0 | 5 | 1 | 1 | 8 |  | 0 | 0 | 0 | 7 | 0 | 2 | 9
Pune Tathawade RSA | 2 | 0 | 2 | 15 | 6 | 4 | 29 |  | 2 | 13 | 4 | 10 | 0 | 0 | 29 | 1 | 0 | 0 | 6 | 2 | 2 | 11 |  | 0 | 7 | 1 | 3 | 0 | 11 |  |  | 17 | 12 | 29 |  | 0 | 0 | 2 | 5 | 3 | 2 | 12 |  | 2 | 0 | 0 | 10 | 3 | 2 | 17
Satara West RSA | 0 | 0 | 1 | 19 | 4 | 1 | 25 |  | 2 | 9 | 6 | 6 | 2 | 0 | 25 | 0 | 0 | 0 | 4 | 1 | 0 | 5 |  | 0 | 3 | 0 | 1 | 1 | 5 |  |  | 9 | 16 | 25 |  | 0 | 0 | 1 | 11 | 3 | 1 | 16 |  | 0 | 0 | 0 | 8 | 1 | 0 | 9
Satara East RSA | 0 | 0 | 4 | 15 | 9 | 3 | 31 |  | 4 | 12 | 5 | 7 | 3 | 0 | 31 | 0 | 0 | 0 | 4 | 0 | 1 | 5 |  | 0 | 3 | 1 | 1 | 0 | 5 |  |  | 7 | 24 | 31 |  | 0 | 0 | 3 | 10 | 9 | 2 | 24 |  | 0 | 0 | 1 | 5 | 0 | 1 | 7
Shirdi RSA | 0 | 0 | 0 | 8 | 6 | 2 | 16 |  | 1 | 3 | 7 | 3 | 2 | 0 | 16 | 0 | 0 | 0 | 3 | 2 | 1 | 6 |  | 0 | 0 | 3 | 1 | 2 | 6 |  |  | 10 | 6 | 16 |  | 0 | 0 | 0 | 3 | 2 | 1 | 6 |  | 0 | 0 | 0 | 5 | 4 | 1 | 10
Pune DO | 25 | 0 | 11 | 134 | 66 | 31 | 267 |  | 9 | 87 | 33 | 25 | 21 | 0 | 267 | 8 | 0 | 0 | 39 | 17 | 11 | 75 |  | 0 | 37 | 14 | 13 | 11 | 75 |  |  | 119 | 148 | 267 |  | 16 |  | 4 | 37 | 23 | 10 | 148 |  | 7 | 0 | 0 | 40 | 18 | 11 | 119
SALES AREA | Class of Marketwise Target-A Site | [7 empty] | Class of Marketwise Target- B Site | [6 empty] | Commissioning Status till Date- A Site | [7 empty] | Commissioning Status till Date- B Site | [7 empty] | MONTHWISE COMMISSIONING | [14 empty] | RO/KSK Commisisoning
| A | B | C | D1 | D2 | E | Total |  | A | B | C | D1 | D2 | E | Total | A | B | C | D1 | D2 | E | Total |  | A | B | C | D1 | D2 | E | Total |  | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total |  |  | RO | KSK | TOTAL
Ahmednagar East RSA | 0 | 0 | 0 | 3 | 1 | 0 | 4 |  | 0 | 0 | 0 | 0 | 3 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Ahmednagar West RSA | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  | 0 | 0 | 0 | 5 | 2 | 3 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune City RSA | 1 | 0 | 0 | 1 | 0 | 0 | 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pimpri Chinchwad RSA | 4 | 0 | 0 | 1 | 0 | 0 | 5 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune Saswad RSA | 0 | 0 | 0 | 4 | 0 | 0 | 4 |  | 0 | 0 | 0 | 3 | 0 | 2 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune Wagholi RSA | 0 | 0 | 0 | 1 | 1 | 0 | 2 |  | 0 | 0 | 0 | 2 | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune Hadapsar RSA | 0 | 0 | 0 | 2 | 0 | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune Tathawade RSA | 1 | 0 | 0 | 3 | 2 | 1 | 7 |  | 0 | 0 | 0 | 3 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Satara West RSA | 0 | 0 | 0 | 1 | 1 | 0 | 2 |  | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Satara East RSA | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 0 | 3 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Shirdi RSA | 0 | 0 | 0 | 1 | 2 | 1 | 4 |  | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune DO | 6 | 0 | 0 | 18 | 8 | 3 | 35 |  | 2 | 0 | 0 | 10 | 9 | 6 | 40 | 1 | 0 | 0 | 1 | 1 | 1 | 4 |  | 0 | 0 | 0 | 2 | 0 | 2 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
District | Class of Marketwise Target-A Site | [7 empty] | Class of Marketwise Target- B Site | [6 empty] | Commissioning Status till Date- A Site | [7 empty] | Commissioning Status till Date- B Site | [7 empty] | MONTHWISE COMMISSIONING | [14 empty] | RO/KSK Commisisoning
| A | B | C | D1 | D2 | E | Total |  | A | B | C | D1 | D2 | E | Total | A | B | C | D1 | D2 | E | Total |  | A | B | C | D1 | D2 | E | Total |  | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total |  |  | RO | KSK | TOTAL
Ahmadnagar | 0 | 0 | 0 | 4 | 4 | 1 | 9 |  | 0 | 0 | 0 | 7 | 4 | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune | 6 | 0 | 0 | 12 | 3 | 2 | 23 |  | 2 | 0 | 0 | 8 | 5 | 3 | 18 | 1 | 0 | 0 | 1 | 1 | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Satara | 0 | 0 | 0 | 2 | 1 | 0 | 3 |  | 0 | 0 | 0 | 6 | 0 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Pune DO | 6 | 0 | 0 | 18 | 8 | 3 | 35 |  | 2 | 0 | 0 | 21 | 9 | 8 | 40 | 1 | 0 | 0 | 1 | 1 | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
SALES AREA | Rental Negotiation Status (For Commissionable Sites) | [7 empty] | IO Status (For Targeted Locations) | [6 empty] | Advance Tendering Status (For Targeted Locations) |  |  |  |  | PESO Status (For Targeted Locations) |  |  |  |  | LSR Status (For Targeted Locations) | [6 empty] | NOC Available Status (For Targeted Locations) |  |  |  |  | NOC Available Status (For Targeted Locations) | [8 empty] | IO Awaited
| Total No of A Sites (Commissionable) |  | Rental Negotiation Done | Valuation Received, Negotiation Pending | Valuation Pending, Negotiation Pending |  |  |  | Total No of Sites | Site Commissioned | Sites Pending | IO Available | IO in Process | IO Note to be Initiated | Total | Total No of Sites | Adv Tendering approval Initiated and In Process | Adv Tendering approval Not Yet Initiated | Adv Tendering approval Obtained |  | Total No of Sites | CA Applied but not Yet Received | CA Received | CA Not Applied |  | Total No of Sites | LSR Received | LSR In Process | LSR Yet to be assigned | Total LSR | Total LSR |  | Total No of Sites | Site Commissioned | NOC Available | NOC in Process |  | RO-A | RO-B | Total | KSK-A | KSK-B | Total | Grand Total |  |  | RO-A | RO-B | Total | KSK-A | KSK-B | Total | Grand Total
Ahmednagar East RSA | 4 |  | 3 | 1 | 0 |  |  |  | 8 | 0 | 8 | 2 | 2 | 4 | 8 | 4 | 0 | 2 | 2 |  | 8 | 0 | 3 | 0 |  | 8 | 6 | 1 | 1 | 8 | 10 |  | 8 | 0 | 1 | 7 |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  |  | 2 | 1 | 3 | 0 | 0 | 0 | 3
Ahmednagar West RSA | 1 |  | 1 | 0 | 0 |  |  |  | 11 | 1 | 10 | 3 | 2 | 5 | 10 | 1 | 0 | 0 | 1 |  | 11 | 0 | 6 | 3 |  | 11 | 5 | 4 | 2 | 11 | 17 |  | 11 | 1 | 1 | 10 |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  |  | 1 | 2 | 3 | 0 | 3 | 3 | 6
Pune City RSA | 2 |  | 1 | 1 | 0 |  |  |  | 3 | 0 | 3 | 1 | 0 | 2 | 3 | 2 | 0 | 1 | 1 |  | 3 | 0 | 2 | 0 |  | 3 | 1 | 2 | 0 | 3 | 5 |  | 3 | 0 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 2
Pimpri Chinchwad RSA | 5 |  | 3 | 1 | 0 |  |  |  | 6 | 1 | 5 | 2 | 1 | 2 | 5 | 5 | 0 | 2 | 3 |  | 6 | 0 | 5 | 1 |  | 6 | 5 | 1 | 0 | 6 | 7 |  | 6 | 1 | 1 | 5 |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  |  | 3 | 0 | 3 | 0 | 0 | 0 | 3
Pune Saswad RSA | 4 |  | 3 | 1 | 0 |  |  |  | 9 | 2 | 7 | 1 | 1 | 5 | 7 | 4 | 0 | 1 | 3 |  | 9 | 0 | 9 | 0 |  | 9 | 4 | 5 | 0 | 9 | 14 |  | 9 | 2 | 2 | 7 |  | 1 | 0 | 1 | 0 | 1 | 1 | 2 |  |  | 2 | 3 | 5 | 0 | 1 | 1 | 6
Pune Wagholi RSA | 2 |  | 0 | 2 | 0 |  |  |  | 8 | 0 | 8 | 3 | 0 | 5 | 8 | 2 | 0 | 2 | 0 |  | 8 | 0 | 6 | 1 |  | 8 | 4 | 2 | 2 | 8 | 12 |  | 8 | 0 | 1 | 7 |  | 0 | 1 | 1 | 0 | 0 | 0 | 1 |  |  | 2 | 3 | 5 | 0 | 0 | 0 | 5
Pune Hadapsar RSA | 3 |  | 1 | 1 | 0 |  |  |  | 3 | 0 | 3 | 1 | 0 | 2 | 3 | 3 | 0 | 2 | 1 |  | 3 | 0 | 2 | 0 |  | 3 | 1 | 2 | 0 | 3 | 5 |  | 3 | 0 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Tathawade RSA | 7 |  | 3 | 4 | 0 |  |  |  | 11 | 2 | 9 | 1 | 1 | 7 | 9 | 7 | 0 | 4 | 3 |  | 11 | 0 | 10 | 1 |  | 11 | 5 | 6 | 0 | 11 | 17 |  | 11 | 2 | 2 | 9 |  | 1 | 0 | 1 | 1 | 0 | 1 | 2 |  |  | 5 | 2 | 7 | 0 | 1 | 1 | 8
Satara West RSA | 2 |  | 0 | 2 | 0 |  |  |  | 5 | 1 | 4 | 1 | 0 | 3 | 4 | 2 | 0 | 2 | 0 |  | 5 | 0 | 4 | 0 |  | 5 | 1 | 4 | 0 | 5 | 9 |  | 5 | 1 | 1 | 4 |  | 0 | 1 | 1 | 0 | 0 | 0 | 1 |  |  | 2 | 1 | 3 | 0 | 0 | 0 | 3
Satara East RSA | 1 |  | 1 | 0 | 0 |  |  |  | 5 | 1 | 4 | 4 | 0 | 0 | 4 | 1 | 0 | 0 | 1 |  | 5 | 0 | 5 | 0 |  | 5 | 4 | 1 | 0 | 5 | 6 |  | 5 | 1 | 2 | 3 |  | 1 | 0 | 1 | 0 | 1 | 1 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shirdi RSA | 4 |  | 3 | 0 | 0 |  |  |  | 6 | 0 | 6 | 3 | 0 | 3 | 6 | 4 | 0 | 2 | 2 |  | 6 | 1 | 2 | 1 |  | 6 | 3 | 2 | 1 | 6 | 9 |  | 6 | 0 | 0 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 2
Pune DO | 35 |  | 19 | 13 | 0 |  |  |  | 75 | 8 | 67 | 22 | 7 | 38 | 67 | 35 | 0 | 18 | 17 |  | 75 | 1 | 33 | 7 |  | 75 | 39 | 30 | 6 | 75 | 111 |  | 75 | 8 | 11 | 64 |  | 6 | 2 | 8 | 1 | 2 | 3 | 11 |  |  | 19 | 14 | 33 | 0 | 5 | 5 | 38
RSA | MONTHWISE LOI CANCELATION
| 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | [12 empty] | 0
Ahmednagar West RSA | [12 empty] | 0
Pune City RSA | [12 empty] | 0
Pimpri Chinchwad RSA | [12 empty] | 0
Pune Saswad RSA | [12 empty] | 0
Pune Wagholi RSA | [12 empty] | 0
Pune Hadapsar RSA | [12 empty] | 0
Pune Tathawade RSA | [12 empty] | 0
Satara West RSA | [12 empty] | 0
Satara East RSA | [12 empty] | 0
Shirdi RSA | [12 empty] | 0
Pune DO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RSA | MONTHWISE LOI ISSUANCE
| 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | [12 empty] | 0
Ahmednagar West RSA | [12 empty] | 0
Pune City RSA | [12 empty] | 0
Pimpri Chinchwad RSA | [12 empty] | 0
Pune Saswad RSA | [12 empty] | 0
Pune Wagholi RSA | [12 empty] | 0
Pune Hadapsar RSA | [12 empty] | 0
Pune Tathawade RSA | [12 empty] | 0
Satara West RSA | [12 empty] | 0
Satara East RSA | [12 empty] | 0
Shirdi RSA | [12 empty] | 0
Pune DO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Review PPT update
A
RSA Name | Total LOI Available for FY 2026-27 | Total Commissionable LOI | Commissionable LOI in FY 2026-27 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ahmednagar West RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune City RSA | 12 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
Pimpri Chinchwad RSA | 10 | 5 | 5 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 5
Pune Saswad RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Wagholi RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Hadapsar RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Tathawade RSA | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Satara West RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Satara East RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shirdi RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 22 | 9 | 8 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 1 | 8
D1
RSA Name | Total LOI Available for FY 2026-27 | Total Commissionable LOI | Commissionable LOI in FY 2026-27 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3
Ahmednagar West RSA | 13 | 6 | 5 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 5
Pune City RSA | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Pimpri Chinchwad RSA | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Pune Saswad RSA | 18 | 10 | 7 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 7
Pune Wagholi RSA | 19 | 8 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 3
Pune Hadapsar RSA | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
Pune Tathawade RSA | 15 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 3 | 6
Satara West RSA | 19 | 8 | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Satara East RSA | 15 | 5 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 4
Shirdi RSA | 8 | 5 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 3
Total | 134 | 68 | 39 | 0 | 3 | 6 | 1 | 3 | 3 | 3 | 4 | 2 | 6 | 5 | 3 | 39
C
RSA Name | Total LOI Available for FY 2026-27 | Total Commissionable LOI | Commissionable LOI in FY 2026-27 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ahmednagar West RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune City RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pimpri Chinchwad RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Saswad RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Wagholi RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Hadapsar RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Tathawade RSA | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Satara West RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Satara East RSA | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shirdi RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D2
RSA Name | Total LOI Available for FY 2025-26 | Total Commissionable LOI | Commissionable LOI in FY 2025-26 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | 10 | 6 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 4
Ahmednagar West RSA | 12 | 5 | 3 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Pune City RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pimpri Chinchwad RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Saswad RSA | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Wagholi RSA | 13 | 7 | 5 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 5
Pune Hadapsar RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Tathawade RSA | 6 | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Satara West RSA | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
Satara East RSA | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shirdi RSA | 6 | 4 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Total | 66 | 26 | 17 | 0 | 1 | 5 | 1 | 1 | 3 | 2 | 0 | 1 | 2 | 0 | 1 | 17
E
RSA Name | Total LOI Available for FY 2026-27 | Total Commissionable LOI | Commissionable LOI in FY 2026-27 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Ahmednagar West RSA | 8 | 4 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3
Pune City RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pimpri Chinchwad RSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Saswad RSA | 6 | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
Pune Wagholi RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Hadapsar RSA | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Pune Tathawade RSA | 4 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2
Satara West RSA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Satara East RSA | 3 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Shirdi RSA | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
Total | 31 | 15 | 11 | 1 | 2 | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 11
All COM
RSA Name | Total LOI Available for FY 2026-27 | Total Commissionable LOI | Commissionable LOI in FY 2026-27 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | 22 | 14 | 8 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 3 | 0 | 0 | 8
Ahmednagar West RSA | 33 | 15 | 11 | 0 | 1 | 4 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 11
Pune City RSA | 16 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 3
Pimpri Chinchwad RSA | 16 | 7 | 6 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 6
Pune Saswad RSA | 28 | 13 | 9 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 9
Pune Wagholi RSA | 34 | 15 | 8 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 8
Pune Hadapsar RSA | 17 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 3
Pune Tathawade RSA | 29 | 17 | 11 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 2 | 3 | 11
Satara West RSA | 25 | 9 | 5 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5
Satara East RSA | 31 | 7 | 5 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 5
Shirdi RSA | 16 | 10 | 6 | 0 | 0 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 6
Total | 267 | 119 | 75 | 1 | 7 | 12 | 3 | 5 | 7 | 7 | 4 | 7 | 9 | 7 | 6 | 75
Other Than A and D1 COM
RSA Name | Total LOI Available for FY 2026-27 | Total Commissionable LOI | Commissionable LOI in FY 2026-27 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
Ahmednagar East RSA | 22 | 8 | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 5
Ahmednagar West RSA | 33 | 9 | 6 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6
Pune City RSA | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pimpri Chinchwad RSA | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pune Saswad RSA | 28 | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
Pune Wagholi RSA | 34 | 7 | 5 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 5
Pune Hadapsar RSA | 17 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Pune Tathawade RSA | 29 | 5 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4
Satara West RSA | 25 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
Satara East RSA | 31 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Shirdi RSA | 16 | 5 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3
Total | 267 | 42 | 28 | 1 | 3 | 6 | 1 | 2 | 3 | 4 | 0 | 2 | 3 | 1 | 2 | 28

## OMC Last 10 Years
| IOCL | IOCL | IOCL | IOCL | IOCL | IOCL | BPCL | BPCL | BPCL | BPCL | BPCL | BPCL | HPCL | HPCL | HPCL | HPCL | HPCL | HPCL | PSU | PSU | PSU | PSU | PSU | Gross Total | IOCL | BPCL | HPCL
| A | C | D1 | D2 | E | Total | A | C | D1 | D2 | E | Total | A | C | D1 | D2 | E | Total | A | C | D1 | D2 | E
2015-16 | 0 | 0 | 11 | 4 | 3 | 18 | 5 | 2 | 10 | 5 | 0 | 22 | 1 | 2 | 8 | 11 | 1 | 23 | 6 | 4 | 29 | 20 | 4 | 63 | 28.57% | 34.92% | 36.51%
2016-17 | 2 | 1 | 4 | 7 | 4 | 18 | 0 | 0 | 2 | 2 | 2 | 6 | 1 | 0 | 8 | 2 | 3 | 14 | 3 | 1 | 14 | 11 | 9 | 38 | 47.37% | 15.79% | 36.84%
2017-18 | 1 | 0 | 7 | 10 | 4 | 22 | 4 | 0 | 6 | 7 | 7 | 24 | 3 | 1 | 11 | 6 | 3 | 24 | 8 | 1 | 24 | 23 | 14 | 70 | 31.43% | 34.29% | 34.29%
2018-19 | 2 | 0 | 4 | 2 | 5 | 13 | 0 | 0 | 6 | 7 | 5 | 18 | 2 | 4 | 3 | 3 | 1 | 13 | 4 | 4 | 13 | 12 | 11 | 44 | 29.55% | 40.91% | 29.55%
2019-20 | 1 | 0 | 8 | 4 | 3 | 16 | 5 | 2 | 5 | 11 | 4 | 27 | 3 | 2 | 7 | 2 | 3 | 17 | 9 | 4 | 20 | 17 | 10 | 60 | 26.67% | 45% | 28.33%
2020-21 | 3 | 3 | 14 | 12 | 12 | 44 | 5 | 7 | 11 | 11 | 13 | 47 | 9 | 3 | 13 | 13 | 5 | 43 | 17 | 13 | 38 | 36 | 30 | 134 | 32.84% | 35.07% | 32.09%
2021-22 | 2 | 0 | 26 | 11 | 17 | 56 | 5 | 2 | 12 | 6 | 8 | 33 | 8 | 4 | 19 | 15 | 5 | 51 | 15 | 6 | 57 | 32 | 30 | 140 | 40% | 23.57% | 36.43%
2022-23 | 0 | 0 | 11 | 6 | 9 | 26 | 0 | 2 | 7 | 5 | 4 | 18 | 3 | 4 | 16 | 3 | 5 | 31 | 3 | 6 | 34 | 14 | 18 | 75 | 34.67% | 24% | 41.33%
2024-25 | 0 | 2 | 8 | 11 | 3 | 24 | 4 | 3 | 18 | 7 | 6 | 38 | 3 | 2 | 20 | 9 | 5 | 39 | 7 | 7 | 46 | 27 | 14 | 101 | 23.76% | 37.62% | 38.61%
2025-26 | 0 | 0 | 7 | 2 | 2 | 11 | 1 | 0 | 7 | 3 | 0 | 11 | 4 | 2 | 2 | 1 | 1 | 10 | 5 | 2 | 16 | 6 | 3 | 32 | 34.38% | 34.38% | 31.25%
Total | 11 | 6 | 100 | 69 | 62 | 248 | 29 | 18 | 84 | 64 | 49 | 244 | 37 | 24 | 107 | 65 | 32 | 265 | 77 | 48 | 291 | 198 | 143 | 757 | 32.76% | 32.23% | 35.01%
| IOCL | IOCL | IOCL | IOCL | IOCL | IOCL | BPCL | BPCL | BPCL | BPCL | BPCL | BPCL | HPCL | HPCL | HPCL | HPCL | HPCL | HPCL | IOCL | BPCL | HPCL
| A | C | D1 | D2 | E | Total | A | C | D1 | D2 | E | Total | A | C | D1 | D2 | E | Total
2015-16 | 0% | 0% | 37.93% | 20% | 75% | 28.57% | 83.33% | 50% | 34.48% | 25% | 0% | 34.92% | 16.67% | 50% | 27.59% | 55% | 25% | 36.51% | 28.57% | 34.92% | 36.51%
2016-17 | 66.67% | 100% | 28.57% | 63.64% | 44.44% | 47.37% | 0% | 0% | 14.29% | 18.18% | 22.22% | 15.79% | 33.33% | 0% | 57.14% | 18.18% | 33.33% | 36.84% | 47.37% | 15.79% | 36.84%
2017-18 | 12.5% | 0% | 29.17% | 43.48% | 28.57% | 31.43% | 50% | 0% | 25% | 30.43% | 50% | 34.29% | 37.5% | 100% | 45.83% | 26.09% | 21.43% | 34.29% | 31.43% | 34.29% | 34.29%
2018-19 | 50% | 0% | 30.77% | 16.67% | 45.45% | 29.55% | 0% | 0% | 46.15% | 58.33% | 45.45% | 40.91% | 50% | 100% | 23.08% | 25% | 9.091% | 29.55% | 29.55% | 40.91% | 29.55%
2019-20 | 11.11% | 0% | 40% | 23.53% | 30% | 26.67% | 55.56% | 50% | 25% | 64.71% | 40% | 45% | 33.33% | 50% | 35% | 11.76% | 30% | 28.33% | 26.67% | 45% | 28.33%
2020-21 | 17.65% | 23.08% | 36.84% | 33.33% | 40% | 32.84% | 29.41% | 53.85% | 28.95% | 30.56% | 43.33% | 35.07% | 52.94% | 23.08% | 34.21% | 36.11% | 16.67% | 32.09% | 32.84% | 35.07% | 32.09%
2021-22 | 13.33% | 0% | 45.61% | 34.38% | 56.67% | 40% | 33.33% | 33.33% | 21.05% | 18.75% | 26.67% | 23.57% | 53.33% | 66.67% | 33.33% | 46.88% | 16.67% | 36.43% | 40% | 23.57% | 36.43%
2022-23 | 0% | 0% | 32.35% | 42.86% | 50% | 34.67% | 0% | 33.33% | 20.59% | 35.71% | 22.22% | 24% | 100% | 66.67% | 47.06% | 21.43% | 27.78% | 41.33% | 34.67% | 24% | 41.33%
2024-25 | 0% | 28.57% | 17.39% | 40.74% | 21.43% | 23.76% | 57.14% | 42.86% | 39.13% | 25.93% | 42.86% | 37.62% | 42.86% | 28.57% | 43.48% | 33.33% | 35.71% | 38.61% | 23.76% | 37.62% | 38.61%
2025-26 | 0% | 0% | 43.75% | 33.33% | 66.67% | 34.38% | 20% | 0% | 43.75% | 50% | 0% | 34.38% | 80% | 100% | 12.5% | 16.67% | 33.33% | 31.25% | 34.38% | 34.38% | 31.25%
Total | 14.29% | 12.5% | 34.36% | 34.85% | 43.36% | 32.76% | 37.66% | 37.5% | 28.87% | 32.32% | 34.27% | 32.23% | 48.05% | 50% | 36.77% | 32.83% | 22.38% | 35.01% | 32.76% | 32.23% | 35.01%

## Planned 50 Sites
Sl No | Name of Location | COM | Type | Date of LOI | NOC Status | IO Status | Tendering Status | Planned month of NOC | Planned month of IO | Planned month of Commissioning
1 | Within 6 Km from Atmaram Baba Mandir,Mandali towards Solapur on Ahmednagar-Solapur NH | D1 | B | 2024-06-17 | Available | Yes | Not Required | 2026-04-01 | Available | 2026-04-01
2 | From Jadhavwadi to Laxmi Chowk on DP Road | A | A | 2024-01-31 | Pending | Yes | Yes | 2026-04-01 | Available | 2026-04-01
3 | Village Yelse on MDR (Pawna lake to Kamshet Road) | E | A | 2024-01-24 | Available | Yes | Yes | 2026-03-01 | Available | 2026-04-01
4 | From Navnagapur to Shendi on Shendi Bypass | D2 | A | 2024-02-27 | Pending | No | Yes | 2026-04-01 | 2026-04-01 | 2026-05-01
5 | Within 3km From Jawakhede Khalsa Primary Health Sub Centre Towards Miri on Miri-Tisgaon Road (MDR) | E | B | 2025-02-11 | Pending | No | Not Required | 2026-04-01 | 2026-04-01 | 2026-05-01
6 | At Village Karhavagaj on Jejuri-Morgaon-Baramati Road | D2 | A | 2024-09-12 | Pending | Yes | Yes | 2026-05-01 | Available | 2026-05-01
7 | Within 3 KM from Akshata Mangal Karyalaya towards Taklibhan on Shrirampur Nevasa SH | D2 | B | 2023-11-27 | Pending | Yes | Not Required | 2026-05-01 | Available | 2026-05-01
8 | Within 2 Km from DBM English Medium School on either side on Parner to Pune Highway (SH) | D2 | A | 2024-03-06 | Pending | No | Pending | 2026-04-01 | 2026-04-01 | 2026-05-01
9 | From Km Stone 8 to Km Stone 12 on Ahmednagar-Daund NH | D1 | B | 2024-06-15 | Pending | Yes | Not Required | 2026-05-01 | Available | 2026-05-01
10 | From Bhigwan Circle to Dalaj Phata on RHS of Pune- Solapur Highway | D1 | A | 2024-06-20 | Pending | Yes | Yes | 2026-05-01 | Available | 2026-05-01
11 | From Bahul to Sablewadi on LHS on NH (Chakan-Shikrapur Road) | D1 | B | 2024-06-13 | Pending | Yes | Not Required | 2026-01-01 | Available | 2026-06-01
12 | From Talegaon Damdhere to Dhanore within 2km on SH (Talegaon Dhamdere - Pimpri Sandas Road) | D2 | B | 2025-11-03 | Pending | No | Not Required | 2026-05-01 | 2026-04-01 | 2026-06-01
13 | WITHIN 5 KM FROM DHEBEWADI PHATA KARAD TOWARDS SATARA ON LHS OF KARAD TO SATARA ROAD | D1 | B | 2023-12-11 | Pending | Yes | Not Required | 2026-05-01 | Available | 2026-06-01
14 | FROM SHITPUR PHATA TO NIMBODI PHATA ON SHRIGONDA - JAMKHED ROAD | D1 | B | 2024-02-27 | Pending | Yes | Not Required | 2026-05-01 | Available | 2026-07-01
15 | On RHS of Pune-Solapur NH, From Vangali to intersection of Indapur Bypass & Baramati Highway | D1 | A | 2024-01-16 | Pending | Yes | Yes | 2026-05-01 | Available | 2026-07-01
16 | AT VADAPURI ON LHS OF INDAPUR-AKLUJ ROAD , | D1 | A | 2023-03-27 | Pending | No | Pending | 2026-06-01 | 2026-04-01 | 2026-07-01
17 | From Kasar-Dumala to Chikhali on Sangamner Akole SH | D2 | A | 2023-12-19 | Pending | Yes | Pending | 2026-05-01 | Available | 2026-07-01
18 | Within 4km from Within 4 km from M.M.Nirhali College, Pathardi towards baramat on Baramati-Amrapur SH | D2 | B | 2024-07-06 | Pending | Yes | Not Required | 2026-06-01 | Available | 2026-07-01
19 | Within 3 KM from Varunji Phata Karad Towards Chiplun On Karad Chiplun Road | D1 | B | 2024-06-15 | Pending | No | Not Required | 2026-07-01 | 2026-06-01 | 2026-08-01
20 | ON NH-4 BETWEEN KM STONE 760 TO 755 LHS OF PUNE TO SATARA ROAD | D1 | B | 2019-03-12 | Pending | Yes | Not Required | 2026-07-01 | Available | 2026-08-01
21 | Within 3 Km from Ghodegaon Sonai Chowk towards Ahmednagar on Pune-Aurangabad NH | D1 | A | 2023-12-14 | Pending | No | Pending | 2026-07-01 | 2026-06-01 | 2026-09-01
22 | Bhose to Shelpimpalgaon on LHS on Chakan Shikrapur Road | D1 | A | 2025-01-02 | Pending | No | Yes | 2026-01-01 | 2026-04-01 | 2026-09-01
23 | On RHS from Chandni Chowk to Bhugaon Gram Panchayat on National Highway | A | A | 2024-12-06 | Pending | Yes | Yes | 2026-09-01 | Available | 2026-09-01
24 | WITH IN 5 KM FROM MORGAON ON LHS OF MORGAON -BARAMATI ROAD , | D2 | A | 2023-05-01 | Pending | No | Pending | 2026-07-01 | 2026-06-01 | 2026-09-01
25 | From Kapurhol to Kikvi on RHS on NH (Pune-Bangalore Highway) | D1 | B | 2024-06-17 | Pending | Yes | Not Required | 2026-07-01 | Available | 2026-09-01
26 | Moshi Chowk on Pune Nashik Road to Talwade Chowk on LHS on Dehu Alandi Road (within PCMC Limits ) | A | A | 2024-02-01 | Pending | No | Yes | 2024-12-01 | 2026-06-01 | 2026-10-01
27 | Within 2 KM from Medha Bus Stand towards Satara on Mahabaleshwar Satara Road | D2 | A | 2024-02-16 | Pending | No | Pending | 2026-09-01 | 2026-08-01 | 2026-10-01
28 | From Village Walwane to Village Raytale on Supe Sarolakasar Road SH | D2 | B | 2023-12-15 | Pending | No | Not Required | 2026-09-01 | 2026-06-01 | 2026-10-01
29 | From km stone 56 to 58 on RHS on SH (Belhe -Jejuri road) | D2 | B | 2024-06-13 | Pending | No | Not Required | 2026-09-01 | 2026-06-01 | 2026-10-01
30 | From Village Pargaon Shingave to Village Manjarwadi on RHS on SH | D2 | B | 2024-01-18 | Pending | No | Not Required | 2026-09-01 | 2026-06-01 | 2026-10-01
31 | On RHS From Venavadi to Ambeghar on National Highway (Bhor-Shirwal Road) | D1 | B | 2024-06-21 | Pending | No | Not Required | 2026-10-01 | 2026-06-01 | 2026-11-01
32 | From ALAGUDEWADI To SOMANTHALI ON PHALTAN BARAMATI ROAD | D1 | B | 2023-12-05 | Pending | Yes | Not Required | 2026-10-01 | Available | 2026-11-01
33 | From Sus-Pashan Bridge to Bavdhan on RHS on NH (Pune-Bangalore Highway) | A | A | 2024-10-15 | Pending | No | Pending | 2026-09-01 | 2026-08-01 | 2026-12-01
34 | Within 2km from Shivaji Maharaj Square to Narayangaon on SH | D2 | A | 2026-02-17 | Pending | No | Pending | 2026-10-01 | 2026-08-01 | 2026-12-01
35 | From Dahigaon Ne. to Khamgaon on Dahigaon-Khamgaon Road | E | B | 2024-06-13 | Pending | No | Not Required | 2026-11-01 | 2026-06-01 | 2026-12-01
36 | From Nhavare to Nirvi on NH (Nhavare-Shrigonda Road) | D1 | B | 2024-01-23 | Pending | No | Not Required | 2026-11-01 | 2026-06-01 | 2026-12-01
37 | From Chanda to Fattepur on Ghodegaon-Kukana SH | D2 | B | 2024-06-18 | Pending | No | Not Required | 2026-12-01 | 2026-06-01 | 2027-01-01
38 | Village Hivere zare, On Ahmednagar Daund Road (NH) | D1 | B | 2025-07-01 | Pending | No | Not Required | 2026-12-01 | 2026-06-01 | 2027-01-01
39 | From Undri Chowk to Mantarwadi Chowk towards Pune Saswad Road,Urlidevachi on NH | D1 | A | 2024-02-12 | Pending | Yes | Yes | 2026-10-01 | Available | 2027-01-01
40 | From Kanheri-Katewadi to Junction on LHS on Baramti-Indapur NH | D1 | B | 2024-01-23 | Pending | No | Not Required | 2026-12-01 | 2026-06-01 | 2027-01-01
41 | From Kanheri-Katewadi to Junction on RHS on Baramati-Indapur NH | D1 | B | 2024-06-18 | Pending | No | Not Required | 2026-12-01 | 2026-06-01 | 2027-01-01
42 | From Ghusalkhamb Naka to Muleshwar temple on Lonavala Ambey Valley Road | E | B | 2023-12-13 | Pending | No | Not Required | 2026-12-01 | 2026-06-01 | 2027-01-01
43 | Village Barhanpur, on RHS towards Patas on NH (Baramati Patas Road) | D1 | B | 2024-06-13 | Pending | No | Not Required | 2026-12-01 | 2026-06-01 | 2027-01-01
44 | From Kasari to Kodhapuri on RHS on NH (Pune-Ahmednagar Road) | D1 | A | 2024-06-19 | Pending | No | Pending | 2026-11-01 | 2026-08-01 | 2027-01-01
45 | Within 4 kms from Warje Bridge towards Takalwadi in Shivane , Pune | A | B | 2023-11-23 | Pending | No | Not Required | 2027-01-01 | 2026-06-01 | 2027-02-01
46 | Within 5 km from Sub-registrar Office, Paud on Mulshi- Chandni Chowk Highway towards Pirangut | D1 | A | 2025-07-30 | Pending | No | Pending | 2027-01-01 | 2026-08-01 | 2027-02-01
47 | Village Murti (Taluka Baramati) on National Highway 965D | D1 | A | 2024-06-18 | Pending | No | Pending | 2027-02-01 | 2026-08-01 | 2027-03-01
48 | From Talegaon Dabhade Phata to Vadgaon on NH(Pune-Bangalore Highway) | D1 | A | 2025-12-06 | Pending | No | Pending | 2027-02-01 | 2026-08-01 | 2027-03-01
49 | From Garade to Khed Shivapur on Khed-Shivapur-Saswad Link Road | E | B | 2025-04-29 | Pending | No | Not Required | 2027-02-01 | 2026-06-01 | 2027-03-01
50 | From Pabal to Kanhur Mesai on SH (Shirur-Pabal Road) | D2 | B | 2026-02-18 | Pending | No | Not Required | 2027-02-01 | 2026-06-01 | 2027-03-01
Formulas:
Planned month of IO = +EOMONTH([Planned month of NOC],-2)+1

## NOC and Advance Tender Sites
SN | Location | Retail Sales Area | Market Class | Type | RO/KSK | Reamrks
1 | Within 4 km from Manchar to Peth on LHS on NH (Pune-Nashik Road) | Pune Wagholi RSA | D1 | A | RO | #N/A
2 | From KM Stone 47 to 50 on LHS on NH (Pune-Nashik Road) | Pune Wagholi RSA | D1 | A | RO | #N/A
3 | Within 2 KM from Mundhwa Chowk towards Keshavnagar in Keshav Nagar Road | Pune City RSA | A | B | RO | #N/A
4 | Inside Nanded city, Pune | Pune City RSA | A | A | RO | #N/A
5 | SHANKARSHETH ROAD, PUNE CITY, | Pune City RSA | A | A | RO | #N/A

## Sheet1
Sl No | Name of Location | Date of LOI | NOC Status | IO Status | Tendering Status | Planned month of Final NOC | Planned month of IO | Planned month of Commissioning
1 | From Dange Chowk to Sant Tukaram Maharaj Bridge under PCMC Limits | #N/A | #N/A | #N/A | Yes | #N/A | #N/A | Commissioned in Nov'25
2 | SHANKARSHETH ROAD, PUNE CITY, | #N/A | #N/A | #N/A | Yes | #N/A | #N/A | #REF!
3 | Inside Nanded city, Pune | #N/A | #N/A | #N/A | Yes | #N/A | #N/A | Commissioned in Nov'25
4 | On RHS from Chandni Chowk to Bhugaon Gram Panchayat on National Highway | 2024-12-06 | 0 | Yes | Yes | 2026-09-01 | NA | #REF!
5 | Within 2 KM from Mundhwa Chowk towards Keshavnagar in Keshav Nagar Road | #N/A | #N/A | #N/A | NA | #N/A | #N/A | #REF!
6 | From Jadhavwadi to Laxmi Chowk on DP Road | 2024-01-31 | Yes | Yes | Yes | 2026-04-01 | NA | #REF!
7 | Dehu Phata to Moshi Chowk on RHS on Dehu - Alandi Road | 2024-06-19 | 0 | Yes | NA | 2026-07-01 | NA | #REF!
8 | From Sus-Pashan Bridge to Bavdhan on RHS on NH (Pune-Bangalore Highway) | 2024-10-15 | 0 | 2026-09-02 | No | 2026-09-01 | 2026-09-02 | #REF!
D1_1
Sl No | Name of Location | Date of LOI | NOC Status | IO Status | Tendering Status | Planned month of Final NOC | Planned month of IO | Planned month of Commissioning
1 | From Sardewadi Toll Plaza to intersection of Indapur Bypass & Baramati Highway towards Pune | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
2 | From Koregaon Bhima to Sanaswadi on RHS on NH (PUNE-AHMEDNAGAR ROAD) | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
3 | Within 2 Km from Bhairavnath Temple (Agaskhand) towards Kharwadi on Kalyan-Nirmal NH | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
4 | From Darewadi MIRC to Bypass Road on Ahmednagar-Solapur NH | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
5 | From KM stone 44 to KM stone 52 on LHS OF PUNE SOLAPUR NH | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
6 | From Village Nade to Village Patan on Karad Chiplun Road | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
7 | INDURI TO DEHUGAON ROAD JUNCTION ON TALEGAON CHAKAN ROAD, | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
8 | From Village Atit To Village Kashil On LHS of Satara To Karad NH | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
9 | From Supe to Morgaon on NH (Nira Supe Highway) | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
10 | From Wadala Bahiroba to Babhulwedhe towards Nevasa on Pune-Aurangabad NH | #N/A | #N/A | #N/A | No | #N/A | #N/A | #REF!
D1_2
Sl No | Name of Location | Date of LOI | NOC Status | IO Status | Tendering Status | Planned month of Final NOC | Planned month of IO | Planned month of Commissioning
Within 2km On either side of Army Cadet Public School on Ahmednagar-Solapur NH
Within 3 Km from Pandit Jawaharlal Nehru School and Junior College of Science towards Jamkhed on Adhalgaon-Jamkhed NH
From Bahul to Sablewadi on LHS on NH (Chakan-Shikrapur Road)
From Kalamb to Narayangaon on RHS on NH (Pune-Nashik Road)
From KM Stone 47 to 50 on LHS on NH (Pune-Nashik Road)
On RHS of Pune-Solapur NH, From Vangali to intersection of Indapur Bypass & Baramati Highway
From Rajuri to Alephata on LHS on NH (Ahmednagar- Kalyan Road)
Within 6 Km from Atmaram Baba Mandir,Mandali towards Solapur on Ahmednagar-Solapur NH
From Km Stone 8 to Km Stone 12 on Ahmednagar-Daund NH
From Pusegaon to Nidhal on Satara Pandharpur Road
D1_3
Sl No | Name of Location | Date of LOI | NOC Status | IO Status | Tendering Status | Planned month of Final NOC | Planned month of IO | Planned month of Commissioning
From Kanheri-Katewadi to Junction on LHS on Baramti-Indapur NH
Village Barhanpur, on RHS towards Patas on NH (Baramati Patas Road)
ON SH-60(NH753F)LHS FROM PUNE TO AHMEDNAGAR BETWEEN KM STONE NO. 367 TO 372
From Undri Chowk to Mantarwadi Chowk towards Pune Saswad Road,Urlidevachi on NH
Within 4 km from Manchar to Peth on LHS on NH (Pune-Nashik Road)
From Vadapuri to Vakilwasti on LHS of Indapur-Akluj NH
Shelpimpalgaon to Bahul on RHS on Chakan Shikrapur Road
From Bhigwan Circle to Dalaj Phata on RHS of Pune- Solapur Highway
From Datta Chowk Karad to Rajmachi on Karad Vita Road
on RHS From Khadki to Bhigwan Circle on Pune-Solapur NH
Formulas:
Date of LOI = VLOOKUP([Name of Location],'LOI and Commissioning Master Sh'!B:M,12,0)
NOC Status = VLOOKUP([Name of Location],'LOI and Commissioning Master Sh'!B:AC,28,0)
Planned month of Final NOC = VLOOKUP([Name of Location],'LOI and Commissioning Master Sh'!B:AD,29,0)
IO Status = VLOOKUP([Name of Location],'LOI and Commissioning Master Sh'!B:Y,24,0)